## FinalOutput
PK | Route | Location Description | From | To | From RP | To RP | PvmtArea | RC | FA | Planned Project | # Lanes | Surf Type | NHS | Sub | Unit | County | AADT | AADTT | Chipable | Replacement cycle (years) | Adjusted Replacement cycle (years) | Year of latest project completion | 20y Project plan 1 | 20y Project plan 2 | 20y Project plan 3 | 20y Project plan 4 | 20y Project plan 5 | 20y chip seal 3rd phase plan | Planned rpm project by David | 20y Project plan 1_description | 20y Project plan 2_description | 20y Project plan 3_description | 20y Project plan 4_description | 20y Project plan 5_description | 20y Chip Seal Plan | Davids's plan for rpm replacement | replacement due | Possible integration with planned projects year | Possible integrated planned projects
60000 | US 50 | From US 150 to SR 60 | 43.2896 | 53.4249 | 43 +0.223 | 53 +0.372 | 167677 | C1 | 20 | 2026 | 2 | FLEX | Is on the NHS | Paoli,Vincennes | Bedford Unit 3,Loogootee Unit | Lawrence,Martin,Orange | 3656 | 986 | N/A | 4 | 8 | [7 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60001 | I-64 | From Illinois State Line to 0.6 mile W of SR 165 (Bridge Over Flat Run Ditch) | 0 | 11.2964 | 0 +0.000 | 11 +0.272 | 544122 | A2 | 4 | 2036 | 4 | FLEX | Is on the NHS | Evansville,Vincennes | Oakland City Unit,Poseyville Unit 3 | Gibson,Posey | 14526 | 6148 | N/A | 3 | 6 |  | 2036 | [5 empty] | 2027 | 2036 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60002 | I-64 | From 0.6 mile W of SR 165 (Bridge Over Flat Run Ditch) to 3.32 mi E of SR 65 | 11.2964 | 20.9642 | 11 +0.272 | 20 +0.988 | 467255 | A2 | 3 | 2036 | 4 | FLEX | Is on the NHS | Evansville | Boyle Lane Unit 2,Poseyville Unit 3 | Gibson,Posey,Vanderburgh | 15003 | 4991 | N/A | 3 | 6 |  | 2036 | [5 empty] | 2027 | 2036 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60003 | I-64 | From 3.32 mi E of SR 65 to 0.5 mi E of US 41 | 20.9642 | 25.5402 | 20 +0.988 | 25 +0.524 | 213562 | A2 | 8 | 2034 | 4 | FLEX | Is on the NHS | Evansville | Boyle Lane Unit 2 | Gibson,Vanderburgh | 15539 | 6135 | N/A | 3 | 6 |  | 2034 | [5 empty] | 2027 | 2034 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60004 | I-64 | From 0.5 mi E of US 41 to 0.41 mi E of I-69 | 25.5402 | 29.8488 | 25 +0.524 | 29 +0.888 | 208325 | A2 | 11 | 2025 | 4 | FLEX | Is on the NHS | Evansville | Boyle Lane Unit 2,Chandler Unit 4 | Gibson,Vanderburgh,Warrick | 19060 | 12948 | N/A | 3 | 6 |  | 2039 | [5 empty] | 2027 | 2039 Minor Structural | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60005 | I-64 | From 0.41 mi E of I-69 to 0.13 mi E of SR 61 | 29.8488 | 39.713 | 29 +0.888 | 39 +0.732 | 469394 | A2 | 9 | 2030 | 4 | FLEX | Is on the NHS | Evansville,Tell City,Vincennes | Boyle Lane Unit 2,Chandler Unit 4,Dale Unit 4,Oakland City Unit | Gibson,Warrick | 17394 | 6116 | N/A | 3 | 6 |  | 2030 | [5 empty] | 2027 | 2030 Minor Structural | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60006 | I-64 | From 0.13 mile E of SR 61 to 1.91 mile W SR 161 Overpass | 39.713 | 48.6749 | 39 +0.732 | 48 +0.702 | 437846 | A2 | 1 | 2038 | 4 | FLEX | Is on the NHS | Tell City | Chrisney Unit 5,Dale Unit 4 | Spencer,Warrick | 17458 | 6486 | N/A | 3 | 6 | 2022 | 2038 | [5 empty] | 2027 | 2038 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60007 | I-64 | From 1.91 mile W SR 161 Overpass to 0.79 Miles E of US 231 | 48.6749 | 57.2493 | 48 +0.702 | 57 +0.254 | 405427 | A2 | 6 | 2030 | 4 | FLEX | Is on the NHS | Tell City,Vincennes | Dale Unit 4,Oakland City Unit | Spencer,Warrick | 16956 | 5780 | N/A | 3 | 6 |  | 2030 | [5 empty] | 2027 | 2030 Minor Structural | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60008 | I-64 | From 0.79 Miles E of US 231 to 3.21 miles E of SR 162 | 57.2493 | 65.9486 | 57 +0.254 | 65 +0.924 | 412860 | A2 | 6 | 2035 | 4 | FLEX | Is on the NHS | Tell City | Birdseye Unit 3,Chrisney Unit 5,Dale Unit 4 | Dubois,Spencer | 16523 | 6112 | N/A | 3 | 6 |  | 2035 | [5 empty] | 2027 | 2035 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60009 | I-64 | From 3.21 miles E of SR 162 to 0.26 mi W of SR145 | 65.9486 | 71.7294 | 65 +0.924 | 71 +0.799 | 278987 | A2 | 14 | 2025 | 4 | FLEX | Is on the NHS | Tell City | Birdseye Unit 3,Derby Unit 2 | Dubois,Perry,Spencer | 17112 | 5662 | N/A | 3 | 6 |  | 2040 | [5 empty] | 2027 | 2040 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60010 | I-64 | From 0.26 mi W of SR145 to 0.47 Miles W of SR 37 | 71.7294 | 78.0771 | 71 +0.799 | 78 +0.137 | 310405 | A2 | 6 | 2034 | 4 | FLEX | Is on the NHS | Tell City | Birdseye Unit 3,Derby Unit 2 | Crawford,Perry | 16328 | 6350 | N/A | 3 | 6 |  | 2034 | [5 empty] | 2027 | 2034 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60011 | I-64 | From 0.47 Miles W of SR 37 to 1.30 Miles W of SR 237 | 78.0771 | 84.4252 | 78 +0.137 | 84 +0.504 | 304464 | A2 | 7 | 2031 | 4 | FLEX | Is on the NHS | Tell City | Birdseye Unit 3 | Crawford,Perry | 16917 | 6712 | N/A | 3 | 6 |  | 2031 | [5 empty] | 2027 | 2031 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60012 | I-64 | From 1.30 mi W of SR 237 to 0.62 miles E of SR 66 | 84.4252 | 92.693 | 84 +0.504 | 92 +0.755 | 412955 | A2 | 6 | 2033 | 4 | FLEX | Is on the NHS | Tell City | Birdseye Unit 3,Derby Unit 2 | Crawford,Perry | 18617 | 5005 | N/A | 3 | 6 |  | 2033 | [5 empty] | 2027 | 2033 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60013 | I-69 | From US 41 to 2.3 mi E of US 41 | 0.68251 | 2.9597 | 0 +0.036 | 2 +0.566 | 113294 | A2 | 5 | 2042 | 4 | FLEX | Is on the NHS | Evansville | Evansville Unit 1 | Vanderburgh | 29956 | 3336 | N/A | 3 | 6 |  | 2042 | [5 empty] | 2027 | 2042 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60014 | I-69 | From Jct. SR 66 to I-64 | 7.8557 | 21.5032 | 7 +0.472 | 20 +0.884 | 657681 | A2 | 5 | 2029 | 4 | RIGID | Is on the NHS | Evansville | Chandler Unit 4,Evansville Unit 1 | Gibson,Vanderburgh,Warrick | 29775 | 3802 | N/A | 3 | 6 |  | 2038 | 2039 |  |  |  |  | 2027 | 2038 Rehab | 2039 Rehab |  |  |  |  | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60015 | I-69 | From I-64 to 0.60 mi N. SR 168 (Concrete) | 21.5032 | 28.5562 | 20 +0.884 | 27 +0.869 | 342817 | A2 | 11 | 2034 | 4 | RIGID | Is on the NHS | Evansville,Vincennes | Boyle Lane Unit 2,Chandler Unit 4,Oakland City Unit | Gibson,Pike | 16435 | 2679 | N/A | 3 | 6 |  | 2034 | 2044 |  |  |  |  | 2027 | 2034 Preventive Maintenance | 2044 Preventive Maintenance |  |  |  |  | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60016 | I-69 | From 0.60 mi. N SR 168 to 2.12 mi S. SR 57 (Asphalt) | 28.5562 | 40.4036 | 27 +0.869 | 39 +0.719 | 532167 | A2 | 10 | 2025 | 4 | FLEX | Is on the NHS | Tell City,Vincennes | Dale Unit 4,Oakland City Unit | Gibson,Pike | 11096 | 2596 | N/A | 3 | 6 |  | 2039 | [5 empty] | 2027 | 2039 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60017 | I-69 | From 2.12 mi S. SR 57 to 1.57 mi N. SR 356 (6.9 mi Concrete, 2.9 mi Asphalt) | 40.4036 | 50.2471 | 39 +0.719 | 49 +0.561 | 460524 | A2 | 11 | 2033 | 4 | RIGID | Is on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Knox,Pike | 9900 | 2252 | N/A | 4 | 8 |  | 2033 | 2043 |  |  |  |  | 2027 | 2033 Preventive Maintenance | 2043 Preventive Maintenance |  |  |  |  | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60018 | I-69 | From 1.57 mi N. SR 356 to 0.73 mi N. US 50(12.21 mi Concrete, 0.90 mi Asphalt) | 50.2471 | 63.3511 | 49 +0.561 | 62 +0.667 | 511778 | A2 | 11 | 2033 | 4 | RIGID | Is on the NHS | Vincennes | Loogootee Unit,Oakland City Unit,Vincennes Unit 2 | Daviess,Knox,Pike | 9034 | 1637 | N/A | 4 | 8 |  | 2033 | 2043 |  |  |  |  | 2027 | 2033 Preventive Maintenance | 2043 Preventive Maintenance |  |  |  |  | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60019 | I-69 | From 0.73 mi N. US 50 to 6.62 mi N. US 50 (Concrete) | 63.3511 | 69.2387 | 62 +0.667 | 68 +0.556 | 215743 | A2 | 11 | 2036 | 4 | RIGID | Is on the NHS | Linton,Vincennes | Crane Unit,Loogootee Unit | Daviess,Knox | 8895 | 2383 | N/A | 4 | 8 |  | 2036 | [5 empty] | 2027 | 2036 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60020 | I-69 | From 6.62 mi N. US 50 to 3.12 mi S. SR 58 (Asphalt) | 69.2387 | 73.4996 | 68 +0.556 | 72 +0.818 | 111443 | A2 | 11 | 2027 | 4 | FLEX | Is on the NHS | Linton,Vincennes | Linton,Loogootee Unit | Daviess | 8895 | 2383 | N/A | 4 | 8 |  | 2042 | [5 empty] | 2027 | 2042 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60021 | US 41 | From KY /IN State line To 0.10 mi S. I69 | 0 | 1.0578 | 0 -0.064 | 1 +0.112 | 53754 | B1 | 4 |  | 4 | FLEX | Is on the NHS | Evansville | Evansville Unit 1 | Vanderburgh | 38467 | 5122 | N/A | 2 | 4 | [15 empty] | 2025
60022 | US 41 | From SR 57 to 3.30 mi N SR-57 (0.20 mi N Boonville/New Harmony Road) | 8.9041 | 12.1947 | 8 +0.646 | 12 +0.248 | 142320 | B1 | 6 |  | 4 | FLEX | Is on the NHS | Evansville | Boyle Lane Unit 2 | Vanderburgh | 25274 | 3433 | N/A | 3 | 6 | 2025 | [6 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2028 | 2027 | 2027 RPM Replacement
60023 | US 41 | From 3.30 mi N SR-57 (0.20 mi N Boonville/New Harmony Road) to 0.85 mi S. SR 168 (0.20 mi N. Coal Mine Rd) | 12.1947 | 22.4035 | 12 +0.248 | 22 +0.354 | 527969 | B1 | 8 | 2027 | 4 | FLEX | Is on the NHS | Evansville,Vincennes | Boyle Lane Unit 2,Oakland City Unit | Gibson,Vanderburgh | 23678 | 3386 | N/A | 3 | 6 |  | 2030 | [6 empty] | 2030 Major Structural | [6 empty] | 2025
60024 | US 41 | From 0.85 SR 168 ( 0.20 mil N. Coal Mine Rd) to 0.53 N. SR 64 (Southern RR Bridge) | 22.4035 | 31.5167 | 22 +0.354 | 31 +0.451 | 406131 | B1 | 11 | 2027 | 4 | FLEX | Is on the NHS | Evansville,Vincennes | Boyle Lane Unit 2,Oakland City Unit,Vincennes Unit 2 | Gibson | 19159 | 2941 | N/A | 3 | 6 | 2021 | [6 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2024 | 2027 | 2027 RPM Replacement
60025 | US 41 | From 0.53 miles N of SR-64 to 0.50 miles S of SR-241 | 31.5167 | 43.1781 | 31 +0.451 | 43 +0.177 | 513715 | B2 | 5 |  | 4 | FLEX | Is on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Gibson,Knox | 11679 | 1791 | N/A | 3 | 6 | 2025 | [6 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2028 | 2027 | 2027 RPM Replacement
60026 | US 41 | From 0.50 miles S of SR-241 to 0.58 mi S of E intersection with US 50 (Kelso Creek bridge) | 43.1781 | 54.7367 | 43 +0.177 | 54 +0.594 | 543253 | B2 | 17 | 2026 | 4 | FLEX | Is on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Gibson,Knox | 13676 | 2097 | N/A | 3 | 6 | [7 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60027 | US 41 | From W. Jct. US 50 to SR 550 | 56.4907 | 64.4972 | 56 +0.155 | 64 +0.433 | 416914 | B2 | 15 | 2028 | 4 | FLEX | Is on the NHS | Linton,Vincennes | Sullivan Unit 3,Vincennes Unit 2 | Knox | 10183 | 1562 | N/A | 3 | 6 | 2025 | [6 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2028 | 2027 | 2027 RPM Replacement
60028 | US 41 | From SR 550 to 5.94 miles S of SR 58 (N. of Oaktown) | 64.4972 | 70.4499 | 64 +0.433 | 70 +0.490 | 279906 | B2 | 15 | 2030 | 4 | FLEX | Is on the NHS | Linton | Sullivan Unit 3 | Knox | 9109 | 1397 | N/A | 4 | 8 | 2025 | 2030 | [5 empty] | 2027 | 2030 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2029 | 2027 | 2027 RPM Replacement
60029 | US 41 | From 5.94 miles S of SR 58 (N. of Oaktown) to 0.44 mi S. SR 58 | 70.4499 | 75.8197 | 70 +0.490 | 75 +0.856 | 247349 | B2 | 1 |  | 4 | FLEX | Is on the NHS | Linton | Sullivan Unit 3 | Knox,Sullivan | 8302 | 1274 | N/A | 4 | 8 | 2022 | [6 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2026 | 2027 | 2027 RPM Replacement
60030 | US 41 | From 0.44 mi S. SR 58 to 0.47 mi N of SR 54 at RR | 75.8197 | 84.4953 | 75 +0.856 | 84 +0.570 | 397884 | B2 | 17 |  | 4 | FLEX | Is on the NHS | Linton | Sullivan Unit 3 | Sullivan | 9801 | 1503 | N/A | 4 | 8 | [7 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60031 | US 41 | From 0.47 mi N of SR 54 at RR to 1.64 miles S of SR 48 | 84.4953 | 90.7421 | 84 +0.570 | 90 +0.793 | 292217 | B2 | 9 |  | 4 | FLEX | Is on the NHS | Linton | Sullivan Unit 3 | Sullivan | 12706 | 1948 | N/A | 3 | 6 | [7 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60032 | US 41 | From 1.64 miles S of SR 48 to SR 246 | 90.7421 | 98.5366 | 90 +0.793 | 98 +0.616 | 364439 | B2 | 5 |  | 4 | FLEX | Is on the NHS | Linton | Sullivan Unit 3 | Sullivan,Vigo | 15749 | 2415 | N/A | 3 | 6 | [7 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60033 | US 50 | From IL/IN State Line to US 41/6th St | 0 | 1.8622 | 0 +0.000 | 1 +0.844 | 87060 | B2 | 1 |  | 4 | FLEX | Is on the NHS | Vincennes | Vincennes Unit 2 | Knox | 6107 | 1020 | N/A | 4 | 8 | 2022 | [14 empty] | 2026
60034 | US 50 | From 4.47 E. of E. Jct. US 41 to W. Of White River Bridge | 6.61 | 16.1865 | 7 +0.462 | 17 +0.168 | 433802 | B2 | 13 |  | 4 | RIGID | Is on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Daviess,Knox | 8395 | 1413 | N/A | 4 | 8 | [7 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60035 | US 50 | From 0.40 mi E. I 69 to 1.79 mi S. of W. Jct. US 231 | 24.1172 | 34.0531 | 24 +0.411 | 34 +0.016 | 187050 | C1 | 15 |  | 2 | FLEX | Is on the NHS | Vincennes | Loogootee Unit | Daviess,Knox | 7306 | 2412 | N/A | 3 | 6 | 2024 | [14 empty] | 2027
60036 | US 50 | From 0.25 mi. E. SR 550 to SR 450 | 36.132 | 41.759 | 36 +0.168 | 41 +0.714 | 119450 | C1 | 4 |  | 2 | FLEX | Is on the NHS | Paoli,Vincennes | Loogootee Unit,Paoli Unit 1 | Martin | 5511 | 961 | N/A | 4 | 8 | [15 empty] | 2025
60038 | US 50 | From SR 60 to S. Jct. SR 37 | 53.4249 | 63.1947 | 53 +0.372 | 63 +0.114 | 183460 | C2 | 3 | 2029 | 2 | FLEX | Is on the NHS | Paoli | Bedford Unit 3,Paoli Unit 1 | Lawrence | 3199 | 959 | N/A | 4 | 8 | [6 empty] | 2043 | 2026 | [5 empty] | 2043 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60039 | US 50 | From S. Jct. SR 37 to N. Jct. SR 37 | 63.1947 | 67.1128 | 63 +0.114 | 66 +1.006 | 177921 | B2 | 5 |  | 4 | FLEX | Is on the NHS | Paoli | Bedford Unit 3 | Lawrence | 20057 | 6012 | N/A | 3 | 6 | 2024 | [14 empty] | 2027
60040 | US 50 | From SR-37 N Jct to 3.33 mi East of SR 37 (West of Leatherwood Rd. Intersection) | 67.1128 | 70.4367 | 66 +1.006 | 68 +0.618 | 85357 | B2 | 14 |  | 4 | FLEX | Is on the NHS | Paoli | Bedford Unit 3 | Lawrence | 12486 | 1281 | N/A | 3 | 6 | 2024 | 2039 | [6 empty] | 2039 Preventive Maintenance | [6 empty] | 2027
60041 | US 50 | From 3.33 mi East of SR 37 (West of Leatherwood Rd. Intersection) to to SR 446 (District Line) | 70.4367 | 77.1131 | 68 +0.618 | 75 +0.445 | 134922 | C1 | 13 | 2026 | 2 | FLEX | Is on the NHS | Paoli | Bedford Unit 3 | Lawrence | 6037 | 165 | N/A | 3 | 6 | [15 empty] | 2025
60042 | US 231 | From SR 70 to 3.65 mi S. SR 162 | 7.122 | 12.2315 | 19 +0.689 | 24 +0.773 | 134818 | B2 | 13 | 2032 | 4 | FLEX | Is on the NHS | Tell City | Chrisney Unit 5 | Spencer,Warrick | 4883 | 2027 | N/A | 4 | 8 |  | 2032 | [5 empty] | 2026 | 2032 Preventive Maintenance | [5 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60043 | US 231 | From 3.65 mi S. SR 162 to 0.95 mi N. I 64 | 12.2315 | 22.6956 | 24 +0.773 | 35 +0.305 | 485369 | B2 | 13 |  | 4 | RIGID | Is on the NHS | Tell City | Chrisney Unit 5,Dale Unit 4 | Dubois,Spencer | 6124 | 2283 | N/A | 4 | 8 | [7 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60044 | US 231 | From 0.95 miles N of I-64 to 1.64 miles S of SR-64 | 22.6956 | 27.6406 | 35 +0.305 | 40 +0.250 | 95570 | C1 | 6 |  | 2 | FLEX | Is on the NHS | Paoli,Tell City | Dale Unit 4,Jasper Unit 4 | Dubois | 7316 | 938 | N/A | 3 | 6 | [15 empty] | 2025
60045 | US 231 | From 1.64 miles S of SR-64 to 1.02 mi N SR 64 (19th St) | 27.6406 | 30.2877 | 40 +0.250 | 42 +0.944 | 64757 | B1 | 2 |  | 2 | FLEX | Is on the NHS | Paoli,Tell City | Dale Unit 4,Jasper Unit 4 | Dubois | 10325 | 992 | N/A | 3 | 6 | 2021 | 2041 | [6 empty] | 2041 Preventive Maintenance | [6 empty] | 2024
60046 | US 231 | From 1.02 mi N SR 64 ( 19th St) to 0.40 mi S. SR 162 | 30.2877 | 33.529 | 42 +0.944 | 46 +0.182 | 92083 | B1 | 10 | 2029 | 2 | FLEX | Is on the NHS | Paoli,Tell City | Dale Unit 4,Jasper Unit 4 | Dubois | 13898 | 1274 | N/A | 3 | 6 | [15 empty] | 2025
60047 | US 231 | From 0.40 mi S. SR 162 to S Jct with SR-56 | 33.529 | 35.9055 | 46 +0.182 | 48 +0.557 | 94355 | B1 | 7 | 2029 | 2 | RIGID | Is on the NHS | Paoli,Vincennes | Jasper Unit 4,Loogootee Unit | Dubois | 14892 | 1236 | N/A | 3 | 6 | 2021 | [14 empty] | 2024
60048 | US 231 | From S Jct with SR-56 to 3.30 miles N of SR-164 (47th St) | 35.9055 | 39.5791 | 48 +0.557 | 52 +0.047 | 79077 | B1 | 2 |  | 2 | FLEX | Is on the NHS | Paoli,Vincennes | Jasper Unit 4,Loogootee Unit | Dubois | 16747 | 1008 | N/A | 3 | 6 | 2021 | 2040 | [6 empty] | 2040 Preventive Maintenance | [6 empty] | 2024
60049 | US 231 | From 3.30 miles N of SR-164 (47th St) to 1.04 mi N. N. Jct SR 56 (N side of White River Bridge) | 39.5791 | 44.1655 | 52 +0.047 | 56 +0.683 | 92571 | C1 | 4 |  | 2 | FLEX | Is on the NHS | Paoli,Vincennes | Jasper Unit 4,Loogootee Unit | Daviess,Dubois | 6797 | 810 | N/A | 3 | 6 | 2025 | [14 empty] | 2028
60050 | US 231 | From 1.04 mi N. N. Jct SR 56 (N side of White River Bridge) to West Jct US 50 | 44.1655 | 56.4098 | 56 +0.683 | 68 +0.941 | 233826 | C1 | 4 |  | 2 | FLEX | Is on the NHS | Paoli,Vincennes | Jasper Unit 4,Loogootee Unit | Dubois,Martin | 6450 | 844 | N/A | 3 | 6 | [15 empty] | 2025
60051 | US 231 | From 0.97 mi N. of E. Jct. US 50 (N. Corporate Limits Loogootee) to SR 45 | 57.3711 | 73.229 | 70 +0.341 | 86 +0.254 | 296365 | C1 | 10 | 2026 | 2 | FLEX | Is on the NHS | Linton | Crane Unit,Linton | Daviess,Greene,Martin | 5706 | 703 | N/A | 4 | 8 | [15 empty] | 2025
60052 | US 231 | From SR 45 to 1.16 mi S of E Jct SR-54/SR-157 (Richland Creek) | 73.229 | 80 | 86 +0.254 | 92 +1.030 | 124923 | C2 | 19 | 2026 | 2 | FLEX | Is on the NHS | Linton | Crane Unit,Linton | Greene | 4760 | 635 | N/A | 4 | 8 | [6 empty] | 2039 | [6 empty] | 2039 Chip Seal |  | 2025
60053 | US 231 | From 0.67 mi. W. Jct. SR 54/SR157 (Bloomfield W. CL) to Jct SR-57 / SR 54 | 81.7939 | 85.1507 | 94 +0.822 | 98 +0.156 | 68682 | C1 | 6 | 2031 | 2 | FLEX | Is on the NHS | Linton | Crane Unit,Linton | Greene | 7959 | 1063 | N/A | 3 | 6 |  | 2031 | [6 empty] | 2031 Major Structural | [6 empty] | 2025
60054 | US 231 | From W Jct SR-57 / SR 54 to SR 67 | 85.1507 | 88.4427 | 98 +0.156 | 101 +0.494 | 58777 | C2 | 4 | 2027 | 2 | FLEX | Is on the NHS | Linton | Linton | Greene | 2259 | 302 | N/A | 4 | 8 | [6 empty] | 2040 | [6 empty] | 2040 Chip Seal |  | 2025
60056 | US 150 | From US 50 to SR 56 | 14.8547 | 28.3798 | 14 +1.134 | 125 +0.404 | 232962 | C2 | 5 | 2027 | 2 | FLEX | Not on the NHS | Paoli | Paoli Unit 1 | Martin,Orange | 1496 | 214 | Yes | 4 | 8 | [6 empty] | 2039 | 2027 | [5 empty] | 2039 Chip Seal | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60057 | US 150 | From SR 56 to 1.67 mi W. Jct SR 37 (Paoli Town Limits) | 28.3798 | 35.4667 | 125 +0.404 | 132 +0.537 | 156121 | C2 | 9 | 2026 | 2 | FLEX | Not on the NHS | Paoli | Paoli Unit 1 | Orange | 4796 | 707 | N/A | 4 | 8 | [6 empty] | 2040 | 2027 | [5 empty] | 2040 Chip Seal | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60058 | US 150 | From 1.24 mi E. Jct. SR 37 (Paoli E.Town Limits) to SR 66 | 38.5208 | 51.0923 | 135 +0.494 | 148 +0.039 | 211237 | C2 | 4 | 2026 | 2 | FLEX | Not on the NHS | Paoli | Paoli Unit 1 | Orange,Washington | 2760 | 183 | Yes | 4 | 8 | [6 empty] | 2039 | 2027 | [5 empty] | 2039 Chip Seal | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60059 | SR 145 | From SR 37 to 10.5 mi N SR 37 (Bristow- Athens Rd) | 0 | 10.5223 | 0 +0.000 | 10 +0.492 | 176709 | C2 | 14 | 2027 | 2 | FLEX | Not on the NHS | Tell City | Birdseye Unit 3,Derby Unit 2 | Crawford,Perry | 425 | 30 | Yes | 4 | 8 | [6 empty] | 2027 | 2027 | [5 empty] | 2027 Chip Seal | 2027 RPM Replacement | 2025 | 2027 | 2027 Chip Seal
60060 | SR 145 | From 10.5 mi N SR 37 (Bristow- Athens Rd) to I 64 | 10.5223 | 17.6358 | 10 +0.492 | 17 +0.586 | 121630 | C2 | 19 | 2027 | 2 | FLEX | Not on the NHS | Paoli,Tell City | Birdseye Unit 3,Derby Unit 2,Jasper Unit 4 | Crawford,Perry | 202 | 19 | Yes | 4 | 8 | [6 empty] | 2027 | 2027 | [5 empty] | 2027 Chip Seal | 2027 RPM Replacement | 2025 | 2027 | 2027 Chip Seal
60061 | SR 145 | From I-64 to 0.69 mi S. W. Jct SR 64 (S. Birdseye town Limits) | 17.6358 | 24.1409 | 17 +0.586 | 24 +0.082 | 101699 | C2 | 19 | 2027 | 2 | FLEX | Not on the NHS | Tell City | Birdseye Unit 3,Derby Unit 2 | Dubois,Perry | 375 | 30 | Yes | 4 | 8 | [6 empty] | 2033 | 2027 | [5 empty] | 2033 Chip Seal | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60062 | SR 145 | From SR 164 to SR 56 | 27.2987 | 40.9875 | 31 +0.668 | 45 +0.307 | 378198 | C2 | 13 | 2026 | 2 | FLEX | Not on the NHS | Paoli | Jasper Unit 4,Paoli Unit 1 | Crawford,Orange | 2806 | 417 | N/A | 4 | 8 | [6 empty] | 2039 | [6 empty] | 2039 Chip Seal |  | 2025
60063 | SR 154 | From Illinois/Indiana State Line to SR 63 | 0 | 5.6768 | 0 -0.133 | 5 +0.728 | 103082 | C2 | 16 | 2025 | 2 | FLEX | Not on the NHS | Linton | Sullivan Unit 3 | Sullivan | 2313 | 275 | Yes | 4 | 8 | [6 empty] | 2030 | 2026 | [5 empty] | 2030 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60064 | SR 157 | From US 231/SR 54 to 1.10 N. US 231/SR54 | 0 | 1.097 | 0 +0.000 | 1 +0.093 | 20778 | C1 | 1 |  | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Greene | 3685 | 370 | N/A | 4 | 8 | 2022 | [14 empty] | 2026
60065 | SR 158 | From Beginning of SR 158 (Crane Gate) to SR 450 | 0 | 10.1685 | 0 +0.000 | 10 +0.094 | 146330 | C2 | 14 | 2026 | 2 | FLEX | Not on the NHS | Linton,Paoli | Bedford Unit 3,Crane Unit | Lawrence,Martin | 1666 | 201 | Yes | 4 | 8 | [6 empty] | 2026 | [6 empty] | 2026 Chip Seal |  | 2025
60066 | SR 159 | From SR 67 to 0.33 mi S. SR 58 | 0 | 5.7544 | 0 +0.000 | 5 +0.763 | 109735 | C2 | 18 | 2028 | 2 | FLEX | Not on the NHS | Linton | Linton,Sullivan Unit 3 | Knox | 1922 | 231 | Yes | 4 | 8 | [6 empty] | 2028 | [6 empty] | 2028 Chip Seal |  | 2025
60067 | SR 159 | From Greene / Sullivan Co. Line to From 0.32 mi. S. SR 54 (S. Dugger Town Limits) | 6.0847 | 13.8677 | 5 +1.094 | 13 +0.729 | 112701 | C2 | 20 | 2030 | 2 | FLEX | Not on the NHS | Linton | Linton,Sullivan Unit 3 | Sullivan | 951 | 113 | Yes | 4 | 8 | [6 empty] | 2037 | [6 empty] | 2037 Chip Seal |  | 2025
60068 | SR 161 | From KY/ IN state Line to E. Jct SR 66 | 0 | 8.2129 | 500 +0.000 | 508 +0.222 | 164674 | C1 | 13 |  | 2 | FLEX | Not on the NHS | Tell City | Chrisney Unit 5 | Spencer,Warrick | 7932 | 1051 | N/A | 3 | 6 | [7 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60069 | SR 161 | From W. Jct SR 66 to W. Jct SR 62 | 8.2139 | 18.6931 | 508 +0.223 | 10 +0.464 | 174876 | C2 | 21 | 2026 | 2 | FLEX | Not on the NHS | Evansville,Tell City | Chandler Unit 4,Chrisney Unit 5 | Spencer,Warrick | 942 | 54 | No | 4 | 8 |  | 2040 |  |  |  |  | 2032 |  | 2040 Preventive Maintenance |  |  |  |  | 2032 Chip Seal |  | 2025
60070 | SR 161 | From E. Jct. SR 62 to W. Jct. SR 68 | 18.6941 | 30.074 | 10 +0.465 | 27 +0.123 | 179709 | C2 | 2 | 2029 | 2 | FLEX | Not on the NHS | Tell City | Chrisney Unit 5 | Spencer,Warrick | 432 | 26 | Yes | 4 | 8 | 2021 | [5 empty] | 2043 | 2026 | [5 empty] | 2043 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60071 | SR 161 | From E. Jct. SR-68 to 3.24 miles North of I-64 (RP 30+59 to 34+49) | 30.075 | 34.1216 | 27 +0.124 | 34 +0.563 | 102507 | C2 | 6 |  | 2 | RIGID | Not on the NHS | Tell City | Chrisney Unit 5,Dale Unit 4 | Dubois,Spencer,Warrick | 2678 | 352 | Yes | 4 | 8 | [15 empty] | 2025
60072 | SR 161 | From 3.24 miles North of I-64 (RP 34+49) to SR 64 (RP 38.25) | 34.1216 | 37.8095 | 34 +0.563 | 38 +0.248 | 73263 | C2 | 13 |  | 2 | RIGID | Not on the NHS | Tell City | Dale Unit 4 | Dubois | 4014 | 434 | Yes | 4 | 8 | 2025 | [14 empty] | 2029
60073 | SR 162 | From SR 62 to E. Jct. SR 245 | 0 | 6.8019 | 0 +0.000 | 6 +0.808 | 144294 | C2 | 15 | 2027 | 2 | FLEX | Not on the NHS | Tell City | Chrisney Unit 5,Dale Unit 4 | Spencer,Warrick | 2899 | 226 | Yes | 4 | 8 |  | 2033 |  |  |  |  | 2034 |  | 2033 Preventive Maintenance |  |  |  |  | 2034 Chip Seal |  | 2025
60074 | SR 162 | From E. Jct. SR 245 to I-64 | 6.8019 | 13.7085 | 6 +0.808 | 13 +0.763 | 193351 | C2 | 2 | 2029 | 2 | FLEX | Not on the NHS | Tell City | Birdseye Unit 3,Dale Unit 4 | Spencer | 3864 | 350 | Yes | 4 | 8 | 2021 | [5 empty] | 2042 | 2026 | [5 empty] | 2042 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60075 | SR 162 | From I-64 To 0.10 mi N SR 264 (N. Ferdinand Town Limits) | 13.7085 | 15.9948 | 13 +0.763 | 15 +1.041 | 55576 | C1 | 1 |  | 2 | FLEX | Not on the NHS | Paoli | Jasper Unit 4 | Dubois | 8311 | 639 | N/A | 3 | 6 | 2022 | [14 empty] | 2025
60076 | SR 162 | From SR 64 to US 231 | 20.5857 | 27.8613 | 20 +0.628 | 27 +0.922 | 172429 | C1 | 16 | 2025 | 2 | FLEX | Not on the NHS | Paoli,Tell City | Dale Unit 4,Jasper Unit 4 | Dubois | 8168 | 573 | N/A | 3 | 6 | [15 empty] | 2025
60077 | SR 164 | From 0.51 mi E. of US 231 to SR 545 | 0.51148 | 11.8808 | 0 +0.510 | 11 +0.781 | 189810 | C2 | 6 | 2029 | 2 | FLEX | Not on the NHS | Paoli | Jasper Unit 4,Paoli Unit 1 | Dubois | 3615 | 188 | N/A | 4 | 8 | [6 empty] | 2043 | [6 empty] | 2043 Chip Seal |  | 2025
60078 | SR 164 | From SR 545 to SR 145 | 11.8808 | 19.0959 | 11 +0.781 | 19 +0.119 | 143946 | C2 | 24 | 2027 | 2 | FLEX | Not on the NHS | Paoli | Jasper Unit 4,Paoli Unit 1 | Crawford,Dubois | 1739 | 190 | Yes | 4 | 8 | [6 empty] | 2027 | [6 empty] | 2027 Chip Seal |  | 2025
60079 | SR 165 | From SR 66 to W. Jct. SR 68 | 0 | 3.8216 | 0 +0.000 | 3 +0.867 | 60875 | C2 | 11 | 2026 | 2 | FLEX | Not on the NHS | Evansville | Poseyville Unit 3 | Posey | 3250 | 174 | Yes | 4 | 8 | [6 empty] | 2034 | 2026 | [5 empty] | 2034 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60080 | SR 165 | From E. Jct SR 68 to 0.47 mi W. SR 65 (W. City Limits Owensville) | 3.8226 | 15.7313 | 3 +0.868 | 16 +0.731 | 199912 | C2 | 4 | 2027 | 2 | FLEX | Not on the NHS | Evansville | Boyle Lane Unit 2,Poseyville Unit 3 | Gibson,Posey | 1890 | 217 | No | 4 | 8 | [15 empty] | 2025
60081 | SR 166 | From SR 66 to End of Rd (Tobinsport) | 0 | 6.3598 | 0 +0.000 | 6 +0.410 | 92063 | C2 | 18 | 2031 | 2 | FLEX | Not on the NHS | Tell City | Derby Unit 2 | Perry | 308 | 29 | Yes | 4 | 8 | [15 empty] | 2025
60082 | SR 168 | From 0.73 mi E. SR 65 (Owensville E. City Limits) to US 41 | 0.73386 | 7.672 | 0 +0.733 | 7 +0.696 | 129295 | C2 | 20 | 2028 | 2 | FLEX | Not on the NHS | Evansville,Vincennes | Boyle Lane Unit 2,Oakland City Unit | Gibson | 3812 | 458 | Yes | 4 | 8 | 2024 | [14 empty] | 2028
60083 | SR 168 | From US 41 to SR 57 | 7.672 | 17.1788 | 7 +0.696 | 17 +0.271 | 156604 | C1 | 14 |  | 2 | FLEX | Not on the NHS | Evansville,Vincennes | Boyle Lane Unit 2,Oakland City Unit | Gibson,Pike | 4677 | 563 | N/A | 4 | 8 | [7 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60085 | SR 241 | From US 41 to W Jct. SR 61 | 0 | 13.6501 | 0 +0.000 | 13 +0.713 | 207269 | C2 | 4 | 2028 | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Gibson,Knox | 289 | 34 | Yes | 4 | 8 | [6 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2025
60086 | SR 241 | From E. Jct. SR 61 to US 50 | 13.6511 | 17.571 | 13 +0.714 | 18 +0.046 | 66929 | C2 | 17 | 2027 | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Knox | 1432 | 171 | Yes | 4 | 8 | [6 empty] | 2027 | [6 empty] | 2027 Chip Seal |  | 2025
60087 | SR 245 | From SR 70 to 3.51 mi S E. Jct. SR 162 (Crooked Creek Bridge) | 0 | 4.9249 | 1 -1.063 | 5 +0.036 | 91856 | C2 | 13 | 2027 | 2 | FLEX | Not on the NHS | Tell City | Chrisney Unit 5 | Spencer | 1781 | 193 | Yes | 4 | 8 | [6 empty] | 2033 | [6 empty] | 2033 Chip Seal |  | 2025
60088 | SR 245 | From W. Jct. SR 162 to SR 62 | 8.1383 | 12.7316 | 8 +0.430 | 13 +0.562 | 67835 | C2 | 22 | 2026 | 2 | FLEX | Not on the NHS | Tell City | Dale Unit 4 | Spencer | 743 | 40 | Yes | 4 | 8 | [6 empty] | 2026 | [6 empty] | 2026 Chip Seal |  | 2025
60089 | SR 257 | From Beginning of SR 257 (Stendal) to SR 64 | 0 | 4.4628 | 0 +0.000 | 4 +0.443 | 58948 | C2 | 20 | 2031 | 2 | FLEX | Not on the NHS | Paoli,Tell City | Dale Unit 4,Jasper Unit 4 | Pike | 167 | 13 | Yes | 4 | 8 | 2022 | [14 empty] | 2026
60090 | SR 257 | From SR 64 to SR 356 | 4.4628 | 17.2588 | 4 +0.443 | 16 +0.945 | 209812 | C2 | 20 | 2031 | 2 | FLEX | Not on the NHS | Paoli,Tell City,Vincennes | Dale Unit 4,Jasper Unit 4,Loogootee Unit | Knox,Pike | 1021 | 123 | Yes | 4 | 8 | 2024 | [14 empty] | 2028
60091 | SR 257 | From SR 356 to 0.10 mi S. US 50 | 17.2588 | 30.2374 | 16 +0.945 | 29 +0.913 | 229203 | C2 | 7 |  | 2 | FLEX | Not on the NHS | Paoli,Vincennes | Jasper Unit 4,Loogootee Unit,Oakland City Unit,Vincennes Unit 2 | Daviess,Knox,Pike | 3585 | 554 | No | 4 | 8 |  | 2041 | [5 empty] | 2026 | 2041 Preventive Maintenance | [5 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60092 | SR 261 | From SR 66 to From 3.01 mi N. SR 66 | 0 | 2.984 | 0 +0.000 | 3 +0.060 | 90770 | B1 | 9 | 2030 | 2 | FLEX | Not on the NHS | Evansville | Chandler Unit 4 | Warrick | 12797 | 973 | N/A | 3 | 6 |  | 2030 | [6 empty] | 2030 Preventive Maintenance | [6 empty] | 2025
60093 | SR 264 | From SR 162 to End of Road (Ferdinand State Forest) | 0 | 4.8586 | 0 +0.000 | 4 +0.863 | 67290 | C2 | 3 | 2028 | 2 | FLEX | Not on the NHS | Paoli,Tell City | Dale Unit 4,Jasper Unit 4 | Dubois,Perry | 802 | 25 | Yes | 4 | 8 | [6 empty] | 2042 | 2026 | [5 empty] | 2042 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60094 | SR 269 | From SR 69 to End of Road (Harmonie State Park) | 0 | 0.88983 | 0 +0.000 | 0 +0.889 | 14049 | C2 | 20 | 2026 | 2 | FLEX | Not on the NHS | Evansville | Poseyville Unit 3 | Posey | 105 | 5 | Yes | 4 | 8 |  | 2038 | [6 empty] | 2038 Preventive Maintenance | [6 empty] | 2025
60095 | SR 337 | From SR 56 (Lavonia) to 1.03 mi S. SR 37 (Orleans Town Limits) | 12.3036 | 23.7667 | 21 +0.991 | 33 +0.429 | 168687 | C2 | 2 | 2028 | 2 | FLEX | Not on the NHS | Paoli | Paoli Unit 1 | Orange,Washington | 763 | 46 | No | 4 | 8 | 2021 | [6 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60096 | SR 356 | From 0.85 mi E. SR 57 (E. Petersburg City Limits) to SR 257 | 0.85149 | 9.9106 | 0 +0.850 | 9 +0.944 | 145986 | C2 | 25 | 2028 | 2 | FLEX | Not on the NHS | Paoli,Vincennes | Jasper Unit 4,Loogootee Unit,Oakland City Unit,Vincennes Unit 2 | Knox,Pike | 1699 | 185 | Yes | 4 | 8 | 2022 | [5 empty] | 2042 | 2026 | [5 empty] | 2042 Chip Seal | 2026 RPM Replacement | 2026 | 2026 | 2026 RPM Replacement
60097 | SR 357 | From SR 57 to SR 64 (Oakland City) | 0 | 1.2384 | 0 +0.000 | 1 +0.237 | 24901 | C1 | 6 |  | 2 | FLEX | Not on the NHS | Tell City,Vincennes | Dale Unit 4,Oakland City Unit | Gibson,Pike | 1020 | 121 | N/A | 4 | 8 | [15 empty] | 2025
60098 | SR 358 | From SR 67 to S. Jct SR 57 | 0 | 6.4123 | 0 +0.000 | 6 +0.427 | 99093 | C2 | 16 | 2027 | 2 | FLEX | Not on the NHS | Linton,Vincennes | Sullivan Unit 3,Vincennes Unit 2 | Daviess,Knox | 1365 | 164 | Yes | 4 | 8 | [6 empty] | 2041 | [6 empty] | 2041 Chip Seal |  | 2025
60099 | SR 358 | From N. JCt SR 57 to SR 58 | 6.4133 | 8.22 | 6 +0.428 | 11 +0.972 | 26498 | C2 | 22 | 2031 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Daviess,Knox | 1243 | 149 | Yes | 4 | 8 | 2024 | [5 empty] | 2031 | [6 empty] | 2031 Chip Seal |  | 2028 | 2031 | 2031 Chip Seal
60100 | SR 364 | From SR 61 to End of Road (Pike State Forest) | 0 | 4.1752 | 0 +0.000 | 4 +0.229 | 51927 | C2 | 27 | 2028 | 2 | FLEX | Not on the NHS | Paoli,Vincennes | Jasper Unit 4,Oakland City Unit | Pike | 115 | 15 | Yes | 4 | 8 | [6 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2025
60102 | SR 37 | From SR 70 to I 64 | 10.9151 | 22.4662 | 10 +0.919 | 22 +0.428 | 299239 | C1 | 8 |  | 2 | FLEX | Not on the NHS | Tell City | Derby Unit 2 | Crawford,Perry | 3161 | 852 | N/A | 4 | 8 | [15 empty] | 2025
60103 | SR 37 | From I-64 to W. Jct SR 64 | 22.4662 | 29.5691 | 22 +0.428 | 29 +0.552 | 195655 | C2 | 2 | 2028 | 2 | FLEX | Not on the NHS | Tell City | Birdseye Unit 3,Derby Unit 2 | Crawford,Perry | 2450 | 560 | N/A | 4 | 8 | 2021 | [5 empty] | 2028 | 2026 | [5 empty] | 2028 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60104 | SR 37 | From W . Jct SR 64 to E. Jct. SR 64 / SR 237 | 29.5691 | 37.8838 | 29 +0.552 | 38 +0.385 | 166039 | C2 | 2 | 2029 | 2 | FLEX | Not on the NHS | Paoli | Paoli Unit 1 | Crawford | 2611 | 549 | Yes | 4 | 8 | 2021 | [5 empty] | 2043 | 2026 | [5 empty] | 2043 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60105 | SR 37 | From E. Jct. SR 64 to 1.24 mi S. Jct US 150 (S. Paoli Town Limits) | 37.8838 | 53.3453 | 38 +0.385 | 53 +0.901 | 287510 | C2 | 4 | 2028 | 2 | FLEX | Not on the NHS | Paoli | Paoli Unit 1 | Crawford,Orange | 1333 | 114 | Yes | 4 | 8 | [6 empty] | 2042 | 2027 | [5 empty] | 2042 Chip Seal | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60106 | SR 37 | From 1.14 mi. N. Jct. US 150 (N. Paoli Town Limits) to 1.34 mi S. SR 337 (S. Orleans Town Limits) | 55.7313 | 60.8409 | 56 +0.418 | 61 +0.515 | 121321 | C1 | 9 |  | 2 | FLEX | Not on the NHS | Paoli | Paoli Unit 1 | Orange | 7339 | 225 | N/A | 3 | 6 | [15 empty] | 2025
60107 | SR 37 | From 0.62 mile S of South Jct SR-60 (Concrete Pavement Starts) to the South Jct of US-50 | 66.2673 | 73.4718 | 66 +0.940 | 74 +0.142 | 350671 | B2 | 4 |  | 4 | RIGID | Is on the NHS | Paoli | Bedford Unit 3,Paoli Unit 1 | Lawrence | 15403 | 1025 | N/A | 3 | 6 | 2024 | [14 empty] | 2027
60108 | SR 37 | From N Jct of US-50 to 1.06 mi S. SR 54 | 73.4728 | 76.2524 | 74 +0.143 | 81 +0.060 | 131898 | B1 | 5 |  | 4 | FLEX | Is on the NHS | Paoli | Bedford Unit 3 | Lawrence | 21560 | 1556 | N/A | 3 | 6 | [7 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60109 | SR 43 | From SR 54 to SR 48 (District Line) | 0 | 12.6947 | 0 +0.000 | 12 +0.575 | 193933 | C2 | 14 | 2028 | 2 | FLEX | Not on the NHS | Linton | Crane Unit | Greene,Monroe,Owen | 999 | 110 | Yes | 4 | 8 | [6 empty] | 2041 | [6 empty] | 2041 Chip Seal |  | 2025
60110 | SR 441 | From 0.12 mi E. US 41 (Ramsey Rd) To ILL/ IN Bridge | 0 | 2.7274 | 0 -0.134 | 2 +0.581 | 63162 | C1 | 11 | 2025 | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Knox | 8843 | 718 | N/A | 3 | 6 | [15 empty] | 2025
60111 | SR 445 | From SR 54 to 0.36 mi W. SR 45 | 0 | 0.9272 | 0 +0.000 | 0 +0.927 | 16022 | C2 | 6 | 2030 | 2 | FLEX | Not on the NHS | Linton | Crane Unit | Greene | 3859 | 467 | Yes | 4 | 8 | [6 empty] | 2037 | [6 empty] | 2037 Chip Seal |  | 2025
60112 | SR 45 | From US 231 to SR 58 | 0 | 9.1982 | 6 -0.923 | 14 +0.170 | 171322 | C2 | 16 | 2028 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Greene | 2119 | 271 | Yes | 4 | 8 | [6 empty] | 2035 | [6 empty] | 2035 Chip Seal |  | 2025
60113 | SR 45 | From SR 58 to SR 445 (District Line) | 9.1982 | 18.6152 | 14 +0.170 | 23 +0.689 | 177021 | C2 | 14 | 2026 | 2 | FLEX | Not on the NHS | Linton,Paoli | Bedford Unit 3,Crane Unit | Greene | 3069 | 369 | Yes | 4 | 8 | 2021 | [5 empty] | 2034 | 2026 | [5 empty] | 2034 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60114 | SR 450 | From S. Jct. US 50 to Martin/Lawrence Co. Line | 0 | 13.5626 | 0 +0.000 | 13 +0.548 | 210326 | C2 | 2 | 2029 | 2 | FLEX | Not on the NHS | Paoli | Bedford Unit 3,Paoli Unit 1 | Lawrence,Martin | 493 | 17 | Yes | 4 | 8 | 2021 | [5 empty] | 2035 | 2026 | [5 empty] | 2035 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60115 | SR 458 | From SR 158 to End of Road (Purdue Farm) | 0 | 1.1337 | 0 +0.000 | 1 +0.139 | 13755 | C2 | 20 | 2027 | 2 | FLEX | Not on the NHS | Paoli | Bedford Unit 3 | Lawrence | 289 | 10 | Yes | 4 | 8 | 2021 | [5 empty] | 2041 | [6 empty] | 2041 Chip Seal |  | 2025
60116 | SR 48 | From SR 63 TO US 41 | 0 | 7.0002 | 0 -0.016 | 6 +0.992 | 114275 | C2 | 1 | 2030 | 2 | FLEX | Not on the NHS | Linton | Sullivan Unit 3 | Sullivan | 874 | 96 | Yes | 4 | 8 | 2022 | [5 empty] | 2044 | [6 empty] | 2044 Chip Seal |  | 2026
60117 | SR 48 | From US 41 TO 4.1 mi W. SR 159 (Hymera W. Town Limits) | 7.0002 | 11.8008 | 6 +0.992 | 11 +0.764 | 89715 | C2 | 20 | 2028 | 2 | FLEX | Not on the NHS | Linton | Linton,Sullivan Unit 3 | Sullivan | 3666 | 434 | Yes | 4 | 8 | [6 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2025
60118 | SR 48 | From 0.05 mile E of SR 59 (0.05 mi E. Jasonville E. Town Limits) to SR 157 | 19.579 | 29.9633 | 19 +0.552 | 29 +0.935 | 166914 | C2 | 20 | 2030 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Greene | 1240 | 147 | Yes | 4 | 8 | 2024 | [5 empty] | 2033 | [6 empty] | 2033 Chip Seal |  | 2028
60119 | SR 54 | From US 41 to 0.50 mi W. SR 159 (W. Dugger Town Limits) | 0 | 7.9612 | 10 -0.158 | 17 +0.884 | 166610 | C2 | 9 | 2031 | 2 | FLEX | Not on the NHS | Linton | Linton,Sullivan Unit 3 | Sullivan | 4711 | 684 | N/A | 4 | 8 | 2025 | [14 empty] | 2029
60120 | SR 54 | From 0.51 mi E. SR 159 (E. Dugger Town Limits) to 1.23 mi E Jct of E. SR 59 (Linton W. City Limits) | 8.9758 | 13.8576 | 18 +0.836 | 23 +0.851 | 97247 | C1 | 9 | 2027 | 2 | FLEX | Not on the NHS | Linton | Linton,Sullivan Unit 3 | Greene,Sullivan | 6119 | 892 | N/A | 3 | 6 | 2025 | [14 empty] | 2028
60121 | SR 54 | From 1.23 mi E Jct of E. SR 59 (Linton W. City Limits) to E Jct SR 59 | 13.8576 | 15.4299 | 23 +0.851 | 25 +0.423 | 38269 | C1 | 7 |  | 2 | FLEX | Not on the NHS | Linton | Linton | Greene | 8237 | 1202 | N/A | 3 | 6 | [7 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60122 | SR 54 | From SR 67 to SR 57 / US 231 | 21.3703 | 23.8781 | 31 +0.357 | 33 +0.813 | 50059 | C1 | 7 |  | 2 | FLEX | Not on the NHS | Linton | Linton | Greene | 6797 | 991 | N/A | 3 | 6 | [15 empty] | 2025
60123 | SR 54 | From 0.52 mi East US 231/SR 157 (Bloomfield Town Limits) TO W. Jct. SR 45 | 24.4003 | 37.3471 | 38 +0.358 | 51 +0.170 | 245555 | C2 | 6 | 2027 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Greene | 4057 | 592 | Yes | 4 | 8 | [6 empty] | 2040 | 2027 | [5 empty] | 2040 Chip Seal | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60124 | SR 54 | From E. Jct. SR 45 to SR 58 | 37.3481 | 45.9569 | 51 +0.171 | 59 +0.928 | 148300 | C2 | 23 | 2028 | 2 | FLEX | Not on the NHS | Linton,Paoli | Bedford Unit 3,Crane Unit | Greene,Lawrence,Monroe | 2005 | 292 | Yes | 4 | 8 | 2022 | [5 empty] | 2028 | [6 empty] | 2028 Chip Seal |  | 2026 | 2028 | 2028 Chip Seal
60125 | SR 54 | From SR 58 To SR 37 | 45.9569 | 51.2257 | 59 +0.928 | 65 +0.164 | 93407 | C2 | 13 | 2028 | 2 | FLEX | Not on the NHS | Paoli | Bedford Unit 3 | Lawrence | 4407 | 338 | N/A | 4 | 8 | 2022 | [5 empty] | 2028 | [6 empty] | 2028 Chip Seal |  | 2026 | 2028 | 2028 Chip Seal
60126 | SR 545 | From 0.30 mi N SR 66 to SR 62 | 0.30128 | 13.916 | 0 +0.300 | 14 +0.027 | 240182 | C2 | 5 | 2026 | 2 | FLEX | Not on the NHS | Tell City | Derby Unit 2 | Perry,Spencer | 1679 | 131 | Yes | 4 | 8 | [6 empty] | 2039 | [6 empty] | 2039 Chip Seal |  | 2025
60127 | SR 545 | From SR 164 to SR 56 | 13.917 | 24.9753 | 14 +0.028 | 25 +0.167 | 177661 | C2 | 4 | 2026 | 2 | FLEX | Not on the NHS | Paoli,Tell City | Birdseye Unit 3,Jasper Unit 4 | Dubois | 1438 | 285 | Yes | 4 | 8 | [6 empty] | 2039 | 2027 | [5 empty] | 2039 Chip Seal | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60128 | SR 550 | From US 41 to 0.81 mi W. SR 67 ( Bruceville W. Town Limits | 0 | 3.5282 | 0 +0.000 | 3 +0.536 | 56408 | C2 | 17 | 2031 | 2 | FLEX | Not on the NHS | Linton,Vincennes | Sullivan Unit 3,Vincennes Unit 2 | Knox | 1567 | 266 | Yes | 4 | 8 | 2024 | [14 empty] | 2028
60129 | SR 550 | From SR 67 TO US 50 | 4.3437 | 13.8722 | 4 +0.351 | 13 +0.891 | 166616 | C2 | 22 | 2028 | 2 | FLEX | Not on the NHS | Linton,Vincennes | Sullivan Unit 3,Vincennes Unit 2 | Knox | 1398 | 220 | Yes | 4 | 8 | [6 empty] | 2034 | [6 empty] | 2034 Chip Seal |  | 2025
60130 | SR 550 | From 0.47 mi E. US 50 ( Loogootee E. Town Limits) TO US 150 | 14.3409 | 23.6512 | 14 +0.089 | 23 +0.386 | 125934 | C2 | 29 | 2031 | 2 | FLEX | Not on the NHS | Paoli,Vincennes | Loogootee Unit,Paoli Unit 1 | Martin | 547 | 23 | Yes | 4 | 8 | 2025 | [6 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2029 | 2027 | 2027 RPM Replacement
60131 | SR 558 | From US 231 to end SR 558 (Crane Gate) | 0 | 1.1079 | 0 +0.000 | 1 +0.107 | 18798 | C2 | 3 | 2029 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Daviess,Martin | 3709 | 369 | Yes | 4 | 8 | 2025 | [5 empty] | 2043 | [6 empty] | 2043 Chip Seal |  | 2029
60132 | SR 56 | From 2.20 mi E. US 41 (Hazelton Town Limits) to SR 65 | 2.6018 | 12.0823 | 2 +0.592 | 12 +0.134 | 136697 | C2 | 21 | 2027 | 2 | FLEX | Not on the NHS | Vincennes | Vincennes Unit 2 | Gibson,Knox,Pike | 169 | 9 | Yes | 4 | 8 | 2025 | [5 empty] | 2027 | [6 empty] | 2027 Chip Seal |  | 2029 | 2027 | 2027 Chip Seal
60133 | SR 56 | From SR 65 to 0.93 mi West of S. Jct SR 57 (Petersburg West City Limits) | 12.0823 | 17.7809 | 12 +0.134 | 17 +0.798 | 84065 | C2 | 19 | 2024 | 2 | FLEX | Not on the NHS | Vincennes | Vincennes Unit 2 | Knox,Pike | 808 | 41 | Yes | 4 | 8 | [15 empty] | 2025
60135 | SR 56 | From I-69 Interchnage E. Ramp to E. Jct SR 61 | 20.578 | 23.7377 | 20 +0.659 | 23 +0.821 | 57466 | C2 | 7 | 2027 | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Knox,Pike | 4928 | 265 | Yes | 4 | 8 | [6 empty] | 2041 | 2026 | [5 empty] | 2041 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60136 | SR 56 | From E. Jct SR 61 to SR 257 | 23.7377 | 32.0469 | 23 +0.821 | 32 +0.134 | 135261 | C2 | 1 | 2028 | 2 | FLEX | Not on the NHS | Paoli,Vincennes | Jasper Unit 4,Loogootee Unit | Knox,Pike | 3263 | 168 | Yes | 4 | 8 | 2022 | [5 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2026
60137 | SR 56 | From SR 257 to S. Jct US 231 | 32.0469 | 41.2059 | 32 +0.134 | 41 +0.300 | 159594 | C1 | 13 | 2028 | 2 | FLEX | Not on the NHS | Paoli | Jasper Unit 4 | Dubois,Pike | 7172 | 532 | N/A | 3 | 6 | [7 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60138 | SR 56 | From N. Jct US 231 (Haysville) to SR 545 | 41.2069 | 47.0908 | 41 +0.301 | 54 +0.316 | 110756 | C2 | 14 | 2028 | 2 | FLEX | Not on the NHS | Paoli | Jasper Unit 4,Paoli Unit 1 | Dubois | 3381 | 424 | Yes | 4 | 8 | [6 empty] | 2035 | [6 empty] | 2035 Chip Seal |  | 2025
60139 | SR 56 | From SR 545 to 0.80 mi W. SR 145 | 47.0908 | 58.8347 | 54 +0.316 | 66 +0.105 | 208485 | C2 | 14 | 2030 | 2 | FLEX | Not on the NHS | Paoli,Vincennes | Jasper Unit 4,Loogootee Unit,Paoli Unit 1 | Dubois,Martin,Orange | 3549 | 317 | Yes | 4 | 8 | 2025 | [5 empty] | 2037 | [6 empty] | 2037 Chip Seal |  | 2029
60140 | SR 56 | From 0.80 mi W. SR 145 to W. Jct US 150 (French Lick_West Baden) | 58.8347 | 61.4796 | 66 +0.105 | 68 +0.774 | 58898 | C1 | 8 | 2025 | 2 | FLEX | Not on the NHS | Paoli | Jasper Unit 4,Paoli Unit 1 | Orange | 7825 | 666 | N/A | 3 | 6 | [15 empty] | 2025
60141 | SR 56 | From 1.24 mi E. Jct. US 150 (Paoli) to SR 337 (District Line) | 62.7204 | 71.5585 | 79 +0.028 | 87 +0.867 | 164551 | C2 | 18 | 2028 | 2 | FLEX | Not on the NHS | Paoli | Paoli Unit 1 | Orange,Washington | 1735 | 253 | Yes | 4 | 8 | 2022 | [5 empty] | 2028 | [6 empty] | 2028 Chip Seal |  | 2026 | 2028 | 2028 Chip Seal
60142 | SR 57 | From US 41 to 1.32 N. US 41( End of Concrete) | 0 | 1.3161 | 0 +0.000 | 1 +0.321 | 37207 | B1 | 11 |  | 2 | RIGID | Is on the NHS | Evansville | Boyle Lane Unit 2 | Vanderburgh | 10896 | 912 | N/A | 3 | 6 | [15 empty] | 2025
60143 | SR 57 | From 1.32 N. US 41( End of Concrete) to S. Jct. of I 69 (end of Asphalt) | 1.3161 | 7.7505 | 1 +0.321 | 7 +0.717 | 138609 | C1 | 11 | 2025 | 2 | FLEX | Is on the NHS | Evansville | Boyle Lane Unit 2,Chandler Unit 4 | Vanderburgh | 5462 | 732 | N/A | 4 | 8 | [15 empty] | 2025
60144 | SR 57 | From N. Jct. I 69 / SR 68 to SR 64 | 8.5562 | 19.8977 | 8 +0.552 | 22 +0.900 | 236659 | C2 | 16 | 2025 | 2 | FLEX | Not on the NHS | Evansville,Vincennes | Boyle Lane Unit 2,Chandler Unit 4,Oakland City Unit | Gibson,Pike,Warrick | 1443 | 314 | N/A | 4 | 8 | [6 empty] | 2038 | [6 empty] | 2038 Chip Seal |  | 2025
60146 | SR 57 | From SR 64 to 0.66 mi S. of W. Jct SR 56 (Petersburg South City Limits) | 19.8977 | 32.1651 | 22 +0.900 | 35 +0.113 | 234071 | C2 | 5 | 2027 | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Gibson,Knox,Pike | 2185 | 481 | N/A | 4 | 8 | [6 empty] | 2041 | [6 empty] | 2041 Chip Seal |  | 2025
60147 | SR 57 | From 0.95 mi N. SR 356 (N. Petersburg City Limits) to Old US 50 | 33.9246 | 46.0912 | 37 +0.403 | 49 +0.550 | 279706 | C2 | 7 | 2027 | 2 | FLEX | Not on the NHS | Paoli,Vincennes | Jasper Unit 4,Loogootee Unit,Vincennes Unit 2 | Daviess,Knox,Pike | 4423 | 971 | N/A | 4 | 8 | [6 empty] | 2041 | [6 empty] | 2041 Chip Seal |  | 2025
60148 | SR 57 | From N. City Limits of Washington to 0.41 mi S. SR 358 (Plainville S.Town Limits) | 47.3132 | 56.8201 | 50 +0.746 | 60 +0.252 | 175140 | C2 | 2 | 2028 | 2 | FLEX | Not on the NHS | Vincennes | Loogootee Unit,Vincennes Unit 2 | Daviess,Knox | 2347 | 515 | N/A | 4 | 8 | 2021 | [5 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2025
60150 | SR 57 | From 6.09 mi N. of W. Jct. SR 58 (S. Approach) White River to US 231 / SR 54 | 69.415 | 76.6726 | 72 +0.792 | 80 +0.070 | 135816 | C2 | 15 | 2027 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Greene | 1778 | 391 | N/A | 4 | 8 | [6 empty] | 2034 | [6 empty] | 2034 Chip Seal |  | 2025
60151 | SR 58 | From 0.79 mi E. SR 63 (Merom E. Town Limits) to US 41 | 0.79233 | 13.5293 | 0 +0.783 | 13 +0.698 | 200353 | C2 | 25 | 2028 | 2 | FLEX | Not on the NHS | Linton | Sullivan Unit 3 | Sullivan | 357 | 43 | Yes | 4 | 8 | 2021 | [5 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2025
60152 | SR 58 | From US 41 to 0.79 mi E. US 41 (RR Track) | 13.5293 | 14.3384 | 13 +0.698 | 14 +0.528 | 13758 | C1 | 6 |  | 2 | FLEX | Not on the NHS | Linton | Sullivan Unit 3 | Sullivan | 1273 | 154 | N/A | 4 | 8 | [7 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60153 | SR 58 | From 0.79 mi E. of US 41 (RR Track) to 0.34 mi W. SR 159 | 14.3384 | 22.9658 | 14 +0.528 | 23 +0.211 | 137382 | C2 | 3 | 2028 | 2 | FLEX | Not on the NHS | Linton | Linton,Sullivan Unit 3 | Knox,Sullivan | 741 | 89 | Yes | 4 | 8 | [6 empty] | 2042 | 2026 | [5 empty] | 2042 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60154 | SR 58 | From 0.90 mi E. SR 159 to W. Jct. SR 67 | 24.2033 | 28.4867 | 24 +0.475 | 29 +0.216 | 68924 | C2 | 24 | 2029 | 2 | FLEX | Not on the NHS | Linton | Linton,Sullivan Unit 3 | Daviess,Knox | 460 | 55 | Yes | 4 | 8 | 2023 | [5 empty] | 2043 | [6 empty] | 2043 Chip Seal |  | 2027
60155 | SR 58 | From W. Jct. SR 67 to E. Jct. SR 67 | 28.4867 | 29.793 | 29 +0.216 | 29 +1.522 | 22880 | C2 | 16 | 2030 | 2 | FLEX | Not on the NHS | Linton | Linton | Daviess,Knox | 2567 | 310 | Yes | 4 | 8 | [6 empty] | 2030 | [6 empty] | 2030 Chip Seal |  | 2025
60156 | SR 58 | From E. Jct. SR 67 to W. Jct SR 57 | 29.793 | 36.2703 | 29 +1.522 | 36 +0.705 | 108907 | C2 | 14 | 2025 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Daviess,Knox | 1651 | 197 | Yes | 4 | 8 | 2025 | [5 empty] | 2025 | [6 empty] | 2025 Chip Seal |  | 2029
60157 | SR 58 | From E. Jct. of SR 57 to SR 358 (Thru Town Limits of Elnora) | 36.2713 | 38.27 | 36 +0.706 | 38 +0.801 | 31857 | C2 | 4 | 2029 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Daviess | 1762 | 211 | Yes | 4 | 8 | [6 empty] | 2043 | [6 empty] | 2043 Chip Seal |  | 2025
60159 | SR 58 | From SR 45 to SR 54 | 47.2537 | 54.9051 | 47 +0.781 | 69 +0.228 | 138834 | C2 | 4 | 2029 | 2 | FLEX | Not on the NHS | Paoli | Bedford Unit 3 | Greene,Lawrence | 3254 | 296 | Yes | 4 | 8 | [6 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2025
60160 | SR 58 | From SR 37 to 4.78 mi E. of SR 37 (Co. Rd N200E) | 54.9061 | 59.625 | 69 +0.229 | 82 +0.215 | 77844 | C1 | 9 |  | 2 | FLEX | Not on the NHS | Paoli | Bedford Unit 3 | Lawrence | 5166 | 308 | N/A | 4 | 8 | [7 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60161 | SR 58 | From 4.78 mi E. of SR 37 (Co. Rd N200E) to SR 446 (District Line) | 59.625 | 66.4711 | 82 +0.215 | 89 +0.061 | 101720 | C2 | 2 | 2028 | 2 | FLEX | Not on the NHS | Paoli | Bedford Unit 3 | Lawrence | 613 | 36 | Yes | 4 | 8 | 2021 | [5 empty] | 2042 | 2026 | [5 empty] | 2042 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60162 | SR 59 | From SR 58 to SR 67 (Thru Town Limits of Sandborn) | 0 | 1.6047 | 0 +0.000 | 1 +0.611 | 32177 | C1 | 20 |  | 2 | FLEX | Not on the NHS | Linton | Linton | Daviess,Knox | 1176 | 68 | N/A | 4 | 8 | 2024 | [14 empty] | 2028
60163 | SR 59 | From SR 67 to 1.05 mi S. SR 54 (Co. Rd 25 S) | 1.6047 | 10.7999 | 1 +0.611 | 10 +0.760 | 146629 | C2 | 20 | 2025 | 2 | FLEX | Not on the NHS | Linton | Linton | Daviess,Greene,Knox | 2173 | 261 | Yes | 4 | 8 | [6 empty] | 2031 | [6 empty] | 2031 Chip Seal |  | 2025
60164 | SR 59 | From N. Jct. SR 54 to SR 48 | 11.8469 | 18.7123 | 12 +0.018 | 21 +0.441 | 114934 | C2 | 17 | 2026 | 2 | FLEX | Not on the NHS | Linton | Linton | Greene | 3861 | 463 | Yes | 4 | 8 | 2024 | [5 empty] | 2040 | [6 empty] | 2040 Chip Seal |  | 2028
60165 | SR 60 | From US 50 to W. Jct. SR 37 | 0 | 8.8407 | 0 -0.076 | 8 +0.739 | 167414 | C2 | 6 | 2027 | 2 | FLEX | Not on the NHS | Paoli | Bedford Unit 3,Paoli Unit 1 | Lawrence | 2238 | 232 | Yes | 4 | 8 | [6 empty] | 2039 | [6 empty] | 2039 Chip Seal |  | 2025
60166 | SR 60 | From E. Jct. SR 37 to 12.30 mi E. SR 37 (District line) | 8.8417 | 20.14 | 8 +0.740 | 20 +0.875 | 201896 | C2 | 2 | 2029 | 2 | FLEX | Is on the NHS | Paoli | Bedford Unit 3,Paoli Unit 1 | Lawrence,Orange | 3518 | 445 | Yes | 4 | 8 | 2021 | [5 empty] | 2043 | [6 empty] | 2043 Chip Seal |  | 2025
60167 | SR 61 | From SR 66 to E. Jct. SR 62 | 0 | 8.823 | 0 +0.000 | 8 +0.820 | 244874 | C2 | 8 | 2032 | 2 | RIGID | Not on the NHS | Evansville | Boyle Lane Unit 2,Chandler Unit 4 | Warrick | 3680 | 233 | N/A | 4 | 8 |  | 2032 | [5 empty] | 2026 | 2032 Preventive Maintenance | [5 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60168 | SR 61 | From W. Jct. SR 62 to E. Jct. SR 62 | 8.823 | 9.2745 | 8 +0.820 | 9 +0.061 | 29625 | B2 | 1 |  | 4 | RIGID | Not on the NHS | Evansville | Chandler Unit 4 | Warrick | 18159 | 1020 | N/A | 3 | 6 | [7 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60169 | SR 61 | From New Harmony / Shelton Rd Roundabout (Old SR 61) to 0.14 mi S. of I 64 | 13.4816 | 20.6962 | 12 +0.716 | 19 +0.696 | 124454 | C2 | 14 | 2026 | 2 | FLEX | Not on the NHS | Evansville,Tell City | Chandler Unit 4,Dale Unit 4 | Warrick | 4290 | 239 | No | 4 | 8 | [15 empty] | 2025
60170 | SR 61 | From 0.88 mi N of SR 68 (N Town Limits Lynnville) to SR 64 | 21.9871 | 33.2098 | 20 +1.001 | 32 +0.269 | 190852 | C2 | 19 | 2024 | 2 | FLEX | Not on the NHS | Evansville,Tell City | Boyle Lane Unit 2,Dale Unit 4 | Pike,Warrick | 755 | 100 | Yes | 4 | 8 | [15 empty] | 2025
60171 | SR 61 | From SR 64 to 3.3 mi N. SR 64 (S. Winslow Town Limts) | 33.2098 | 36.5175 | 32 +0.269 | 35 +0.660 | 58252 | C2 | 7 | 2025 | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Pike | 1765 | 233 | Yes | 4 | 8 | [6 empty] | 2039 | 2026 | [5 empty] | 2039 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60172 | SR 61 | From 1.10 miles N of Jct with SR 56/SR 57 to 0.83 mi S. of S. Jct. SR 241 | 42.3256 | 51.0155 | 45 +0.978 | 54 +0.640 | 157208 | C2 | 24 | 2025 | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Gibson,Knox,Pike | 1888 | 249 | Yes | 4 | 8 | [6 empty] | 2033 | [6 empty] | 2033 Chip Seal |  | 2025
60173 | SR 61 | From the N. Jct. SR 241 to 0.20 mi E. US 41 (Kimmell Rd- Vincennes)) | 52.3351 | 60.7646 | 55 +0.971 | 64 +0.335 | 141238 | C2 | 21 | 2031 | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Knox | 2654 | 350 | Yes | 4 | 8 | 2024 | [14 empty] | 2028
60174 | SR 62 | From IL/IN State line to 1.96 mi E of W. Jct SR 69 (Park St) | 0 | 7.3705 | 0 -0.794 | 6 +0.614 | 138968 | C2 | 13 | 2028 | 2 | FLEX | Not on the NHS | Evansville | Poseyville Unit 3 | Posey | 4846 | 642 | N/A | 4 | 8 | [6 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2025
60175 | SR 62 | From 1.96 mi E of W. Jct SR 69 (Park St) to 1.34 mi W. of E. Jct SR 69 | 7.3705 | 9.3487 | 6 +0.614 | 8 +0.590 | 57069 | B1 | 5 |  | 2 | FLEX | Not on the NHS | Evansville | Evansville Unit 1,Poseyville Unit 3 | Posey | 12781 | 1333 | N/A | 3 | 6 |  | 2041 | [6 empty] | 2041 Preventive Maintenance | [6 empty] | 2025
60176 | SR 62 | From 1.34 mi W. of E. Jct SR 69 to 8.45 mi E. of E. Jct. SR 69 (Posey / Vand. Co. Line) | 9.3487 | 19.1424 | 8 +0.590 | 18 +0.393 | 455979 | B2 | 5 |  | 4 | RIGID | Is on the NHS | Evansville | Evansville Unit 1,Poseyville Unit 3 | Posey | 15442 | 1774 | N/A | 3 | 6 |  | 2028 | 2035 |  |  |  |  | 2027 | 2028 Pavement Patching | 2035 Minor Structural |  |  |  |  | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60178 | SR 62 | From US-41 to 0.25 mi E of I-69 | 28.2388 | 32.5206 | 27 +0.497 | 32 +0.813 | 150728 | B2 | 4 |  | 4 | FLEX | Not on the NHS | Evansville | Chandler Unit 4,Evansville Unit 1 | Vanderburgh,Warrick | 19552 | 604 | N/A | 3 | 6 | [15 empty] | 2025
60179 | SR 62 | From Posey/Vanderburgh Co. Line to 5.60 mi W of S Jct US 41 (Boehne Camp Rd) | 19.1424 | 22.6305 | 18 +0.393 | 21 +0.899 | 190791 | B1 | 4 | 2024 | 4 | FLEX | Is on the NHS | Evansville | Evansville Unit 1,Poseyville Unit 3 | Posey,Vanderburgh | 26205 | 1557 | N/A | 3 | 6 |  | 2042 | [6 empty] | 2042 Preventive Maintenance | [6 empty] | 2025
60180 | SR 62 | From 0.24 mi East of E. Jct SR 61 to 1.38 mi E. of E. Jct SR 61 (Boonvile E. Corporate Limits) | 42.8747 | 44.681 | 42 +1.169 | 45 +0.363 | 27060 | B1 | 3 |  | 2 | FLEX | Not on the NHS | Evansville,Tell City | Chandler Unit 4,Chrisney Unit 5 | Spencer,Warrick | 11860 | 439 | N/A | 3 | 6 |  | 2036 | [6 empty] | 2036 Preventive Maintenance | [6 empty] | 2025
60181 | SR 62 | From 1.38 mi E. of E. Jct SR 61 (Boonville E. Corporate Limits) to E. Jct SR 161 | 44.681 | 53.538 | 45 +0.363 | 54 +0.216 | 159881 | C2 | 18 | 2029 | 2 | FLEX | Not on the NHS | Evansville,Tell City | Chandler Unit 4,Chrisney Unit 5 | Spencer,Warrick | 2739 | 101 | Yes | 4 | 8 | 2023 | [5 empty] | 2029 | [6 empty] | 2029 Chip Seal |  | 2027 | 2029 | 2029 Chip Seal
60182 | SR 62 | From E. Jct SR 161 to S. Jct US 231 | 53.538 | 64.5953 | 54 +0.216 | 65 +0.350 | 205120 | C2 | 15 | 2029 | 2 | FLEX | Not on the NHS | Tell City | Chrisney Unit 5 | Spencer,Warrick | 1430 | 121 | Yes | 4 | 8 | 2023 | [5 empty] | 2029 | [6 empty] | 2029 Chip Seal |  | 2027 | 2029 | 2029 Chip Seal
60183 | SR 62 | From N. Jct. US 231 to SR 245 (Dale) | 64.5963 | 66.1918 | 65 +0.351 | 67 +0.487 | 35538 | C1 | 1 |  | 2 | FLEX | Not on the NHS | Tell City | Chrisney Unit 5,Dale Unit 4 | Spencer | 2424 | 261 | N/A | 4 | 8 | 2022 | [6 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2026 | 2027 | 2027 RPM Replacement
60184 | SR 62 | From SR 245 to SR 162 | 66.1918 | 71.325 | 67 +0.487 | 72 +0.632 | 89367 | C2 | 18 | 2028 | 2 | FLEX | Not on the NHS | Tell City | Chrisney Unit 5,Dale Unit 4 | Spencer | 1367 | 125 | Yes | 4 | 8 | [6 empty] | 2028 | [6 empty] | 2028 Chip Seal |  | 2025
60187 | SR 62 | From SR 145 to SR 37 | 84.0086 | 90.1853 | 85 +0.351 | 91 +0.442 | 95136 | C2 | 22 | 2026 | 2 | FLEX | Not on the NHS | Paoli,Tell City | Birdseye Unit 3,Jasper Unit 4 | Dubois,Perry | 258 | 41 | Yes | 4 | 8 | [6 empty] | 2026 | 2027 | [5 empty] | 2026 Chip Seal | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60188 | SR 62 | From SR 37 to W. Jct. SR 66 / SR 237 (Sulphur) | 90.1853 | 97.48 | 91 +0.442 | 98 +0.798 | 100879 | C2 | 19 | 2030 | 2 | FLEX | Not on the NHS | Tell City | Birdseye Unit 3,Derby Unit 2 | Crawford,Perry | 269 | 16 | Yes | 4 | 8 | [6 empty] | 2037 | 2027 | [5 empty] | 2037 Chip Seal | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60189 | SR 62 | From W. Jct. SR 66 / SR 237 (Sulphur) to E. Jct. SR 66 | 97.48 | 105.2217 | 98 +0.798 | 106 +0.531 | 112499 | C2 | 19 | 2030 | 2 | FLEX | Not on the NHS | Tell City | Birdseye Unit 3,Derby Unit 2 | Crawford,Perry | 393 | 15 | Yes | 4 | 8 | [6 empty] | 2030 | 2027 | [5 empty] | 2030 Chip Seal | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60190 | SR 63 | From SR 58 (Merom) to SR 154 | 0 | 4.3361 | 0 -0.036 | 4 +0.338 | 63793 | C2 | 25 | 2028 | 2 | FLEX | Not on the NHS | Linton | Sullivan Unit 3 | Sullivan | 593 | 71 | Yes | 4 | 8 | 2021 | [5 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2025
60191 | SR 63 | From SR 48 to SR 246 | 10.666 | 16.3182 | 10 +0.648 | 16 +0.274 | 86969 | C2 | 15 | 2027 | 2 | FLEX | Not on the NHS | Linton | Sullivan Unit 3 | Sullivan,Vigo | 1496 | 179 | Yes | 4 | 8 | [6 empty] | 2027 | [6 empty] | 2027 Chip Seal |  | 2025
60192 | SR 64 | From 0.35 mi E. of IL/IN (East End of Bridge) to 1.36 mi E of the W Jct of SR-65 | 0 | 6.0947 | 0 +0.000 | 6 +0.111 | 124499 | C1 | 6 |  | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Gibson | 7990 | 1137 | N/A | 3 | 6 | [15 empty] | 2025
60193 | SR 64 | From 1.36 mi E of the W Jct of SR-65 to US 41 | 6.0947 | 9.5637 | 6 +0.111 | 9 +0.534 | 69680 | C1 | 3 |  | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit | Gibson | 10217 | 1490 | N/A | 3 | 6 | [15 empty] | 2025
60194 | SR 64 | From US 41 to 1.01 mi E. Of US 41 (Brown St) | 9.5637 | 10.5741 | 9 +0.534 | 10 +0.559 | 47943 | B2 | 0 |  | 4 | FLEX | Not on the NHS | Vincennes | Oakland City Unit | Gibson | 13118 | 1913 | N/A | 3 | 6 | 2023 | [14 empty] | 2026
60195 | SR 64 | From 1.01 mi E. Of US 41 (Brown St) to 2.88 mi E of US 41 (Lake Road) | 10.5741 | 12.441 | 10 +0.559 | 12 +0.464 | 37991 | C1 | 9 | 2026 | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit | Gibson | 7599 | 1107 | N/A | 3 | 6 | [15 empty] | 2025
60196 | SR 64 | From 2.88 mi E of US 41 (Lake Road) to 3.10 Mi W. of I-69 (300' W. RR Track in Francisco) | 12.441 | 18.3389 | 12 +0.464 | 18 +0.366 | 120042 | C2 | 15 | 2026 | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit | Gibson,Pike | 4348 | 159 | N/A | 4 | 8 | [6 empty] | 2039 | 2026 | [5 empty] | 2039 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60197 | SR 64 | From 0.76 mi E. SR 357 to SR 61 | 25.0671 | 29.9818 | 25 +0.027 | 29 +0.948 | 97188 | C2 | 2 | 2029 | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit | Gibson,Pike | 3529 | 281 | Yes | 4 | 8 | 2021 | [5 empty] | 2043 | [6 empty] | 2043 Chip Seal |  | 2025
60198 | SR 64 | From SR 61 to SR 257 | 29.9818 | 36.5134 | 29 +0.948 | 36 +0.401 | 110752 | C2 | 13 | 2027 | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit | Pike | 1988 | 158 | No | 4 | 8 | [15 empty] | 2025
60199 | SR 64 | From SR 257 to SR 161 | 36.5134 | 41.9997 | 36 +0.401 | 41 +0.890 | 94179 | C2 | 13 | 2027 | 2 | FLEX | Not on the NHS | Paoli,Tell City | Dale Unit 4,Jasper Unit 4 | Dubois,Pike | 2665 | 425 | No | 4 | 8 | [6 empty] | 2041 | [6 empty] | 2041 Chip Seal |  | 2025
60200 | SR 64 | From SR 161 to 1.52 mi W. of US 231 (WCL Huntingburg) | 41.9997 | 44.8401 | 41 +0.890 | 44 +0.724 | 49535 | C1 | 18 |  | 2 | FLEX | Not on the NHS | Tell City | Dale Unit 4 | Dubois | 5357 | 526 | N/A | 4 | 8 | [15 empty] | 2025
60201 | SR 64 | From 1.02 mi E. US 231 (ECL Huntingburg) to SR 162 | 47.375 | 50.96 | 47 +0.283 | 50 +0.769 | 66107 | C2 | 0 | 2031 | 2 | FLEX | Not on the NHS | Paoli,Tell City | Dale Unit 4,Jasper Unit 4 | Dubois | 3839 | 470 | N/A | 4 | 8 | 2023 | [5 empty] | 2044 | [6 empty] | 2044 Chip Seal |  | 2027
60202 | SR 64 | From SR 162 to W. Jct. SR 145 (Birdseye) | 50.96 | 61.45 | 50 +0.769 | 61 +0.365 | 196627 | C2 | 18 | 2030 | 2 | FLEX | Not on the NHS | Paoli,Tell City | Dale Unit 4,Jasper Unit 4 | Dubois | 3411 | 528 | No | 4 | 8 | 2025 | [14 empty] | 2029
60203 | SR 64 | From W. Jct SR 145 (Birdseye) to W. Jct SR 37 | 61.45 | 66.9741 | 61 +0.365 | 66 +0.812 | 121380 | C2 | 2 | 2028 | 2 | FLEX | Not on the NHS | Paoli | Jasper Unit 4,Paoli Unit 1 | Crawford,Dubois | 2185 | 378 | Yes | 4 | 8 | 2025 | [5 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2029
60204 | SR 64 | From E. Jct. SR 37 / SR 237 to W. Jct SR 66 (Marengo) | 66.9751 | 74.2196 | 66 +0.813 | 82 +0.342 | 146204 | C2 | 25 | 2025 | 2 | FLEX | Not on the NHS | Paoli,Tell City | Birdseye Unit 3,Paoli Unit 1 | Crawford | 3291 | 340 | Yes | 4 | 8 | [6 empty] | 2038 | [6 empty] | 2038 Chip Seal |  | 2025
60205 | SR 64 | From W. Jct SR 66 (Marengo) to E. Jct. SR 66 (District Line) | 74.2196 | 77.9087 | 82 +0.342 | 85 +0.990 | 77032 | C2 | 25 | 2025 | 2 | FLEX | Not on the NHS | Tell City | Birdseye Unit 3 | Crawford,Harrison | 3741 | 332 | Yes | 4 | 8 | [6 empty] | 2038 | [6 empty] | 2038 Chip Seal |  | 2025
60206 | SR 645 | From US 231 to End SR 645 (Crane Gate) | 0 | 1.9687 | 0 +0.000 | 1 +0.968 | 31286 | C2 | 3 | 2029 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Daviess,Martin | 1330 | 160 | Yes | 4 | 8 | [6 empty] | 2043 | 2026 | [5 empty] | 2043 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60207 | SR 65 | From SR 66 to I-64 | 0 | 10.9224 | 0 -0.037 | 10 +0.914 | 185103 | C2 | 18 | 2027 | 2 | FLEX | Not on the NHS | Evansville | Boyle Lane Unit 2,Evansville Unit 1 | Vanderburgh | 3612 | 254 | Yes | 4 | 8 | [6 empty] | 2027 | [6 empty] | 2027 Chip Seal |  | 2025
60208 | SR 65 | From I-64 to 0.60 mi S. of W. Jct. SR 68 | 10.9224 | 12.9648 | 10 +0.914 | 13 +0.026 | 40209 | C2 | 21 | 2027 | 2 | FLEX | Not on the NHS | Evansville | Boyle Lane Unit 2,Poseyville Unit 3 | Gibson,Posey,Vanderburgh | 1779 | 184 | Yes | 4 | 8 | [6 empty] | 2027 | [6 empty] | 2027 Chip Seal |  | 2025
60209 | SR 65 | From N. Jct. SR 68 to 0.26 mi S. SR 168 (S. Limits Owensville) | 14.899 | 19.7782 | 14 +0.910 | 19 +0.848 | 69973 | C2 | 21 | 2027 | 2 | FLEX | Not on the NHS | Evansville | Boyle Lane Unit 2,Poseyville Unit 3 | Gibson,Posey | 1383 | 154 | Yes | 4 | 8 | [6 empty] | 2027 | [6 empty] | 2027 Chip Seal |  | 2025
60211 | SR 65 | From E. Jct. SR 64 to 1. 70 N. SR 64 (N Old Petersburg Rd) (Princeton) | 26.2703 | 27.9713 | 26 +0.346 | 34 +0.564 | 29008 | C1 | 22 | 2024 | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Gibson | 4305 | 469 | N/A | 4 | 8 | [15 empty] | 2025
60212 | SR 65 | From 1. 70 N. SR 64 (N Old Petersburg Rd) to SR 56 | 27.9713 | 41.1611 | 34 +0.564 | 47 +0.664 | 199651 | C2 | 22 | 2027 | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Gibson,Knox,Pike | 841 | 91 | Yes | 4 | 8 | [6 empty] | 2041 | [6 empty] | 2041 Chip Seal |  | 2025
60213 | SR 650 | From US 50 to End SR 650 (Gypsum Plant Gate) | 0 | 0.87904 | 0 +0.000 | 0 +0.878 | 12693 | C2 | 3 | 2029 | 2 | FLEX | Not on the NHS | Linton,Paoli | Bedford Unit 3,Crane Unit | Martin | 929 | 112 | Yes | 4 | 8 | [6 empty] | 2043 | 2026 | [5 empty] | 2043 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60214 | SR 66 | From N. Jct. SR 69 to SR 165 | 0 | 6.723 | 0 +0.000 | 8 +0.779 | 129496 | C2 | 15 | 2028 | 2 | FLEX | Not on the NHS | Evansville | Poseyville Unit 3 | Posey | 1890 | 188 | Yes | 4 | 8 | 2023 | [5 empty] | 2035 | [6 empty] | 2035 Chip Seal |  | 2027
60215 | SR 66 | From SR 165 to 4.3 mi W. SR 65 (Beginning of 4 Lane Section) | 6.723 | 13.4305 | 8 +0.779 | 15 +0.481 | 145351 | C1 | 0 |  | 2 | FLEX | Not on the NHS | Evansville | Evansville Unit 1,Poseyville Unit 3 | Posey | 6814 | 378 | N/A | 3 | 6 | 2023 | [14 empty] | 2026
60216 | SR 66 | From 4.3 mi W. SR 65 (Beginning of 4 Lane Section) to 2.11 mi E. SR 65 | 13.4305 | 19.7407 | 15 +0.481 | 21 +0.735 | 298335 | B2 | 9 |  | 4 | FLEX | Not on the NHS | Evansville | Evansville Unit 1,Poseyville Unit 3 | Posey,Vanderburgh | 10369 | 681 | N/A | 3 | 6 | [7 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60217 | SR 66 | From 2.11 mi E. SR 65 to N. Jct US 41 | 19.7407 | 23.697 | 21 +0.735 | 25 +0.686 | 265509 | B1 | 17 |  | 4 | RIGID | Not on the NHS | Evansville | Evansville Unit 1 | Vanderburgh | 17838 | 1099 | N/A | 3 | 6 | [15 empty] | 2025
60218 | SR 66 | From S. Jct US 41 to I-69 | 23.698 | 28.7215 | 25 +0.687 | 32 +0.144 | 272572 | B1 | 3 |  | 6 | RIGID | Is on the NHS | Evansville | Chandler Unit 4,Evansville Unit 1 | Vanderburgh,Warrick | 54934 | 1521 | N/A | 2 | 4 | [15 empty] | 2025
60219 | SR 66 | From I-69 to 0.2 E. SR 261 (End of Concrete/ Beginning of Asphalt) | 28.7215 | 32.1947 | 32 +0.144 | 35 +0.600 | 199134 | B1 | 3 |  | 6 | RIGID | Is on the NHS | Evansville | Chandler Unit 4,Evansville Unit 1 | Warrick | 34920 | 1413 | N/A | 2 | 4 | [15 empty] | 2025
60220 | SR 66 | From 0.2 E. SR 261 (End of Concrete/ Beginning of Asphalt) to SR 61 | 32.1947 | 38.1571 | 35 +0.600 | 41 +0.579 | 277315 | B2 | 13 |  | 4 | FLEX | Is on the NHS | Evansville | Chandler Unit 4 | Warrick | 14757 | 778 | N/A | 3 | 6 | [7 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60221 | SR 66 | From SR 61 to End of 4 Lane | 38.1571 | 44.8179 | 41 +0.579 | 48 +0.239 | 312639 | B2 | 2 |  | 4 | FLEX | Is on the NHS | Evansville,Tell City | Chandler Unit 4,Chrisney Unit 5 | Spencer,Warrick | 11589 | 1007 | N/A | 3 | 6 | 2021 | [14 empty] | 2024
60222 | SR 66 | From End of 4 Lane to 2.52 mi W. US 231 (W. City Limits Rockports) | 44.8179 | 52.5728 | 48 +0.239 | 55 +0.814 | 137732 | C1 | 2 |  | 2 | FLEX | Is on the NHS | Evansville,Tell City | Chandler Unit 4,Chrisney Unit 5 | Spencer,Warrick | 9281 | 1051 | N/A | 3 | 6 | 2021 | [14 empty] | 2024
60223 | SR 66 | From 2.52 mi W. US 231 (W. City Limits Rockport) to 1.19 W. of US 231 | 52.5728 | 53.9033 | 55 +0.814 | 57 +0.202 | 24259 | C1 | 17 | 2026 | 2 | FLEX | Is on the NHS | Tell City | Chrisney Unit 5 | Spencer,Warrick | 6233 | 665 | N/A | 3 | 6 | 2021 | [14 empty] | 2024
60224 | SR 66 | From 1.19 W. of US 231 to 0.15 E. SR 70 (Bridge Over Crooked CreeK) | 53.9033 | 67.7973 | 57 +0.202 | 71 +0.062 | 267132 | C2 | 5 | 2028 | 2 | FLEX | Not on the NHS | Tell City | Chrisney Unit 5,Derby Unit 2 | Spencer,Warrick | 2989 | 476 | N/A | 4 | 8 | [6 empty] | 2042 | 2027 | [5 empty] | 2042 Chip Seal | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60225 | SR 66 | From 0.15 E. SR 70 (Bridge Over Crooked Creek) to 0.18 mi W. SR 545 | 67.7973 | 70.6406 | 71 +0.062 | 73 +0.901 | 54184 | C1 | 15 |  | 2 | FLEX | Not on the NHS | Tell City | Chrisney Unit 5,Derby Unit 2 | Perry,Spencer | 4814 | 660 | N/A | 4 | 8 | [15 empty] | 2025
60226 | SR 65 | From 0.67 mi N of SR 165 (Old Princeton Rd) to W. Jct. SR 64 | 20.9076 | 26.2693 | 20 +0.940 | 26 +0.345 | 79308 | C1 | 6 |  | 2 | FLEX | Not on the NHS | Evansville,Vincennes | Oakland City Unit,Poseyville Unit 3 | Gibson | 3664 | 399 | N/A | 4 | 8 | [15 empty] | 2025
60227 | SR 66 | From N. Jct SR 37 to 1.9 mi E of SR 37 | 73.9133 | 75.8508 | 77 +0.216 | 79 +0.403 | 86537 | B1 | 1 |  | 2 | FLEX | Not on the NHS | Tell City | Derby Unit 2 | Perry | 11086 | 600 | N/A | 3 | 6 | 2025 | [14 empty] | 2028
60228 | SR 66 | From 1.9 mi E of SR 37 to SR 237 | 75.8508 | 78.2125 | 79 +0.403 | 81 +0.751 | 55381 | B1 | 7 |  | 2 | FLEX | Not on the NHS | Tell City | Derby Unit 2 | Perry | 9968 | 437 | N/A | 3 | 6 | 2021 | 2036 | [6 empty] | 2036 Preventive Maintenance | [6 empty] | 2024
60229 | SR 66 | From SR 237 SR 166 | 78.2125 | 82.5449 | 81 +0.751 | 86 +0.098 | 75502 | C2 | 4 | 2028 | 2 | FLEX | Not on the NHS | Tell City | Derby Unit 2 | Perry | 1407 | 75 | N/A | 4 | 8 | 2021 | 2034 |  |  |  |  | 2042 |  | 2034 Preventive Maintenance |  |  |  |  | 2042 Chip Seal |  | 2025
60230 | SR 66 | From SR 166 to SR 70 | 82.5449 | 99.7087 | 86 +0.098 | 103 +0.170 | 131648 | C2 | 4 | 2028 | 2 | FLEX | Not on the NHS | Tell City | Derby Unit 2 | Perry | 169 | 30 | Yes | 4 | 8 | [6 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2025
60231 | SR 66 | From SR 70 W. Jct SR 62 | 99.7087 | 118.2152 | 103 +0.170 | 121 +0.659 | 264309 | C2 | 4 | 2028 | 2 | FLEX | Not on the NHS | Tell City | Birdseye Unit 3,Derby Unit 2 | Crawford,Perry | 242 | 22 | Yes | 4 | 8 | [6 empty] | 2042 | 2027 | [5 empty] | 2042 Chip Seal | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60232 | SR 66 | From E. Jct. SR 62 to 0.93 mi S. SR 64 ( S. Marengo Town Limits) | 118.2162 | 129.5615 | 121 +0.660 | 140 +0.742 | 194323 | C2 | 2 | 2028 | 2 | FLEX | Not on the NHS | Tell City | Birdseye Unit 3,Derby Unit 2 | Crawford | 2652 | 276 | Yes | 4 | 8 | 2021 | [5 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2025
60233 | SR 66 | From 0.93 mi S. SR 64 ( S. Marengo Town Limits) to SR 64 | 129.5615 | 130.4946 | 140 +0.742 | 141 +0.688 | 17047 | C2 | 1 | 2031 | 2 | FLEX | Not on the NHS | Paoli,Tell City | Birdseye Unit 3,Paoli Unit 1 | Crawford | 3593 | 219 | Yes | 4 | 8 | 2022 | [5 empty] | 2044 | [6 empty] | 2044 Chip Seal |  | 2026
60234 | SR 66 | From E. Jct SR 64 to US 150 | 130.4956 | 137.5577 | 141 +0.689 | 152 +0.392 | 106772 | C2 | 2 | 2030 | 2 | FLEX | Not on the NHS | Paoli | Paoli Unit 1 | Crawford,Harrison,Washington | 727 | 51 | Yes | 4 | 8 | 2021 | [5 empty] | 2044 | [6 empty] | 2044 Chip Seal |  | 2025
60235 | SR 662 | From I-69 to End SR 62 ( Ellerbusch Co. Rd 950 W) | 0 | 1.5567 | 0 +0.000 | 1 +0.504 | 43375 | B1 | 3 |  | 4 | FLEX | Not on the NHS | Evansville | Chandler Unit 4,Evansville Unit 1 | Warrick | 12853 | 767 | N/A | 3 | 6 | [15 empty] | 2025
60236 | SR 67 | From US 41 to 0.50 mile N. of SR 550 | 0 | 5.509 | 0 +0.000 | 5 +0.550 | 165224 | C1 | 22 |  | 2 | FLEX | Not on the NHS | Linton,Vincennes | Sullivan Unit 3,Vincennes Unit 2 | Knox | 6964 | 702 | N/A | 3 | 6 | 2024 | [14 empty] | 2027
60237 | SR 67 | From 0.50 mile N of SR 550 to 0.51 mile S of SR 159 | 5.509 | 10.5122 | 5 +0.550 | 10 +0.539 | 135688 | C1 | 7 |  | 2 | FLEX | Not on the NHS | Linton,Vincennes | Sullivan Unit 3,Vincennes Unit 2 | Knox | 6573 | 959 | N/A | 3 | 6 | [7 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60238 | SR 67 | From 0.70 mi N SR 159 (Bicknell N. City Limits) to 1.03 mi N. SR 358 (Edwardsport S. Town Limits) | 11.7117 | 14.9301 | 11 +0.734 | 14 +0.943 | 54974 | C2 | 16 | 2030 | 2 | FLEX | Not on the NHS | Linton,Vincennes | Linton,Sullivan Unit 3,Vincennes Unit 2 | Daviess,Knox | 3848 | 560 | Yes | 4 | 8 | [6 empty] | 2030 | [6 empty] | 2030 Chip Seal |  | 2025
60239 | SR 67 | From 1.63 mi. N. SR 358 (Edwardsport N. Town Limits) to S. Jct. SR 58 | 15.5305 | 19.063 | 15 +0.556 | 19 +0.072 | 56122 | C2 | 16 | 2030 | 2 | FLEX | Not on the NHS | Linton,Vincennes | Linton,Loogootee Unit | Daviess,Knox | 1929 | 321 | Yes | 4 | 8 | [6 empty] | 2030 | [6 empty] | 2030 Chip Seal |  | 2025
60240 | SR 67 | From N. Jct. SR 58 to 4.02 mi S. SR 54 Lyons S. City Limits | 19.064 | 29.246 | 19 +0.073 | 30 +0.540 | 184833 | C2 | 14 | 2025 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Daviess,Greene,Knox | 1090 | 159 | Yes | 4 | 8 | [6 empty] | 2033 | 2026 | [5 empty] | 2033 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60241 | SR 67 | From 3.02 mi. S. SR 54 (Lyons N. Town Limits to SR 54) | 30.2442 | 33.2592 | 31 +0.558 | 34 +0.575 | 53594 | C2 | 14 | 2025 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Greene | 1815 | 265 | Yes | 4 | 8 | [6 empty] | 2033 | 2026 | [5 empty] | 2033 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60242 | SR 67 | From SR 54 to US 231 | 33.2592 | 37.2349 | 34 +0.575 | 38 +0.349 | 69501 | C2 | 9 | 2028 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Greene | 2791 | 406 | Yes | 4 | 8 | [6 empty] | 2035 | [6 empty] | 2035 Chip Seal |  | 2025
60243 | SR 68 | From SR 69 to S. Jct. SR 165 | 0 | 6.4252 | 0 +0.000 | 6 +0.333 | 84541 | C2 | 0 | 2031 | 2 | FLEX | Not on the NHS | Evansville | Poseyville Unit 3 | Posey | 359 | 30 | Yes | 4 | 8 | 2023 | [5 empty] | 2045 | [6 empty] | 2045 Chip Seal |  | 2027
60244 | SR 68 | From S. Jct SR 165 to 0.51 mi N. N. Jct. SR 165 (Poseyville E. Town Limits) | 6.4252 | 7.9073 | 6 +0.333 | 8 +0.336 | 25739 | C1 | 7 |  | 2 | FLEX | Not on the NHS | Evansville | Poseyville Unit 3 | Posey | 2243 | 179 | N/A | 4 | 8 |  | 2040 | [6 empty] | 2040 Preventive Maintenance | [6 empty] | 2025
60245 | SR 68 | From 0.51 mi N. N. Jct. SR 165 (Poseyville E. Town Limits) to 0.35 mi W. Jct. SR 65 (Cynthiana W. Town Limits) | 7.9073 | 11.4627 | 8 +0.336 | 12 +0.492 | 57706 | C2 | 22 |  | 2 | FLEX | Not on the NHS | Evansville | Boyle Lane Unit 2,Poseyville Unit 3 | Gibson,Posey | 781 | 76 | No | 4 | 8 |  | 2038 | [6 empty] | 2038 Preventive Maintenance | [6 empty] | 2025
60246 | SR 68 | From E. Jct. SR 65 to US 41 | 11.8143 | 20.0079 | 12 +0.843 | 21 +1.010 | 124402 | C2 | 5 | 2026 | 2 | FLEX | Not on the NHS | Evansville,Vincennes | Boyle Lane Unit 2,Oakland City Unit | Gibson,Posey | 1847 | 180 | N/A | 4 | 8 | [6 empty] | 2039 | [6 empty] | 2039 Chip Seal |  | 2025
60247 | SR 68 | From US 41 to I69 | 20.0079 | 24.498 | 21 +1.010 | 26 +0.485 | 71304 | C1 | 5 |  | 2 | FLEX | Not on the NHS | Evansville | Boyle Lane Unit 2,Chandler Unit 4 | Gibson,Warrick | 5232 | 617 | N/A | 4 | 8 | [15 empty] | 2025
60248 | SR 68 | From SR 57 to SR 61 | 24.499 | 33.3291 | 26 +0.486 | 36 +0.289 | 139557 | C2 | 6 | 2026 | 2 | FLEX | Not on the NHS | Evansville | Boyle Lane Unit 2,Chandler Unit 4 | Gibson,Warrick | 2222 | 267 | N/A | 4 | 8 | [6 empty] | 2039 | [6 empty] | 2039 Chip Seal |  | 2025
60249 | SR 68 | From SR 61 to W. Jct. SR 161 | 33.3291 | 44.7452 | 36 +0.289 | 47 +0.614 | 167726 | C2 | 23 | 2025 | 2 | FLEX | Not on the NHS | Evansville,Tell City | Boyle Lane Unit 2,Dale Unit 4 | Spencer,Warrick | 1189 | 142 | No | 4 | 8 |  | 2040 |  |  |  |  | 2031 |  | 2040 Preventive Maintenance |  |  |  |  | 2031 Chip Seal |  | 2025
60252 | SR 69 | From 8.22 mi S. SR 62 (Hovey Lake)to 3.54 mi S. SR 62 (End Asphalt Section/ Begin Concrete Section) | 0 | 4.6815 | 0 +0.000 | 4 +0.690 | 62468 | C2 | 67 | 2026 | 2 | FLEX | Not on the NHS | Evansville | Poseyville Unit 3 | Posey | 258 | 34 | Yes | 4 | 8 | [6 empty] | 2034 | [6 empty] | 2034 Chip Seal |  | 2025
60253 | SR 69 | From 3.54 mi S. SR 62 (End Asphalt Section/ Begin Concrete Section) to W. Jct. SR 62 | 4.6815 | 8.2166 | 4 +0.690 | 8 +0.240 | 95629 | C2 | 12 |  | 2 | RIGID | Not on the NHS | Evansville | Poseyville Unit 3 | Posey | 1673 | 201 | Yes | 4 | 8 | [15 empty] | 2025
60254 | SR 69 | From E. Jct. SR 62 to 3.90 N E. Jct. SR 62 (Concrete Section) | 8.2176 | 12.1238 | 8 +0.241 | 17 +0.383 | 108339 | C1 | 9 |  | 2 | RIGID | Is on the NHS | Evansville | Poseyville Unit 3 | Posey | 2228 | 574 | N/A | 4 | 8 | [15 empty] | 2025
60255 | SR 69 | From 3.90 N E. Jct. SR 62 (Concrete Section/ Begin Asphalt) to 0.5 miles N of SR-269 | 12.1238 | 21.2366 | 17 +0.383 | 26 +0.549 | 252974 | C1 | 3 |  | 2 | FLEX | Is on the NHS | Evansville | Poseyville Unit 3 | Posey | 3255 | 953 | N/A | 4 | 8 | [15 empty] | 2025
60256 | SR 69 | From to 0.5 miles N of SR-269 to Jct. SR 66 | 21.2366 | 24.4683 | 26 +0.549 | 29 +0.841 | 98812 | C1 | 14 |  | 2 | FLEX | Is on the NHS | Evansville | Poseyville Unit 3 | Posey | 2830 | 1010 | N/A | 4 | 8 | [15 empty] | 2025
60257 | SR 69 | From Jct. SR 66 to I64 | 24.4683 | 29.8651 | 29 +0.841 | 35 +0.089 | 150566 | C1 | 14 |  | 2 | FLEX | Is on the NHS | Evansville | Poseyville Unit 3 | Gibson,Posey | 3291 | 676 | N/A | 4 | 8 | [7 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60258 | SR 70 | From US 231to W. Jct. SR 66 | 0 | 9.1156 | 1 -1.077 | 9 +0.088 | 152633 | C2 | 5 | 2028 | 2 | FLEX | Not on the NHS | Tell City | Chrisney Unit 5,Derby Unit 2 | Spencer,Warrick | 1534 | 200 | No | 4 | 8 | [6 empty] | 2041 | [6 empty] | 2041 Chip Seal |  | 2025
60259 | SR 70 | From SR 37 to E. Jct. SR 66 (Derby) | 9.1166 | 15.2712 | 9 +0.089 | 15 +0.200 | 76180 | C2 | 22 | 2031 | 2 | FLEX | Not on the NHS | Tell City | Derby Unit 2 | Perry | 555 | 54 | Yes | 4 | 8 |  | 2036 | [6 empty] | 2036 Preventive Maintenance | [6 empty] | 2025
60260 | SR 237 | From SR 62/SR 66 to 1.68 mi S. SR 37/ SR 64 (S. Town Limits of English) | 5.3708 | 13.6356 | 5 +0.341 | 36 +0.831 | 158947 | C2 | 18 | 2030 | 2 | FLEX | Not on the NHS | Tell City | Birdseye Unit 3,Derby Unit 2 | Crawford,Perry | 699 | 76 | Yes | 4 | 8 | [6 empty] | 2037 | [6 empty] | 2037 Chip Seal |  | 2025
60261 | I-69 | From 0.68 mi W. of US 41 to US 41 | 0 | 0.68251 | 0 -0.647 | 0 +0.036 | 32177 | A2 | 5 | 2035 | 4 | RIGID | Is on the NHS | Evansville | Evansville Unit 1 | Vanderburgh | 38467 | 5288 | N/A | 2 | 4 |  | 2035 | [6 empty] | 2035 Preventive Maintenance | [6 empty] | 2025
60262 | SR 157 | From N. Jct. US231/SR 67 to 0.61 mi N. US 231 (Worthington N. Limits) | 9.368 | 9.9743 | 9 +0.513 | 10 +0.120 | 12161 | C1 | 55 | 2026 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Greene | 1144 | 137 | N/A | 4 | 8 | [15 empty] | 2025
60263 | SR 57 | From S. Jct. of I 69 (end of Asphalt) to S. Jct. of I69 (Fly Over Ramp over I69) | 7.7505 | 8.5552 | 7 +0.717 | 8 +0.551 | 19034 | C2 | 37 |  | 2 | RIGID | Is on the NHS | Evansville | Boyle Lane Unit 2,Chandler Unit 4 | Vanderburgh,Warrick | 3464 | 490 | N/A | 4 | 8 |  | 2038 | 2039 | [5 empty] | 2038 Rehab | 2039 Rehab | [5 empty] | 2025
60264 | SR 61 | From N. Jct. SR 56 / SR 57 to 1.10 miles N of Jct with SR 56/SR 57 | 41.2213 | 42.3256 | 40 +0.327 | 45 +0.978 | 20587 | C1 | 1 |  | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Knox,Pike | 3341 | 441 | N/A | 4 | 8 | 2022 | [14 empty] | 2026
60265 | OLD SR 66 | From ILL/IN State line to 0.10 mi West SR 69 (New Harmony) | 0 | 1.0896 | 1 -0.920 | 1 +0.170 | 23377 | C1 | 13 | 2025 | 2 | FLEX | Not on the NHS | Evansville | Poseyville Unit 3 | Posey | 1000 | 23 | N/A | 4 | 8 | [15 empty] | 2025
60266 | SR 68 | From W Jct SR 161 to E Jct SR 161 | 44.7452 | 48.2154 | 47 +0.614 | 51 +0.136 | 55403 | C2 | 0 | 2025 | 2 | FLEX | Not on the NHS | Tell City | Chrisney Unit 5,Dale Unit 4 | Spencer,Warrick | 798 | 95 | Yes | 4 | 8 | 2023 | 2043 |  |  |  |  | 2038 |  | 2043 Preventive Maintenance |  |  |  |  | 2038 Chip Seal |  | 2027
60267 | OLD US 231 | From SR 70 to 1.24 mi N. SR 70 (Town limits Chrisney) | 0 | 1.2422 | 20 -0.466 | 20 +0.776 | 18080 | C1 | 2 |  | 2 | FLEX | Not on the NHS | Tell City | Chrisney Unit 5 | Spencer,Warrick | 1544 | 186 | N/A | 4 | 8 | 2021 | [14 empty] | 2025
60268 | SR 57 | From 0.66 mi S. of W. Jct SR 56 (Petersburg South City Limits) to W. Jct. SR 56 | 32.1651 | 32.8282 | 35 +0.113 | 35 +0.776 | 13440 | C1 | 0 |  | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Knox,Pike | 4989 | 1095 | N/A | 4 | 8 | 2023 | [14 empty] | 2027
60269 | SR 162 | From 0.10 mi N. SR 264 N. Ferdinand Town Limits) To SR 64 | 15.9948 | 20.5857 | 15 +1.041 | 20 +0.628 | 122377 | C1 | 3 |  | 2 | FLEX | Not on the NHS | Paoli,Tell City | Dale Unit 4,Jasper Unit 4 | Dubois | 8643 | 666 | N/A | 3 | 6 | [7 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60270 | SR 54 | From 2.02 mi E. Of E. Jct SR 59 ( Linton East City Limits) to SR 67 | 17.4491 | 21.3703 | 27 +0.390 | 31 +0.357 | 78002 | C1 | 6 |  | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Greene | 8080 | 1179 | N/A | 3 | 6 | [15 empty] | 2025
60271 | SR 157 | From 1.10 N. US 231/SR54 to North End of White River Bridge | 1.097 | 8.2961 | 1 +0.093 | 8 +0.472 | 136462 | C2 | 19 | 2026 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Greene | 1705 | 204 | Yes | 4 | 8 | [6 empty] | 2026 | [6 empty] | 2026 Chip Seal |  | 2025
60273 | US 41 | From 0.58 mi S of E intersection with US 50 (Kelso Creek bridge) to the W intersection with US 50 | 54.7367 | 56.4907 | 54 +0.594 | 56 +0.155 | 82909 | B1 | 16 |  | 4 | FLEX | Is on the NHS | Vincennes | Vincennes Unit 2 | Knox | 18139 | 2782 | N/A | 3 | 6 | 2024 | [14 empty] | 2027
60274 | SR 62 | From 2.72 W. of S. Jct US 41 (Wabash Ave.) to US 41 | 25.5086 | 28.2378 | 24 +0.781 | 27 +0.496 | 166653 | B1 | 5 |  | 6 | RIGID | Is on the NHS | Evansville | Evansville Unit 1 | Vanderburgh | 41404 | 2306 | N/A | 2 | 4 | [15 empty] | 2025
60275 | SR 57 | From N. Jct. SR 56 / SR 61to 0.95 mi N. SR 356 (N. Petersburg City Limits) | 32.8292 | 33.9246 | 35 +0.777 | 37 +0.403 | 24615 | C1 | 0 |  | 2 | FLEX | Not on the NHS | Vincennes | Vincennes Unit 2 | Knox,Pike | 5249 | 1152 | N/A | 4 | 8 | 2023 | [14 empty] | 2027
60276 | I-69 | From 3.12 mi S. SR 58 to 4.88 mi N. US 231 (Concrete) | 73.4996 | 92.7181 | 72 +0.818 | 92 +0.048 | 618440 | A2 | 11 | 2034 | 4 | RIGID | Is on the NHS | Linton,Vincennes | Crane Unit,Linton,Loogootee Unit | Daviess,Greene,Martin | 8734 | 2166 | N/A | 4 | 8 |  | 2034 | 2044 |  |  |  |  | 2027 | 2034 Preventive Maintenance | 2044 Preventive Maintenance |  |  |  |  | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60277 | SR 58 | From SR 358 to 3.7 mi E. I69 (W. Odon Limits) | 38.27 | 42.9373 | 38 +0.801 | 43 +0.468 | 76910 | C2 | 10 | 2025 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Daviess | 4178 | 500 | Yes | 4 | 8 | 2025 | [5 empty] | 2025 | [6 empty] | 2025 Chip Seal |  | 2029
60279 | SR 59 | From 1.05 mi S. SR 54 (Co. Rd 25 S) to S. Jct. SR 54 | 10.7999 | 11.8459 | 10 +0.760 | 12 +0.017 | 19339 | C1 | 4 |  | 2 | FLEX | Not on the NHS | Linton | Linton | Greene | 3702 | 444 | N/A | 4 | 8 | [15 empty] | 2025
60280 | SR 261 | From 3.01 mi N. SR 66 to SR 62 | 2.984 | 7.7538 | 3 +0.060 | 7 +0.763 | 93562 | C2 | 4 | 2028 | 2 | FLEX | Not on the NHS | Evansville | Boyle Lane Unit 2,Chandler Unit 4 | Warrick | 3861 | 230 | N/A | 4 | 8 | [6 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2025
60281 | US 50 | From E. Jct. of US 41 to 4.47 mi East of E. Jct. US 41 | 1.8632 | 6.61 | 1 +0.845 | 7 +0.462 | 217251 | B2 | 16 | 2025 | 4 | FLEX | Is on the NHS | Vincennes | Vincennes Unit 2 | Knox | 7582 | 713 | N/A | 4 | 8 | [7 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60282 | OLD US 41 | From 0.17 mi S. US 41/US 50 to US 41/US 50 (Vincennes 6th S.) | 0 | 0.22817 | 0 -0.014 | 0 +0.214 | 31546 | B2 | 13 | 2028 | 4 | FLEX | Not on the NHS | Vincennes | Vincennes Unit 2 | Knox | 6221 | 509 | N/A | 4 | 8 | [15 empty] | 2025
60283 | SR 58 | From 3.7 mi E. I69 (W. Odon Limits) to 2.80 mi W. US 231 (E. Odon Town Limits) | 42.9373 | 44.4514 | 43 +0.468 | 44 +0.989 | 28246 | C1 | 10 |  | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Daviess | 4679 | 560 | N/A | 4 | 8 | [15 empty] | 2025
60284 | OLD SR 70 | From Old US 231 to E. City Limits of Chrisney | 0 | 0.71977 | 0 -0.033 | 0 +0.687 | 4673 | C2 | 2 |  | 2 | FLEX | Not on the NHS | Tell City | Chrisney Unit 5 | Spencer,Warrick | 1027 | 139 | N/A | 4 | 8 | 2021 | [14 empty] | 2025
60285 | SR 64 | From 3.10 mi W. of I-69 (300' W. RR Track in Francisco) to 2.45 mi W. I-69 (ECL of Francisco) | 18.3389 | 18.9707 | 18 +0.366 | 18 +0.998 | 13742 | C1 | 2 |  | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit | Gibson,Pike | 7106 | 674 | N/A | 3 | 6 | 2021 | [6 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2024 | 2026 | 2026 RPM Replacement
60286 | SR 64 | From 2.45 mi W. I-69 (ECL of Francisco) to SR 57 | 18.9707 | 22.9059 | 18 +0.998 | 22 +0.656 | 88592 | C1 | 1 |  | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit | Gibson,Pike | 6609 | 538 | N/A | 3 | 6 | 2022 | [6 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60287 | SR 57 | From Old US 50 to N. City Limits of Washington | 46.0912 | 47.3132 | 49 +0.550 | 50 +0.746 | 23130 | C1 | 13 | 2029 | 2 | FLEX | Not on the NHS | Vincennes | Loogootee Unit,Oakland City Unit | Daviess,Knox | 5982 | 1313 | N/A | 4 | 8 | 2021 | [14 empty] | 2025
60288 | SR 64 | From 1.52 mi W. of US 231 (WCL Huntingburg) to 1.02 mi E. US 231 (ECL Huntingburg) | 44.8401 | 47.375 | 44 +0.724 | 47 +0.283 | 51716 | C1 | 18 | 2026 | 2 | FLEX | Not on the NHS | Paoli,Tell City | Dale Unit 4,Jasper Unit 4 | Dubois | 4655 | 454 | N/A | 4 | 8 | [15 empty] | 2025
60289 | SR 67 | From 0.51 mile S. SR 159 to 0.70 mi N. SR 159 (Bicknell City Limits) | 10.5122 | 11.7117 | 10 +0.539 | 11 +0.734 | 25307 | C1 | 16 |  | 2 | FLEX | Not on the NHS | Linton,Vincennes | Sullivan Unit 3,Vincennes Unit 2 | Knox | 6393 | 932 | N/A | 3 | 6 | [15 empty] | 2025
60290 | US 50 | From 1.79 mi. S. of W. Jct of US 231 to 0.25 mi. E. SR 550 (Loogootee Limits) | 34.0531 | 36.132 | 34 +0.016 | 36 +0.168 | 47202 | C1 | 15 |  | 2 | FLEX | Is on the NHS | Linton,Vincennes | Crane Unit,Loogootee Unit | Daviess,Martin | 7789 | 1320 | N/A | 3 | 6 | 2024 | [14 empty] | 2027
60291 | SR 168 | From SR 65 to 0.73 mi E. SR 65 (Owensville E. City Limits) | 0 | 0.73386 | 0 +0.000 | 0 +0.733 | 13738 | C1 | 20 | 2025 | 2 | FLEX | Not on the NHS | Evansville,Vincennes | Boyle Lane Unit 2,Oakland City Unit,Poseyville Unit 3 | Gibson | 2834 | 337 | N/A | 4 | 8 | [15 empty] | 2025
60292 | SR 165 | From 0.47 mi . W. SR 65 (W city Limits - Owensville) to SR 65 (Owensville) | 15.7313 | 16.1983 | 16 +0.731 | 17 +0.137 | 8320 | C1 | 28 | 2025 | 2 | FLEX | Not on the NHS | Evansville,Vincennes | Boyle Lane Unit 2,Oakland City Unit,Poseyville Unit 3 | Gibson | 2785 | 327 | N/A | 4 | 8 | [15 empty] | 2025
60293 | SR 61 | From 0.14 mi S of I-64 to 0.88 mi N of SR 68 (N. Town Limits Lynnville) | 20.6962 | 21.9871 | 19 +0.696 | 20 +1.001 | 24383 | C1 | 19 | 2024 | 2 | FLEX | Not on the NHS | Evansville,Tell City,Vincennes | Boyle Lane Unit 2,Chandler Unit 4,Dale Unit 4,Oakland City Unit | Warrick | 2501 | 184 | N/A | 4 | 8 | [15 empty] | 2025
60294 | SR 545 | From SR 66 to 0.30 mi N. SR 66 (Troy) | 0 | 0.30128 | 0 +0.000 | 0 +0.300 | 6406 | C1 | 24 | 2024 | 2 | FLEX | Not on the NHS | Tell City | Derby Unit 2 | Perry,Spencer | 3255 | 507 | N/A | 4 | 8 | [15 empty] | 2025
60295 | SR 66 | From 0.18 W. SR 545 to 0.10 mi E. SR 545 | 70.6406 | 70.9198 | 73 +0.901 | 74 +0.177 | 6761 | C1 | 15 | 2024 | 2 | FLEX | Not on the NHS | Tell City | Derby Unit 2 | Perry,Spencer | 6447 | 799 | N/A | 3 | 6 | [15 empty] | 2025
60296 | SR 66 | From 0.10 mi E. SR 545 to S. Jct SR 37 | 70.9198 | 73.9123 | 74 +0.177 | 77 +0.215 | 62191 | C1 | 15 | 2028 | 2 | FLEX | Not on the NHS | Tell City | Derby Unit 2 | Perry,Spencer | 8303 | 859 | N/A | 3 | 6 | [15 empty] | 2025
60297 | SR 48 | From 1.50 miles W of SR 59 (0.2 mi W. Jasonville W.Town Limits) to 0.05 mile E of SR 59 (0.05 mi E. Jasonville E. Town Limits) | 18.025 | 19.579 | 17 +1.003 | 19 +0.552 | 36340 | C1 | 6 |  | 2 | FLEX | Not on the NHS | Linton | Linton | Greene | 5227 | 620 | N/A | 4 | 8 | [15 empty] | 2025
60298 | SR 54 | From US 231/SR 157 Jct to 0.52 mi. East US 231/SR157 Jct. (Bloomfield Town Limits) | 23.8791 | 24.4003 | 33 +0.814 | 38 +0.358 | 12979 | C1 | 3 |  | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Greene | 5093 | 742 | N/A | 4 | 8 | [15 empty] | 2025
60299 | SR 157 | From North End of White River Bridge to S. Jct US 231 ( Worthington) | 8.2961 | 9.367 | 8 +0.472 | 9 +0.512 | 21003 | C1 | 19 | 2026 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Greene | 1115 | 134 | N/A | 4 | 8 | [15 empty] | 2025
60300 | US 231 | From KY / IN State line to 1.1 mi. N. SR 66 | 0 | 1.1168 | 12 -0.252 | 13 +0.694 | 53383 | B2 | 1 |  | 4 | RIGID | Is on the NHS | Tell City | Chrisney Unit 5 | Spencer,Warrick | 6542 | 2126 | N/A | 4 | 8 | [7 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60301 | US 231 | From 1.1 mi N. SR 66 to SR 70 | 1.1168 | 7.122 | 13 +0.694 | 19 +0.689 | 159327 | B2 | 15 |  | 4 | FLEX | Is on the NHS | Tell City | Chrisney Unit 5 | Spencer,Warrick | 5904 | 2112 | N/A | 4 | 8 |  | 2033 | [5 empty] | 2027 | 2033 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60302 | SR 164 | From US 231 to 0.51 mi. E. US 231 | 0 | 0.51148 | 0 +0.000 | 0 +0.510 | 12680 | B1 | 0 |  | 2 | FLEX | Not on the NHS | Paoli,Vincennes | Jasper Unit 4,Loogootee Unit | Dubois | 11947 | 671 | N/A | 3 | 6 | 2023 | 2036 | [6 empty] | 2036 Preventive Maintenance | [6 empty] | 2026
60303 | SR 48 | From 4.1 mi W. SR 159 (Hymera W. Town Limits) to 3.08 mi W. SR 159 (Hymera E. Town Limits) | 11.8008 | 12.8247 | 11 +0.764 | 12 +0.787 | 20573 | C1 | 20 | 2027 | 2 | FLEX | Not on the NHS | Linton | Linton,Sullivan Unit 3 | Sullivan | 3185 | 377 | N/A | 4 | 8 | [15 empty] | 2025
60304 | SR 48 | From 3.08 mi W. SR 159 (Hymera E. Town Limits) to 1.50 miles W of SR 59 (0.2 mi W. Jasonville W.Town Limits) | 12.8247 | 18.025 | 12 +0.787 | 17 +1.003 | 95183 | C2 | 20 | 2027 | 2 | FLEX | Not on the NHS | Linton | Linton,Sullivan Unit 3 | Clay,Greene,Sullivan | 3292 | 390 | Yes | 4 | 8 | 2024 | [5 empty] | 2027 | [6 empty] | 2027 Chip Seal |  | 2028 | 2027 | 2027 Chip Seal
60305 | SR 65 | From 0.26 mi S. SR 168 (S. Limits Owensville) to SR 165 | 19.7782 | 20.2411 | 19 +0.848 | 20 +0.273 | 8307 | C1 | 21 | 2025 | 2 | FLEX | Not on the NHS | Evansville,Vincennes | Boyle Lane Unit 2,Oakland City Unit,Poseyville Unit 3 | Gibson | 1915 | 212 | N/A | 4 | 8 | [15 empty] | 2025
60306 | SR 61 | From 0.83 mi. S. of S. Jct. SR 241 to N. Jct. of SR 241 (Monroe City) | 51.0155 | 52.3351 | 54 +0.640 | 55 +0.971 | 23462 | C1 | 8 |  | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Knox | 2527 | 334 | N/A | 4 | 8 | [15 empty] | 2025
60307 | SR 237 | From 1.68 mi S. SR 37/ SR 64 (S. Town Limits of English) to SR 37/ SR 64 | 13.6356 | 15.3161 | 36 +0.831 | 38 +0.479 | 27464 | C2 | 18 | 2025 | 2 | FLEX | Not on the NHS | Paoli,Tell City | Birdseye Unit 3,Paoli Unit 1 | Crawford | 978 | 117 | N/A | 4 | 8 | [6 empty] | 2039 | [6 empty] | 2039 Chip Seal |  | 2025
60308 | SR 67 | From 1.03 mi. N. SR 358 (Edwardsport S. Town Limits) to 1.63 mi N. SR 358 (Edwardsport N. Town Limits) | 14.9301 | 15.5305 | 14 +0.943 | 15 +0.556 | 10477 | C2 | 16 |  | 2 | FLEX | Not on the NHS | Linton,Vincennes | Linton,Vincennes Unit 2 | Daviess,Knox | 2885 | 420 | N/A | 4 | 8 | [6 empty] | 2030 | [6 empty] | 2030 Chip Seal |  | 2025
60309 | SR 67 | From 4.02 mi. S. SR 54 (Lyons S. Town Limits) to 3.02 mi. S. SR 54 (Lyons N. Town Limits) | 29.246 | 30.2442 | 30 +0.540 | 31 +0.558 | 22764 | C1 | 14 |  | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Greene | 2049 | 299 | N/A | 4 | 8 | [7 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60310 | US 41 | From 0.10 mi S. I69 to SR 62/SR66 (Lloyd Expressway) | 1.0578 | 3.7629 | 1 +0.112 | 3 +0.825 | 124900 | B1 | 6 |  | 4 | FLEX | Is on the NHS | Evansville | Evansville Unit 1 | Vanderburgh | 31107 | 3840 | N/A | 2 | 4 | [15 empty] | 2025
60311 | US 41 | From SR 62/SR66 (Lloyd Expwy) to 0.74 mi N of SR 66 (Diamond Ave) | 3.7629 | 6.0642 | 3 +0.825 | 6 +0.136 | 123957 | B1 | 6 | 2023 | 6 | FLEX | Is on the NHS | Evansville | Evansville Unit 1 | Vanderburgh | 32484 | 3879 | N/A | 2 | 4 | 2023 | [14 empty] | 2025
60312 | US 41 | From 0.74 mi N of SR 66 (Diamond Ave) to SR 57 | 6.0642 | 8.9041 | 6 +0.136 | 8 +0.646 | 150120 | B1 | 6 |  | 4 | FLEX | Is on the NHS | Evansville | Boyle Lane Unit 2,Evansville Unit 1 | Vanderburgh | 34475 | 3945 | N/A | 2 | 4 | 2025 | [14 empty] | 2027
60313 | SR 62 | From 5.60 mi W of S Jct US 41 (Boehne Camp Rd) to 2.72 mi W of S Jct US 41 (Wabash Ave) | 22.6305 | 25.5086 | 21 +0.899 | 24 +0.781 | 144643 | B1 | 4 | 2024 | 4 | FLEX | Is on the NHS | Evansville | Evansville Unit 1 | Vanderburgh | 39653 | 2010 | N/A | 2 | 4 |  | 2042 | [6 empty] | 2042 Preventive Maintenance | [6 empty] | 2025
60315 | SR 245 | From 3.51 mi S E. Jct. SR 162 (Crooked Creek Bridge) to E. Jct. SR 162 | 4.9249 | 8.1373 | 5 +0.036 | 8 +0.429 | 33270 | C2 | 5 | 2027 | 2 | FLEX | Not on the NHS | Tell City | Chrisney Unit 5,Dale Unit 4 | Spencer | 2894 | 212 | Yes | 4 | 8 | [6 empty] | 2041 | [6 empty] | 2041 Chip Seal |  | 2025
60316 | SR 257 | From 0.10 mi N. US 50 to Old US 50 | 30.4525 | 31.6586 | 30 +0.141 | 31 +0.352 | 22646 | C2 | 4 | 2029 | 2 | FLEX | Not on the NHS | Vincennes | Loogootee Unit,Oakland City Unit,Vincennes Unit 2 | Daviess,Knox | 3481 | 538 | Yes | 4 | 8 | [6 empty] | 2043 | [6 empty] | 2043 Chip Seal |  | 2025
60317 | SR 37 | From 1.06 mi. S. SR 54 to Lawrence/Monroe Co, Line (District Line) | 76.2524 | 83.2763 | 81 +0.060 | 88 +0.063 | 308473 | B1 | 10 |  | 4 | FLEX | Is on the NHS | Paoli | Bedford Unit 3 | Lawrence | 21086 | 1532 | N/A | 3 | 6 | 2024 | [14 empty] | 2027
60318 | SR 445 | From 0.36 mi W. SR 45 to I69 | 0.9272 | 2.9173 | 0 +0.927 | 2 +0.917 | 50686 | C2 | 9 |  | 2 | RIGID | Not on the NHS | Linton | Crane Unit | Greene,Monroe | 3859 | 467 | Yes | 4 | 8 | [15 empty] | 2025
60319 | SR 65 | From 0.60 mi S. of W. Jct. SR 68 to E. Jct. SR 68 (Cynthiana) | 12.9648 | 14.899 | 13 +0.026 | 14 +0.910 | 31387 | C1 | 21 |  | 2 | FLEX | Not on the NHS | Evansville | Boyle Lane Unit 2,Poseyville Unit 3 | Gibson,Posey | 995 | 111 | N/A | 4 | 8 | 2024 | [14 empty] | 2028
60320 | US 231 | From E. Jct US 50 to 0.97 mi N. US 50 (N. Corporate Limits Loogootee) | 56.4108 | 57.3711 | 68 +0.942 | 70 +0.341 | 17907 | C1 | 10 |  | 2 | FLEX | Is on the NHS | Linton,Vincennes | Crane Unit,Loogootee Unit | Daviess,Martin | 6666 | 720 | N/A | 3 | 6 | [15 empty] | 2025
60321 | US 231 | From SR 67 to 0.77 mile S of S Jct SR-157 (S. Limits of Worthington) | 88.4427 | 90.9414 | 101 +0.494 | 103 +0.938 | 45810 | C2 | 9 | 2027 | 2 | FLEX | Is on the NHS | Linton | Crane Unit,Linton | Greene | 4327 | 579 | N/A | 4 | 8 | [6 empty] | 2041 | [6 empty] | 2041 Chip Seal |  | 2025
60322 | SR 61 | From W. Jct. SR 62 to New Harmony / Shelton Rd (Old SR 61-Boonville) | 9.2745 | 13.4816 | 9 +0.061 | 12 +0.716 | 46455 | C2 | 5 | 2028 | 2 | FLEX | Not on the NHS | Evansville | Boyle Lane Unit 2,Chandler Unit 4 | Warrick | 2124 | 119 | Yes | 4 | 8 | [6 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2025
60323 | SR 257 | From 0.1 mi S. US 50 to 0.10 N. US 50 (Concrete) | 30.2374 | 30.4525 | 29 +0.913 | 30 +0.141 | 4796 | C2 | 8 |  | 2 | RIGID | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Daviess,Knox | 4593 | 710 | Yes | 4 | 8 | [15 empty] | 2025
60324 | SR 337 | 1.03 mi S. SR 37 (Orleans Town Limits) to SR 37 | 23.7667 | 24.7997 | 33 +0.429 | 34 +0.443 | 17971 | C1 | 2 |  | 2 | FLEX | Not on the NHS | Paoli | Paoli Unit 1 | Orange | 2428 | 148 | N/A | 4 | 8 | 2021 | [14 empty] | 2025
60326 | US 150 | From 1.67 mi W Jct SR 37 (Paoli W. Town Limits) to 1.24 mi E. Jct. SR 37 (Paoli E.Town Limits) | 35.4667 | 38.5208 | 132 +0.537 | 135 +0.494 | 63842 | C1 | 6 |  | 2 | FLEX | Not on the NHS | Paoli | Paoli Unit 1 | Orange | 5439 | 628 | N/A | 4 | 8 | [15 empty] | 2025
60327 | SR 56 | From E. Jct. US 150 (Paoli) to 1.24 mi E. Jct. US 150 (Paoli) | 61.4806 | 62.7204 | 68 +0.775 | 79 +0.028 | 21243 | C2 | 18 | 2030 | 2 | FLEX | Not on the NHS | Paoli | Paoli Unit 1 | Orange | 2384 | 348 | Yes | 4 | 8 | [6 empty] | 2037 | [6 empty] | 2037 Chip Seal |  | 2025
60328 | SR 64 | From SR 57 to 0.76 mi E. SR 357 | 22.9059 | 25.0671 | 22 +0.656 | 25 +0.027 | 44438 | C1 | 2 |  | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit | Gibson,Pike | 4819 | 382 | N/A | 4 | 8 | 2021 | [14 empty] | 2025
60330 | I-69 | From 4.88 mi N. US 231 to 2.35 mi S. SR 45 (Asphalt) | 92.7181 | 96.636 | 92 +0.048 | 95 +0.974 | 200231 | A2 | 8 | 2033 | 4 | FLEX | Is on the NHS | Linton | Crane Unit,Linton | Greene | 10582 | 1896 | N/A | 3 | 6 |  | 2033 | [5 empty] | 2027 | 2033 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60331 | I-69 | From 2.35 mi S. SR 45 to SR 445 (Concrete) | 96.636 | 104.4063 | 95 +0.974 | 103 +0.735 | 375332 | A2 | 8 | 2036 | 4 | RIGID | Is on the NHS | Linton,Paoli | Bedford Unit 3,Crane Unit | Greene,Monroe | 11561 | 2307 | N/A | 3 | 6 |  | 2036 | [5 empty] | 2027 | 2036 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60332 | SR 62 | From E. Jct. SR 61 to 0.24 mi east of E. Jct SR 61 | 42.6291 | 42.8747 | 42 +0.923 | 42 +1.169 | 9038 | B2 | 1 |  | 4 | RIGID | Not on the NHS | Evansville | Chandler Unit 4 | Warrick | 20418 | 758 | N/A | 3 | 6 | [15 empty] | 2025
60333 | SR 157 | From 0.61 mi N. US 231 (Worthington N. Limits) to SR 48 | 9.9743 | 12.3485 | 10 +0.120 | 12 +0.509 | 33246 | C2 | 14 | 2030 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Greene | 1268 | 153 | Yes | 4 | 8 | 2024 | [5 empty] | 2033 | [6 empty] | 2033 Chip Seal |  | 2028
60334 | SR 62 | From 0.25 mi E of I-69 to W. Jct of SR 61 | 32.5206 | 42.6281 | 32 +0.813 | 42 +0.922 | 537218 | B2 | 1 |  | 4 | RIGID | Not on the NHS | Evansville | Chandler Unit 4,Evansville Unit 1 | Vanderburgh,Warrick | 14595 | 540 | N/A | 3 | 6 | 2024 | [14 empty] | 2027
60335 | OLD US 50 | From US 50 to 0.55 miles E of US 50 (Sand Pit Road) Bedford | 0 | 0.5454 |  |  | 27315 | B2 | 43 | 2026 | 3 | FLEX | Not on the NHS | Paoli | Bedford Unit 3 | Lawrence | 8787 | 713 | N/A | 4 | 8 | [15 empty] | 2025
60337 | SR 58 | From 2.80 mi W. US 231 (E. Odon Town Limits) to US 231 | 44.4514 | 47.2527 | 44 +0.989 | 47 +0.780 | 44506 | C2 | 10 | 2025 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Daviess | 2871 | 241 | Yes | 4 | 8 | 2025 | [5 empty] | 2025 | [6 empty] | 2025 Chip Seal |  | 2029
60338 | SR 154 | From SR 63 TO US 41 | 5.6768 | 13.1959 | 5 +0.728 | 13 +0.182 | 135169 | C2 | 18 | 2025 | 2 | FLEX | Not on the NHS | Linton | Sullivan Unit 3 | Sullivan | 2300 | 335 | No | 4 | 8 | [15 empty] | 2025
60339 | I-69 | From 2.30 E. of US 41 to Jct. SR 66 | 2.9597 | 7.8557 | 2 +0.566 | 7 +0.472 | 237932 | A2 | 5 | 2035 | 4 | RIGID | Is on the NHS | Evansville | Chandler Unit 4,Evansville Unit 1 | Vanderburgh,Warrick | 23778 | 2563 | N/A | 3 | 6 |  | 2035 | [5 empty] | 2027 | 2035 Preventive Maintenance | [5 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60340 | US 231 | From 1.16 mi S of E Jct SR-54/SR-157 (Richland Creek) to 0.67 mi W of Jct SR-54 / SR 157 (Bloomfiled W. CL) | 80 | 81.7939 | 92 +1.030 | 94 +0.822 | 37372 | C1 | 6 |  | 2 | FLEX | Is on the NHS | Linton | Crane Unit,Linton | Greene | 7494 | 1001 | N/A | 3 | 6 | [15 empty] | 2025
60342 | US 50 | From W. White River Bridge to 0.40 mi. E. I69 | 16.1865 | 24.1172 | 17 +0.168 | 24 +0.411 | 362581 | B2 | 8 |  | 4 | RIGID | Is on the NHS | Vincennes | Loogootee Unit,Oakland City Unit,Vincennes Unit 2 | Daviess,Knox | 7558 | 1442 | N/A | 4 | 8 | [7 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60343 | SR 37 | 1.34 mi S. SR 337 (S. Orleans Town Limits) to 1.08 mi N. SR 337 (N. Orleans Town Limits) | 60.8409 | 63.2628 | 61 +0.515 | 63 +0.940 | 51595 | C1 | 10 |  | 2 | FLEX | Not on the NHS | Paoli | Bedford Unit 3,Paoli Unit 1 | Orange | 8130 | 248 | N/A | 3 | 6 | [15 empty] | 2025
60344 | SR 37 | From 1.08 mi N. SR 337 (N. Orleans Town Limits) to 0.62 mi S of South Jct SR-60 (Concrete Pavement Starts) | 63.2628 | 66.2673 | 63 +0.940 | 66 +0.940 | 82328 | C1 | 9 |  | 2 | FLEX | Not on the NHS | Paoli | Bedford Unit 3,Paoli Unit 1 | Lawrence,Orange | 8695 | 265 | N/A | 3 | 6 | [15 empty] | 2025
60345 | SR 54 | 0.50 mi W. SR 159 (W. Dugger Town Limits) to 0.51 mi E. SR 159 (E. Dugger Town Limits) | 7.9612 | 8.9758 | 17 +0.884 | 18 +0.836 | 20716 | C1 | 9 |  | 2 | FLEX | Not on the NHS | Linton | Linton,Sullivan Unit 3 | Sullivan | 4891 | 713 | N/A | 4 | 8 | 2025 | [14 empty] | 2029
60346 | SR 56 | From US 41 to 2.20 mi E. US 41 (Hazleton Town Limits) | 0 | 2.6018 | 0 +0.000 | 2 +0.592 | 39012 | C1 | 21 | 2027 | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Gibson,Knox | 561 | 48 | N/A | 4 | 8 | 2025 | [5 empty] | 2027 | [6 empty] | 2027 Chip Seal |  | 2029 | 2027 | 2027 Chip Seal
60347 | SR 57 | From 0.28 mi S. of S. Jct. SR 58 (S. Elnora Town Limits) to 0.55 mi N. of N. Jct SR 58 (N Elnora Town Limits) | 63.1262 | 64.1072 | 66 +0.530 | 67 +0.480 | 20444 | C1 | 2 |  | 2 | FLEX | Not on the NHS | Linton | Crane Unit | Daviess,Knox | 1740 | 382 | N/A | 4 | 8 | 2021 | [14 empty] | 2025
60348 | SR 58 | From SR 63 to 0.79 mi E. SR 63 (Merom E. Town Limits) | 0 | 0.79233 | 0 -0.009 | 0 +0.783 | 13978 | C2 | 25 | 2028 | 2 | FLEX | Not on the NHS | Linton | Sullivan Unit 3 | Sullivan | 421 | 53 | Yes | 4 | 8 | [6 empty] | 2028 | [6 empty] | 2028 Chip Seal |  | 2025
60349 | SR 63 | From SR 154 to SR 48 | 4.3361 | 10.666 | 4 +0.338 | 10 +0.648 | 97713 | C2 | 15 | 2028 | 2 | FLEX | Not on the NHS | Linton | Sullivan Unit 3 | Sullivan | 1350 | 162 | Yes | 4 | 8 | [6 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2025
60350 | SR 68 | From 0.35 mi W. Jct. SR 65 (Cynthiana W. Town Limits) to SR 65 | 11.4627 | 11.8133 | 12 +0.492 | 12 +0.842 | 5815 | C1 | 22 |  | 2 | FLEX | Not on the NHS | Evansville | Poseyville Unit 3 | Gibson,Posey | 707 | 69 | N/A | 4 | 8 | [15 empty] | 2025
60351 | SR 145 | From E. Jct. SR 64 to SR 164 | 24.8287 | 27.2987 | 24 +0.770 | 31 +0.668 | 73588 | C2 | 16 | 2026 | 2 | FLEX | Not on the NHS | Paoli,Tell City | Birdseye Unit 3,Paoli Unit 1 | Crawford | 2769 | 461 | N/A | 4 | 8 | [6 empty] | 2039 | [6 empty] | 2039 Chip Seal |  | 2025
60352 | SR 159 | From 0.32 mi. S. SR 54 (S. Dugger Town Limits) to SR 54 | 13.8677 | 14.1867 | 13 +0.729 | 14 +0.068 | 5621 | C1 | 20 | 2025 | 2 | FLEX | Not on the NHS | Linton | Linton,Sullivan Unit 3 | Sullivan | 1559 | 186 | N/A | 4 | 8 | [15 empty] | 2025
60353 | SR 356 | From SR 57 to 0.85 mi E. SR 57 (E. Petersburg City Limits) | 0 | 0.85149 | 0 +0.000 | 0 +0.850 | 14526 | C1 | 25 |  | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Knox,Pike | 1284 | 124 | N/A | 4 | 8 | [7 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60354 | SR 450 | From Martin/Lawrence Co. Line to N. Jct. US 50 / SR 37 | 13.5626 | 24.9887 | 13 +0.548 | 24 +0.956 | 166733 | C2 | 2 | 2029 | 2 | FLEX | Not on the NHS | Linton,Paoli | Bedford Unit 3,Crane Unit | Lawrence | 1290 | 36 | Yes | 4 | 8 | 2021 | [5 empty] | 2035 | 2026 | [5 empty] | 2035 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60355 | SR 145 | From 0.69 mi S. W. Jct SR 64 (S. Birdseye town Limits) to W. Jct. SR 64 | 24.1409 | 24.8277 | 24 +0.082 | 24 +0.769 | 11244 | C1 | 19 |  | 2 | FLEX | Not on the NHS | Tell City | Birdseye Unit 3 | Dubois | 817 | 26 | N/A | 4 | 8 | [7 empty] | 2027 | [6 empty] | 2027 RPM Replacement | 2025 | 2027 | 2027 RPM Replacement
60356 | SR 58 | From 0.34 mi. W. SR 159 to 0.90 mi. E. SR 159 (Freelandville Limits) | 22.9658 | 24.2033 | 23 +0.211 | 24 +0.475 | 20594 | C1 | 3 |  | 2 | FLEX | Not on the NHS | Linton | Linton,Sullivan Unit 3 | Knox | 1161 | 141 | N/A | 4 | 8 | [7 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60357 | SR 61 | From 3.3 mi N. SR 64 (S. Winslow Town Limits) to 3.75 mi S. SR 56 (N. Winslow Town Limits) | 36.5175 | 37.3491 | 35 +0.660 | 36 +0.484 | 21666 | C1 | 7 |  | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Pike | 2367 | 312 | N/A | 4 | 8 | [7 empty] | 2026 | [6 empty] | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60358 | SR 61 | From 3.75 mi S. SR 56 (N. Winslow Town Limits) to S. Jct. SR 56 | 37.3491 | 41.2203 | 36 +0.484 | 40 +0.326 | 66717 | C2 | 7 | 2025 | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Knox,Pike | 3020 | 275 | Yes | 4 | 8 | [6 empty] | 2039 | 2026 | [5 empty] | 2039 Chip Seal | 2026 RPM Replacement | 2025 | 2026 | 2026 RPM Replacement
60359 | SR 159 | From 0.33 mi S. SR 58 to SR 58 (Freelandville) | 5.7544 | 6.0837 | 5 +0.763 | 5 +1.093 | 5936 | C1 | 18 |  | 2 | FLEX | Not on the NHS | Linton | Linton,Sullivan Unit 3 | Knox | 1300 | 75 | N/A | 4 | 8 | [15 empty] | 2025
60360 | SR 57 | From 0.41 mi S. SR 358 (Plainville S. Town Limits) to 0.44 mi N. SR 358 (Plainville N. Town LImits) | 56.8201 | 57.6732 | 60 +0.252 | 61 +0.078 | 21152 | C1 | 2 |  | 2 | FLEX | Not on the NHS | Vincennes | Loogootee Unit,Vincennes Unit 2 | Daviess,Knox | 2481 | 544 | N/A | 4 | 8 | 2021 | [14 empty] | 2025
60361 | SR 57 | From 0.44 mi N. SR 358 (Plainville N. Town Limits) to 0.28 mi S. of S. Jct. SR 58 (S. Elnora Town Limits) | 57.6732 | 63.1262 | 61 +0.078 | 66 +0.530 | 108413 | C2 | 2 | 2028 | 2 | FLEX | Not on the NHS | Linton,Vincennes | Crane Unit,Loogootee Unit,Vincennes Unit 2 | Daviess,Knox | 1619 | 355 | N/A | 4 | 8 | 2021 | [5 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2025
60362 | SR 550 | From 0.81 mi W. SR 67 ( Bruceville W. Town Limits) to SR 67 | 3.5282 | 4.3437 | 3 +0.536 | 4 +0.351 | 13851 | C2 | 17 | 2031 | 2 | FLEX | Not on the NHS | Linton,Vincennes | Sullivan Unit 3,Vincennes Unit 2 | Knox | 1964 | 235 | Yes | 4 | 8 | 2024 | [14 empty] | 2028
60363 | SR 550 | From US 50 to 0.47 mi E. US 50 ( Loogootee E. Town Limits) | 13.8732 | 14.3409 | 13 +0.892 | 14 +0.089 | 6583 | C2 | 29 |  | 2 | FLEX | Not on the NHS | Linton,Vincennes | Crane Unit,Loogootee Unit | Martin | 1455 | 50 | N/A | 4 | 8 | 2024 | [14 empty] | 2028
60364 | SR 37 | From 1.24 mi S. Jct US 150 (S. Paoli Town Limits) to S. Jct. US 150 | 53.3453 | 54.5896 | 53 +0.901 | 55 +0.113 | 26798 | C1 | 4 |  | 2 | FLEX | Not on the NHS | Paoli | Paoli Unit 1 | Orange | 2804 | 239 | N/A | 4 | 8 | [15 empty] | 2025
60365 | SR 37 | N. Jct. US 150 to 1.14 mi. N. Jct. US 150 (N. Paoli Town Limits) | 54.5906 | 55.7313 | 55 +0.114 | 56 +0.418 | 25748 | C1 | 7 |  | 2 | FLEX | Not on the NHS | Paoli | Paoli Unit 1 | Orange | 7797 | 239 | N/A | 3 | 6 | [15 empty] | 2025
60366 | SR 68 | From E Jct SR 161 to US 231 | 48.2154 | 51.0213 | 51 +0.136 | 53 +0.880 | 48969 | C2 | 0 | 2031 | 2 | FLEX | Not on the NHS | Tell City | Chrisney Unit 5,Dale Unit 4 | Spencer,Warrick | 1066 | 151 | Yes | 4 | 8 | 2023 | [14 empty] | 2027
60367 | SR 54 | From E Jct SR 59 to 2.02 mi E. Of E. Jct SR 59 ( Linton East City Limits) | 15.4299 | 17.4491 | 25 +0.423 | 27 +0.390 | 91238 | B1 | 1 |  | 2 | FLEX | Not on the NHS | Linton | Linton | Greene | 11283 | 1646 | N/A | 3 | 6 | 2022 | 2040 | [6 empty] | 2040 Preventive Maintenance | [6 empty] | 2025
60368 | SR 65 | From SR 165 (Owensville) to 0.67 mi N of SR 165 (Old Princeton Rd) | 20.2411 | 20.9076 | 20 +0.273 | 20 +0.940 | 16657 | C1 | 6 |  | 2 | FLEX | Not on the NHS | Evansville,Vincennes | Oakland City Unit,Poseyville Unit 3 | Gibson | 3767 | 412 | N/A | 4 | 8 | [15 empty] | 2025
60371 | US 50 | From SR 450 to US 150 | 41.759 | 43.2896 | 41 +0.714 | 43 +0.223 | 14147 | B2 | 4 |  | 3 | FLEX | Is on the NHS | Paoli,Vincennes | Bedford Unit 3,Loogootee Unit | Martin | 6367 | 1200 | N/A | 4 | 8 | [15 empty] | 2025
60374 | SR 56 | From 0.93 mi West of S. Jct SR 57 (Petersburg West City Limits) to N. Jct SR 57/SR61 | 17.7809 | 19.2168 | 17 +0.798 | 19 +0.296 | 15967 | C1 | 0 |  | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Knox,Pike | 4816 | 248 | N/A | 4 | 8 | 2023 | [14 empty] | 2027
60375 | SR 56 | From N. Jct SR 57/SR61 to I-69 Interchange W. Ramp | 19.2168 | 20.578 | 19 +0.296 | 20 +0.659 | 26123 | C1 | 7 | 2031 | 2 | FLEX | Not on the NHS | Vincennes | Oakland City Unit,Vincennes Unit 2 | Knox,Pike | 5468 | 326 | N/A | 4 | 8 |  | 2031 | [6 empty] | 2031 Minor Structural | [6 empty] | 2025
60376 | US 231 | From 0.77 mi S of S Jct SR 157 to 0.54 mi N of S Jct SR 157 (Worthington) | 90.9414 | 92.2597 | 103 +0.938 | 105 +0.240 | 34041 | C1 | 4 |  | 2 | FLEX | Is on the NHS | Linton | Linton | Greene | 4503 | 602 | N/A | 4 | 8 | [15 empty] | 2025
60377 | US 231 | From 0.54 mi N of S Jct SR 157 to 8.32 miles S of W Jct of SR 46 (District Line) | 92.2597 | 100.7916 | 105 +0.240 | 113 +0.767 | 240691 | C2 | 4 | 2028 | 2 | FLEX | Is on the NHS | Linton | Crane Unit,Linton | Clay,Greene,Owen | 3826 | 510 | Yes | 4 | 8 | [6 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2025
60378 | SR 237 | From KY / IN State line to SR 66 | 0 | 0.40513 | 0 +0.000 | 0 +0.404 | 9949 | C1 | 37 |  | 2 | RIGID | Not on the NHS | Tell City | Derby Unit 2 | Perry | 8705 | 675 | N/A | 3 | 6 | [15 empty] | 2025
60379 | SR 237 | From SR 66 to SR 37 | 0.40513 | 5.3698 | 0 +0.404 | 5 +0.340 | 145815 | C2 | 6 | 2026 | 2 | FLEX | Not on the NHS | Tell City | Derby Unit 2 | Perry | 2786 | 431 | Yes | 4 | 8 | [6 empty] | 2039 | [6 empty] | 2039 Chip Seal |  | 2025
60380 | SR 37 | From SR 66 to SR 237 | 0 | 2.2787 | 0 +0.000 | 2 +0.278 | 86146 | C1 | 7 |  | 2 | FLEX | Not on the NHS | Tell City | Derby Unit 2 | Perry,Spencer | 7069 | 570 | N/A | 3 | 6 | [15 empty] | 2025
60381 | SR 37 | From SR 237 to SR 70 | 2.2787 | 10.9151 | 2 +0.278 | 10 +0.919 | 222816 | C1 | 10 | 2032 | 2 | FLEX | Not on the NHS | Tell City | Derby Unit 2 | Perry | 4189 | 825 | N/A | 4 | 8 | 2021 | 2032 | [6 empty] | 2032 Preventive Maintenance | [6 empty] | 2025
60382 | SR 57 | From 0.55 mi N. of N. Jct SR 58 (N Elnora Town Limits) to 5.69 mi N. of W. Jct. SR 58 (S Newberry Town Limits) | 64.1072 | 69.0121 | 67 +0.480 | 72 +0.389 | 94698 | C2 | 2 | 2028 | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Daviess,Greene | 1403 | 308 | Yes | 4 | 8 | 2021 | [5 empty] | 2042 | [6 empty] | 2042 Chip Seal |  | 2025
60383 | SR 57 | From 5.69 mi N. of W. Jct. SR 58 to 6.09 mi N. of W. Jct. SR 58 (S. Approach White River) (Newberry) | 69.0121 | 69.415 | 72 +0.389 | 72 +0.792 | 8456 | C1 | 2 |  | 2 | FLEX | Not on the NHS | Linton | Crane Unit,Linton | Greene | 1897 | 417 | N/A | 4 | 8 | 2021 | [14 empty] | 2025
60384 | SR 62 | From SR 162 to 0.71 mi W of SR 545 | 71.325 | 74.7995 | 72 +0.632 | 76 +0.188 | 61732 | C2 | 18 | 2028 | 2 | FLEX | Not on the NHS | Tell City | Birdseye Unit 3,Dale Unit 4 | Spencer | 1942 | 156 | Yes | 4 | 8 | [6 empty] | 2028 | [6 empty] | 2028 Chip Seal |  | 2025
60385 | SR 62 | From 0.71 mi W of SR 545 to 0.33 mi E of SR 545 (St Meinrad) | 74.7995 | 75.8429 | 76 +0.188 | 77 +0.214 | 18600 | C1 | 18 |  | 2 | FLEX | Not on the NHS | Tell City | Birdseye Unit 3 | Perry,Spencer | 1196 | 95 | N/A | 4 | 8 | [15 empty] | 2025
60386 | SR 62 | From 0.33 mi E of SR 545 to SR 145 | 75.8429 | 84.0086 | 77 +0.214 | 85 +0.351 | 128686 | C2 | 4 | 2027 | 2 | FLEX | Not on the NHS | Tell City | Birdseye Unit 3,Derby Unit 2 | Dubois,Perry,Spencer | 422 | 66 | Yes | 4 | 8 | [6 empty] | 2041 | [6 empty] | 2041 Chip Seal |  | 2025

## RPM_ProjectRecord
PK | # Lanes | AADT | AADTT | Replacement year | past rpm contract | past pavement project | Lastest Plan | last updated list | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2042 | 2042
60000 | 2 | 3656 | 986 | 4
60001 | 4 | 14526 | 6148 | 3
60002 | 4 | 15003 | 4991 | 3
60003 | 4 | 15539 | 6135 | 3
60004 | 4 | 19060 | 12948 | 3
60005 | 4 | 17394 | 6116 | 3
60006 | 4 | 17458 | 6486 | 3 |  | 2022 | 2022 | 2022
60007 | 4 | 16956 | 5780 | 3
60008 | 4 | 16523 | 6112 | 3
60009 | 4 | 17112 | 5662 | 3
60010 | 4 | 16328 | 6350 | 3
60011 | 4 | 16917 | 6712 | 3
60012 | 4 | 18617 | 5005 | 3
60013 | 4 | 29956 | 3336 | 3
60014 | 4 | 29775 | 3802 | 3
60015 | 4 | 16435 | 2679 | 3
60016 | 4 | 11096 | 2596 | 3
60017 | 4 | 9900 | 2252 | 4
60018 | 4 | 9034 | 1637 | 4
60019 | 4 | 8895 | 2383 | 4
60020 | 4 | 8895 | 2383 | 4
60021 | 4 | 38467 | 5122 | 2
60022 | 4 | 25274 | 3433 | 3 | 2025 |  | 2025 | 2025
60023 | 4 | 23678 | 3386 | 3
60024 | 4 | 19159 | 2941 | 3 | 2021 |  | 2021 | 2021
60025 | 4 | 11679 | 1791 | 3 | 2025 |  | 2025 | 2025
60026 | 4 | 13676 | 2097 | 3
60027 | 4 | 10183 | 1562 | 3 | 2025 |  | 2025 | 2025
60028 | 4 | 9109 | 1397 | 4 | 2025 |  | 2025 | 2025
60029 | 4 | 8302 | 1274 | 4 |  | 2022 | 2022 | 2022
60030 | 4 | 9801 | 1503 | 4
60031 | 4 | 12706 | 1948 | 3
60032 | 4 | 15749 | 2415 | 3
60033 | 4 | 6107 | 1020 | 4 |  | 2022 | 2022 | 2022
60034 | 4 | 8395 | 1413 | 4
60035 | 2 | 7306 | 2412 | 3 |  | 2024 | 2024 | 2024
60036 | 2 | 5511 | 961 | 4
60038 | 2 | 3199 | 959 | 4
60039 | 4 | 20057 | 6012 | 3 | 2024 |  | 2024 | 2024
60040 | 4 | 12486 | 1281 | 3 |  | 2024 | 2024 | 2024
60041 | 2 | 6037 | 165 | 3
60042 | 4 | 4883 | 2027 | 4
60043 | 4 | 6124 | 2283 | 4
60044 | 2 | 7316 | 938 | 3
60045 | 2 | 10325 | 992 | 3 |  | 2021 | 2021 | 2021
60046 | 2 | 13898 | 1274 | 3
60047 | 2 | 14892 | 1236 | 3 |  | 2021 | 2021 | 2021
60048 | 2 | 16747 | 1008 | 3 |  | 2021 | 2021 | 2021
60049 | 2 | 6797 | 810 | 3 | 2025 |  | 2025 | 2025
60050 | 2 | 6450 | 844 | 3
60051 | 2 | 5706 | 703 | 4
60052 | 2 | 4760 | 635 | 4
60053 | 2 | 7959 | 1063 | 3
60054 | 2 | 2259 | 302 | 4
60056 | 2 | 1496 | 214 | 4
60057 | 2 | 4796 | 707 | 4
60058 | 2 | 2760 | 183 | 4
60059 | 2 | 425 | 30 | 4
60060 | 2 | 202 | 19 | 4
60061 | 2 | 375 | 30 | 4
60062 | 2 | 2806 | 417 | 4
60063 | 2 | 2313 | 275 | 4
60064 | 2 | 3685 | 370 | 4 |  | 2022 | 2022 | 2022
60065 | 2 | 1666 | 201 | 4
60066 | 2 | 1922 | 231 | 4
60067 | 2 | 951 | 113 | 4
60068 | 2 | 7932 | 1051 | 3
60069 | 2 | 942 | 54 | 4
60070 | 2 | 432 | 26 | 4 |  | 2021 | 2021 | 2021
60071 | 2 | 2678 | 352 | 4
60072 | 2 | 4014 | 434 | 4 | 2025 |  | 2025 | 2025
60073 | 2 | 2899 | 226 | 4
60074 | 2 | 3864 | 350 | 4 |  | 2021 | 2021 | 2021
60075 | 2 | 8311 | 639 | 3 |  | 2022 | 2022 | 2022
60076 | 2 | 8168 | 573 | 3
60077 | 2 | 3615 | 188 | 4
60078 | 2 | 1739 | 190 | 4
60079 | 2 | 3250 | 174 | 4
60080 | 2 | 1890 | 217 | 4
60081 | 2 | 308 | 29 | 4
60082 | 2 | 3812 | 458 | 4 | 2024 |  | 2024 | 2024
60083 | 2 | 4677 | 563 | 4
60085 | 2 | 289 | 34 | 4
60086 | 2 | 1432 | 171 | 4
60087 | 2 | 1781 | 193 | 4
60088 | 2 | 743 | 40 | 4
60089 | 2 | 167 | 13 | 4 | 2022 |  | 2022 | 2022
60090 | 2 | 1021 | 123 | 4 |  | 2024 | 2024 | 2024
60091 | 2 | 3585 | 554 | 4
60092 | 2 | 12797 | 973 | 3
60093 | 2 | 802 | 25 | 4
60094 | 2 | 105 | 5 | 4
60095 | 2 | 763 | 46 | 4 |  | 2021 | 2021 | 2021
60096 | 2 | 1699 | 185 | 4 | 2022 |  | 2022 | 2022
60097 | 2 | 1020 | 121 | 4
60098 | 2 | 1365 | 164 | 4
60099 | 2 | 1243 | 149 | 4 |  | 2024 | 2024 | 2024
60100 | 2 | 115 | 15 | 4
60102 | 2 | 3161 | 852 | 4
60103 | 2 | 2450 | 560 | 4 |  | 2021 | 2021 | 2021
60104 | 2 | 2611 | 549 | 4 |  | 2021 | 2021 | 2021
60105 | 2 | 1333 | 114 | 4
60106 | 2 | 7339 | 225 | 3
60107 | 4 | 15403 | 1025 | 3 | 2024 |  | 2024 | 2024
60108 | 4 | 21560 | 1556 | 3
60109 | 2 | 999 | 110 | 4
60110 | 2 | 8843 | 718 | 3
60111 | 2 | 3859 | 467 | 4
60112 | 2 | 2119 | 271 | 4
60113 | 2 | 3069 | 369 | 4 | 2021 |  | 2021 | 2021
60114 | 2 | 493 | 17 | 4 |  | 2021 | 2021 | 2021
60115 | 2 | 289 | 10 | 4 | 2021 |  | 2021 | 2021
60116 | 2 | 874 | 96 | 4 |  | 2022 | 2022 | 2022
60117 | 2 | 3666 | 434 | 4
60118 | 2 | 1240 | 147 | 4 | 2024 |  | 2024 | 2024
60119 | 2 | 4711 | 684 | 4 | 2025 |  | 2025 | 2025
60120 | 2 | 6119 | 892 | 3 | 2025 |  | 2025 | 2025
60121 | 2 | 8237 | 1202 | 3
60122 | 2 | 6797 | 991 | 3
60123 | 2 | 4057 | 592 | 4
60124 | 2 | 2005 | 292 | 4 | 2022 |  | 2022 | 2022
60125 | 2 | 4407 | 338 | 4 | 2022 |  | 2022 | 2022
60126 | 2 | 1679 | 131 | 4
60127 | 2 | 1438 | 285 | 4
60128 | 2 | 1567 | 266 | 4 |  | 2024 | 2024 | 2024
60129 | 2 | 1398 | 220 | 4
60130 | 2 | 547 | 23 | 4 | 2025 | 2024 | 2025 | 2025
60131 | 2 | 3709 | 369 | 4 | 2025 |  | 2025 | 2025
60132 | 2 | 169 | 9 | 4 | 2025 |  | 2025 | 2025
60133 | 2 | 808 | 41 | 4
60135 | 2 | 4928 | 265 | 4
60136 | 2 | 3263 | 168 | 4 |  | 2022 | 2022 | 2022
60137 | 2 | 7172 | 532 | 3
60138 | 2 | 3381 | 424 | 4
60139 | 2 | 3549 | 317 | 4 | 2025 |  | 2025 | 2025
60140 | 2 | 7825 | 666 | 3
60141 | 2 | 1735 | 253 | 4 | 2022 |  | 2022 | 2022
60142 | 2 | 10896 | 912 | 3
60143 | 2 | 5462 | 732 | 4
60144 | 2 | 1443 | 314 | 4
60146 | 2 | 2185 | 481 | 4
60147 | 2 | 4423 | 971 | 4
60148 | 2 | 2347 | 515 | 4 |  | 2021 | 2021 | 2021
60150 | 2 | 1778 | 391 | 4
60151 | 2 | 357 | 43 | 4 | 2021 |  | 2021 | 2021
60152 | 2 | 1273 | 154 | 4
60153 | 2 | 741 | 89 | 4
60154 | 2 | 460 | 55 | 4 | 2023 |  | 2023 | 2023
60155 | 2 | 2567 | 310 | 4
60156 | 2 | 1651 | 197 | 4 | 2025 |  | 2025 | 2025
60157 | 2 | 1762 | 211 | 4
60159 | 2 | 3254 | 296 | 4
60160 | 2 | 5166 | 308 | 4
60161 | 2 | 613 | 36 | 4 |  | 2021 | 2021 | 2021
60162 | 2 | 1176 | 68 | 4 |  | 2024 | 2024 | 2024
60163 | 2 | 2173 | 261 | 4
60164 | 2 | 3861 | 463 | 4 | 2024 |  | 2024 | 2024
60165 | 2 | 2238 | 232 | 4
60166 | 2 | 3518 | 445 | 4 |  | 2021 | 2021 | 2021
60167 | 2 | 3680 | 233 | 4
60168 | 4 | 18159 | 1020 | 3
60169 | 2 | 4290 | 239 | 4
60170 | 2 | 755 | 100 | 4
60171 | 2 | 1765 | 233 | 4
60172 | 2 | 1888 | 249 | 4
60173 | 2 | 2654 | 350 | 4 |  | 2024 | 2024 | 2024
60174 | 2 | 4846 | 642 | 4
60175 | 2 | 12781 | 1333 | 3
60176 | 4 | 15442 | 1774 | 3
60178 | 4 | 19552 | 604 | 3
60179 | 4 | 26205 | 1557 | 3
60180 | 2 | 11860 | 439 | 3
60181 | 2 | 2739 | 101 | 4 | 2023 |  | 2023 | 2023
60182 | 2 | 1430 | 121 | 4 | 2023 |  | 2023 | 2023
60183 | 2 | 2424 | 261 | 4 |  | 2022 | 2022 | 2022
60184 | 2 | 1367 | 125 | 4
60187 | 2 | 258 | 41 | 4
60188 | 2 | 269 | 16 | 4
60189 | 2 | 393 | 15 | 4
60190 | 2 | 593 | 71 | 4 | 2021 |  | 2021 | 2021
60191 | 2 | 1496 | 179 | 4
60192 | 2 | 7990 | 1137 | 3
60193 | 2 | 10217 | 1490 | 3
60194 | 4 | 13118 | 1913 | 3 |  | 2023 | 2023 | 2023
60195 | 2 | 7599 | 1107 | 3
60196 | 2 | 4348 | 159 | 4
60197 | 2 | 3529 | 281 | 4 |  | 2021 | 2021 | 2021
60198 | 2 | 1988 | 158 | 4
60199 | 2 | 2665 | 425 | 4
60200 | 2 | 5357 | 526 | 4
60201 | 2 | 3839 | 470 | 4 |  | 2023 | 2023 | 2023
60202 | 2 | 3411 | 528 | 4 | 2025 |  | 2025 | 2025
60203 | 2 | 2185 | 378 | 4 | 2025 | 2021 | 2025 | 2025
60204 | 2 | 3291 | 340 | 4
60205 | 2 | 3741 | 332 | 4
60206 | 2 | 1330 | 160 | 4
60207 | 2 | 3612 | 254 | 4
60208 | 2 | 1779 | 184 | 4
60209 | 2 | 1383 | 154 | 4
60211 | 2 | 4305 | 469 | 4
60212 | 2 | 841 | 91 | 4
60213 | 2 | 929 | 112 | 4
60214 | 2 | 1890 | 188 | 4 | 2023 |  | 2023 | 2023
60215 | 2 | 6814 | 378 | 3 |  | 2023 | 2023 | 2023
60216 | 4 | 10369 | 681 | 3
60217 | 4 | 17838 | 1099 | 3
60218 | 6 | 54934 | 1521 | 2
60219 | 6 | 34920 | 1413 | 2
60220 | 4 | 14757 | 778 | 3
60221 | 4 | 11589 | 1007 | 3 |  | 2021 | 2021 | 2021
60222 | 2 | 9281 | 1051 | 3 |  | 2021 | 2021 | 2021
60223 | 2 | 6233 | 665 | 3 |  | 2021 | 2021 | 2021
60224 | 2 | 2989 | 476 | 4
60225 | 2 | 4814 | 660 | 4
60226 | 2 | 3664 | 399 | 4
60227 | 2 | 11086 | 600 | 3 | 2025 | 2022 | 2025 | 2025
60228 | 2 | 9968 | 437 | 3 | 2021 |  | 2021 | 2021
60229 | 2 | 1407 | 75 | 4 | 2021 |  | 2021 | 2021
60230 | 2 | 169 | 30 | 4
60231 | 2 | 242 | 22 | 4
60232 | 2 | 2652 | 276 | 4 |  | 2021 | 2021 | 2021
60233 | 2 | 3593 | 219 | 4 |  | 2022 | 2022 | 2022
60234 | 2 | 727 | 51 | 4 |  | 2021 | 2021 | 2021
60235 | 4 | 12853 | 767 | 3
60236 | 2 | 6964 | 702 | 3 |  | 2024 | 2024 | 2024
60237 | 2 | 6573 | 959 | 3
60238 | 2 | 3848 | 560 | 4
60239 | 2 | 1929 | 321 | 4
60240 | 2 | 1090 | 159 | 4
60241 | 2 | 1815 | 265 | 4
60242 | 2 | 2791 | 406 | 4
60243 | 2 | 359 | 30 | 4 |  | 2023 | 2023 | 2023
60244 | 2 | 2243 | 179 | 4
60245 | 2 | 781 | 76 | 4
60246 | 2 | 1847 | 180 | 4
60247 | 2 | 5232 | 617 | 4
60248 | 2 | 2222 | 267 | 4
60249 | 2 | 1189 | 142 | 4
60252 | 2 | 258 | 34 | 4
60253 | 2 | 1673 | 201 | 4
60254 | 2 | 2228 | 574 | 4
60255 | 2 | 3255 | 953 | 4
60256 | 2 | 2830 | 1010 | 4
60257 | 2 | 3291 | 676 | 4
60258 | 2 | 1534 | 200 | 4
60259 | 2 | 555 | 54 | 4
60260 | 2 | 699 | 76 | 4
60261 | 4 | 38467 | 5288 | 2
60262 | 2 | 1144 | 137 | 4
60263 | 2 | 3464 | 490 | 4
60264 | 2 | 3341 | 441 | 4 |  | 2022 | 2022 | 2022
60265 | 2 | 1000 | 23 | 4
60266 | 2 | 798 | 95 | 4 |  | 2023 | 2023 | 2023
60267 | 2 | 1544 | 186 | 4 |  | 2021 | 2021 | 2021
60268 | 2 | 4989 | 1095 | 4 |  | 2023 | 2023 | 2023
60269 | 2 | 8643 | 666 | 3
60270 | 2 | 8080 | 1179 | 3
60271 | 2 | 1705 | 204 | 4
60273 | 4 | 18139 | 2782 | 3 |  | 2024 | 2024 | 2024
60274 | 6 | 41404 | 2306 | 2
60275 | 2 | 5249 | 1152 | 4 |  | 2023 | 2023 | 2023
60276 | 4 | 8734 | 2166 | 4
60277 | 2 | 4178 | 500 | 4 | 2025 |  | 2025 | 2025
60279 | 2 | 3702 | 444 | 4
60280 | 2 | 3861 | 230 | 4
60281 | 4 | 7582 | 713 | 4
60282 | 4 | 6221 | 509 | 4
60283 | 2 | 4679 | 560 | 4 | 0
60284 | 2 | 1027 | 139 | 4 |  | 2021 | 2021 | 2021
60285 | 2 | 7106 | 674 | 3 |  | 2021 | 2021 | 2021
60286 | 2 | 6609 | 538 | 3 |  | 2022 | 2022 | 2022
60287 | 2 | 5982 | 1313 | 4 |  | 2021 | 2021 | 2021
60288 | 2 | 4655 | 454 | 4
60289 | 2 | 6393 | 932 | 3
60290 | 2 | 7789 | 1320 | 3 |  | 2024 | 2024 | 2024
60291 | 2 | 2834 | 337 | 4
60292 | 2 | 2785 | 327 | 4
60293 | 2 | 2501 | 184 | 4
60294 | 2 | 3255 | 507 | 4
60295 | 2 | 6447 | 799 | 3
60296 | 2 | 8303 | 859 | 3
60297 | 2 | 5227 | 620 | 4
60298 | 2 | 5093 | 742 | 4
60299 | 2 | 1115 | 134 | 4
60300 | 4 | 6542 | 2126 | 4
60301 | 4 | 5904 | 2112 | 4
60302 | 2 | 11947 | 671 | 3 |  | 2023 | 2023 | 2023
60303 | 2 | 3185 | 377 | 4
60304 | 2 | 3292 | 390 | 4 | 2024 |  | 2024 | 2024
60305 | 2 | 1915 | 212 | 4
60306 | 2 | 2527 | 334 | 4
60307 | 2 | 978 | 117 | 4
60308 | 2 | 2885 | 420 | 4
60309 | 2 | 2049 | 299 | 4
60310 | 4 | 31107 | 3840 | 2
60311 | 6 | 32484 | 3879 | 2 |  | 2023 | 2023 | 2023
60312 | 4 | 34475 | 3945 | 2 | 2025 |  | 2025 | 2025
60313 | 4 | 39653 | 2010 | 2
60315 | 2 | 2894 | 212 | 4
60316 | 2 | 3481 | 538 | 4
60317 | 4 | 21086 | 1532 | 3 | 2024 |  | 2024 | 2024
60318 | 2 | 3859 | 467 | 4
60319 | 2 | 995 | 111 | 4 |  | 2024 | 2024 | 2024
60320 | 2 | 6666 | 720 | 3
60321 | 2 | 4327 | 579 | 4
60322 | 2 | 2124 | 119 | 4
60323 | 2 | 4593 | 710 | 4
60324 | 2 | 2428 | 148 | 4 |  | 2021 | 2021 | 2021
60326 | 2 | 5439 | 628 | 4
60327 | 2 | 2384 | 348 | 4
60328 | 2 | 4819 | 382 | 4 |  | 2021 | 2021 | 2021
60330 | 4 | 10582 | 1896 | 3
60331 | 4 | 11561 | 2307 | 3
60332 | 4 | 20418 | 758 | 3
60333 | 2 | 1268 | 153 | 4 | 2024 |  | 2024 | 2024
60334 | 4 | 14595 | 540 | 3 | 2024 |  | 2024 | 2024
60335 | 3 | 8787 | 713 | 3
60337 | 2 | 2871 | 241 | 4 | 2025 |  | 2025 | 2025
60338 | 2 | 2300 | 335 | 4
60339 | 4 | 23778 | 2563 | 3
60340 | 2 | 7494 | 1001 | 3
60342 | 4 | 7558 | 1442 | 4
60343 | 2 | 8130 | 248 | 3
60344 | 2 | 8695 | 265 | 3
60345 | 2 | 4891 | 713 | 4 | 2025 |  | 2025 | 2025
60346 | 2 | 561 | 48 | 4 | 2025 |  | 2025 | 2025
60347 | 2 | 1740 | 382 | 4 |  | 2021 | 2021 | 2021
60348 | 2 | 421 | 53 | 4
60349 | 2 | 1350 | 162 | 4
60350 | 2 | 707 | 69 | 4
60351 | 2 | 2769 | 461 | 4
60352 | 2 | 1559 | 186 | 4
60353 | 2 | 1284 | 124 | 4
60354 | 2 | 1290 | 36 | 4 |  | 2021 | 2021 | 2021
60355 | 2 | 817 | 26 | 4
60356 | 2 | 1161 | 141 | 4
60357 | 2 | 2367 | 312 | 4
60358 | 2 | 3020 | 275 | 4
60359 | 2 | 1300 | 75 | 4
60360 | 2 | 2481 | 544 | 4 |  | 2021 | 2021 | 2021
60361 | 2 | 1619 | 355 | 4 |  | 2021 | 2021 | 2021
60362 | 2 | 1964 | 235 | 4 |  | 2024 | 2024 | 2024
60363 | 2 | 1455 | 50 | 4 |  | 2024 | 2024 | 2024
60364 | 2 | 2804 | 239 | 4
60365 | 2 | 7797 | 239 | 3
60366 | 2 | 1066 | 151 | 4 |  | 2023 | 2023 | 2023
60367 | 2 | 11283 | 1646 | 3 |  | 2022 | 2022 | 2022
60368 | 2 | 3767 | 412 | 4
60371 | 3 | 6367 | 1200 | 3
60374 | 2 | 4816 | 248 | 4 |  | 2023 | 2023 | 2023
60375 | 2 | 5468 | 326 | 4
60376 | 2 | 4503 | 602 | 4
60377 | 2 | 3826 | 510 | 4
60378 | 2 | 8705 | 675 | 3
60379 | 2 | 2786 | 431 | 4
60380 | 2 | 7069 | 570 | 3
60381 | 2 | 4189 | 825 | 4 | 2021 |  | 2021 | 2021
60382 | 2 | 1403 | 308 | 4 |  | 2021 | 2021 | 2021
60383 | 2 | 1897 | 417 | 4 |  | 2021 | 2021 | 2021
60384 | 2 | 1942 | 156 | 4
60385 | 2 | 1196 | 95 | 4
60386 | 2 | 422 | 66 | 4

## RpmContracts
PK | past_contracts | rpm_planned (DAVID)
60000 |  | 2027
60001 |  | 2027
60002 |  | 2027
60003 |  | 2027
60004 |  | 2027
60005 |  | 2027
60006 |  | 2027
60007 |  | 2027
60008 |  | 2027
60009 |  | 2027
60010 |  | 2027
60011 |  | 2027
60012 |  | 2027
60013 |  | 2027
60014 |  | 2027
60015 |  | 2027
60016 |  | 2027
60017 |  | 2027
60018 |  | 2027
60019 |  | 2027
60020 |  | 2027
60021
60022 | 2025 | 2027
60023
60024 | 2021 | 2027
60025 | 2025 | 2027
60026 |  | 2027
60027 | 2025 | 2027
60028 | 2025 | 2027
60029 |  | 2027
60030 |  | 2027
60031 |  | 2027
60032 |  | 2027
60033
60034 |  | 2027
60035
60036
60038 |  | 2026
60039 | 2024
60040
60041
60042 |  | 2026
60043 |  | 2026
60044
60045
60046
60047
60048
60049 | 2025
60050
60051
60052
60053
60054
60055
60056 |  | 2027
60057 |  | 2027
60058 |  | 2027
60059 |  | 2027
60060 |  | 2027
60061 |  | 2027
60062
60063 |  | 2026
60064
60065
60066
60067
60068 |  | 2026
60069
60070 |  | 2026
60071
60072 | 2025
60073
60074 |  | 2026
60075
60076
60077
60078
60079 |  | 2026
60080
60081
60082 | 2024
60083 |  | 2026
60084
60085
60086
60087
60088
60089 | 2022
60090
60091 |  | 2026
60092
60093 |  | 2026
60094
60095 |  | 2026
60096 | 2022 | 2026
60097
60098
60099
60100
60101
60102
60103 |  | 2026
60104 |  | 2026
60105 |  | 2027
60106
60107 | 2024
60108 |  | 2027
60109
60110
60111
60112
60113 | 2021 | 2026
60114 |  | 2026
60115 | 2021
60116
60117
60118 | 2024
60119 | 2025
60120 | 2025
60121 |  | 2026
60122
60123 |  | 2027
60124 | 2022
60125 | 2022
60126
60127 |  | 2027
60128
60129
60130 | 2025 | 2027
60131 | 2025
60132 | 2025
60133
60134
60135 |  | 2026
60136
60137 |  | 2026
60138
60139 | 2025
60140
60141 | 2022
60142
60143
60144
60146
60147
60148
60149
60150
60151 | 2021
60152 |  | 2026
60153 |  | 2026
60154 | 2023
60155
60156 | 2025
60157
60158
60159
60160 |  | 2026
60161 |  | 2026
60162
60163
60164 | 2024
60165
60166
60167 |  | 2026
60168 |  | 2026
60169
60170
60171 |  | 2026
60172
60173
60174
60175
60176 |  | 2027
60178
60179
60180
60181 | 2023
60182 | 2023
60183 |  | 2027
60184
60185
60186
60187 |  | 2027
60188 |  | 2027
60189 |  | 2027
60190 | 2021
60191
60192
60193
60194
60195
60196 |  | 2026
60197
60198
60199
60200
60201
60202 | 2025
60203 | 2025
60204
60205
60206 |  | 2026
60207
60208
60209
60211
60212
60213 |  | 2026
60214 | 2023
60215
60216 |  | 2026
60217
60218
60219
60220 |  | 2027
60221
60222
60223
60224 |  | 2027
60225
60226
60227 | 2025
60228 | 2021
60229 | 2021
60230
60231 |  | 2027
60232
60233
60234
60235
60236
60237 |  | 2026
60238
60239
60240 |  | 2026
60241 |  | 2026
60242
60243
60244
60245
60246
60247
60248
60249
60252
60253
60254
60255
60256
60257 |  | 2026
60258
60259
60260
60261
60262
60263
60264
60265
60266
60267
60268
60269 |  | 2026
60270
60271
60273
60274
60275
60276 |  | 2027
60277 | 2025
60279
60280
60281 |  | 2027
60282
60283
60284
60285 |  | 2026
60286 |  | 2026
60287
60288
60289
60290
60291
60292
60293
60294
60295
60296
60297
60298
60299
60300 |  | 2027
60301 |  | 2027
60302
60303
60304 | 2024
60305
60306
60307
60308
60309 |  | 2026
60310
60311
60312 | 2025
60313
60315
60316
60317 | 2024
60318
60319
60320
60321
60322
60323
60324
60326
60327
60328
60329
60330 |  | 2027
60331 |  | 2027
60332
60333 | 2024
60334 | 2024
60335
60336
60337 | 2025
60338
60339 |  | 2027
60340
60342 |  | 2027
60343
60344
60345 | 2025
60346 | 2025
60347
60348
60349
60350
60351
60352
60353 |  | 2026
60354 |  | 2026
60355 |  | 2027
60356 |  | 2026
60357 |  | 2026
60358 |  | 2026
60359
60360
60361
60362
60363
60364
60365
60366
60367
60368
60369
60370
60371
60381 | 2021

## 20yPlan
PK | 20yP1 | 20yP2 | 20yP3 | 20yP4 | 20yP5
60000
60001 | 2036 Preventive Maintenance
60002 | 2036 Preventive Maintenance
60003 | 2034 Preventive Maintenance
60004 | 2039 Minor Structural
60005 | 2030 Minor Structural
60006 | 2038 Preventive Maintenance
60007 | 2030 Minor Structural
60008 | 2035 Preventive Maintenance
60009 | 2040 Preventive Maintenance
60010 | 2034 Preventive Maintenance
60011 | 2031 Preventive Maintenance
60012 | 2033 Preventive Maintenance
60013 | 2042 Preventive Maintenance
60014 | 2038 Rehab | 2039 Rehab
60015 | 2034 Preventive Maintenance | 2044 Preventive Maintenance
60016 | 2039 Preventive Maintenance
60017 | 2033 Preventive Maintenance | 2043 Preventive Maintenance
60018 | 2033 Preventive Maintenance | 2043 Preventive Maintenance
60019 | 2036 Preventive Maintenance
60020 | 2042 Preventive Maintenance
60021
60022
60023 | 2030 Major Structural
60024
60025
60026
60027
60028 | 2030 Preventive Maintenance
60029
60030
60031
60032
60033
60034
60035
60036
60038
60039
60040 | 2039 Preventive Maintenance
60041
60042 | 2032 Preventive Maintenance
60043
60044
60045 | 2041 Preventive Maintenance
60046
60047
60048 | 2040 Preventive Maintenance
60049
60050
60051
60052
60053 | 2031 Major Structural
60054
60056
60057
60058
60059
60060
60061
60062
60063
60064
60065
60066
60067
60068
60069 | 2040 Preventive Maintenance
60070
60071
60072
60073 | 2033 Preventive Maintenance
60074
60075
60076
60077
60078
60079
60080
60081
60082
60083
60085
60086
60087
60088
60089
60090
60091 | 2041 Preventive Maintenance
60092 | 2030 Preventive Maintenance
60093
60094 | 2038 Preventive Maintenance
60095
60096
60097
60098
60099
60100
60102
60103
60104
60105
60106
60107
60108
60109
60110
60111
60112
60113
60114
60115
60116
60117
60118
60119
60120
60121
60122
60123
60124
60125
60126
60127
60128
60129
60130
60131
60132
60133
60135
60136
60137
60138
60139
60140
60141
60142
60143
60144
60146
60147
60148
60150
60151
60152
60153
60154
60155
60156
60157
60159
60160
60161
60162
60163
60164
60165
60166
60167 | 2032 Preventive Maintenance
60168
60169
60170
60171
60172
60173
60174
60175 | 2041 Preventive Maintenance
60176 | 2028 Pavement Patching | 2035 Minor Structural
60178
60179 | 2042 Preventive Maintenance
60180 | 2036 Preventive Maintenance
60181
60182
60183
60184
60187
60188
60189
60190
60191
60192
60193
60194
60195
60196
60197
60198
60199
60200
60201
60202
60203
60204
60205
60206
60207
60208
60209
60211
60212
60213
60214
60215
60216
60217
60218
60219
60220
60221
60222
60223
60224
60225
60226
60227
60228 | 2036 Preventive Maintenance
60229 | 2034 Preventive Maintenance
60230
60231
60232
60233
60234
60235
60236
60237
60238
60239
60240
60241
60242
60243
60244 | 2040 Preventive Maintenance
60245 | 2038 Preventive Maintenance
60246
60247
60248
60249 | 2040 Preventive Maintenance
60252
60253
60254
60255
60256
60257
60258
60259 | 2036 Preventive Maintenance
60260
60261 | 2035 Preventive Maintenance
60262
60263 | 2038 Rehab | 2039 Rehab
60264
60265
60266 | 2043 Preventive Maintenance
60267
60268
60269
60270
60271
60273
60274
60275
60276 | 2034 Preventive Maintenance | 2044 Preventive Maintenance
60277
60279
60280
60281
60282
60283
60284
60285
60286
60287
60288
60289
60290
60291
60292
60293
60294
60295
60296
60297
60298
60299
60300
60301 | 2033 Preventive Maintenance
60302 | 2036 Preventive Maintenance
60303
60304
60305
60306
60307
60308
60309
60310
60311
60312
60313 | 2042 Preventive Maintenance
60315
60316
60317
60318
60319
60320
60321
60322
60323
60324
60326
60327
60328
60330 | 2033 Preventive Maintenance
60331 | 2036 Preventive Maintenance
60332
60333
60334
60335
60337
60338
60339 | 2035 Preventive Maintenance
60340
60342
60343
60344
60345
60346
60347
60348
60349
60350
60351
60352
60353
60354
60355
60356
60357
60358
60359
60360
60361
60362
60363
60364
60365
60366
60367 | 2040 Preventive Maintenance
60368
60371
60374
60375 | 2031 Minor Structural
60376
60377
60378
60379
60380
60381 | 2032 Preventive Maintenance
60382
60383
60384
60385
60386

## 3rdPhaseChipSeal
PK | Most Recent Chip | Most Recent Chip layers | FY1 | FY2 | FY3 | FY4 | FY1_layer | FY2_layer | FY3_layer | FY4_layer | 3rd phase chip seal year_PLANNED
60000 |  |  | 2026 |  |  |  | 1
60001
60002
60003
60004
60005
60006
60007
60008
60009
60010
60011
60012
60013
60014
60015
60016
60017
60018
60019
60020
60021
60022
60023
60024
60025
60026
60027
60028
60029
60030
60031
60032
60033
60034
60035
60036
60038 |  |  | 2029 | 2036 | 2043 |  | 1 | 2 | 3 |  | 2043
60039
60040
60041 |  |  | 2026 |  |  |  | 1
60042
60043
60044
60045
60046
60047
60048
60049
60050
60051 |  |  | 2026 |  |  |  | 1
60052 |  |  | 2026 | 2032 | 2039 |  | 1 | 2 | 3 |  | 2039
60053
60054 |  |  | 2027 | 2033 | 2040 |  | 1 | 2 | 3 |  | 2040
60056 |  |  | 2027 | 2032 | 2039 |  | 1 | 2 | 3 |  | 2039
60057 |  |  | 2026 | 2033 | 2040 |  | 1 | 2 | 3 |  | 2040
60058 |  |  | 2026 | 2032 | 2039 |  | 1 | 2 | 3 |  | 2039
60059 | 2020 | 2 | 2027 | 2034 | 2041 |  | 3 | 1 | 2 |  | 2027
60060 | 2019 | 2 | 2027 | 2034 | 2041 |  | 3 | 1 | 2 |  | 2027
60061 | 2020 | 1 | 2027 | 2033 | 2040 |  | 2 | 3 | 1 |  | 2033
60062 |  |  | 2026 | 2032 | 2039 |  | 1 | 2 | 3 |  | 2039
60063 | 2025 | 2 | 2025 | 2030 | 2037 | 2044 | 2 | 3 | 1 | 2 | 2030
60064
60065 | 2020 | 2 | 2026 | 2033 | 2040 |  | 3 | 1 | 2 |  | 2026
60066 | 2018 | 2 | 2028 | 2035 | 2042 |  | 3 | 1 | 2 |  | 2028
60067 | 2023 | 1 | 2030 | 2037 | 2044 |  | 2 | 3 | 1 |  | 2037
60068
60069 | 2013 | 1 | 2026 | 2032 |  |  | 2 | 3 |  |  | 2032
60070 |  |  | 2029 | 2036 | 2043 |  | 1 | 2 | 3 |  | 2043
60071
60072
60073 | 2022 | 1 | 2027 | 2034 | 2041 |  | 2 | 3 | 1 |  | 2034
60074 |  |  | 2029 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60075
60076
60077 |  |  | 2029 | 2036 | 2043 |  | 1 | 2 | 3 |  | 2043
60078 | 2019 | 2 | 2027 | 2034 | 2041 |  | 3 | 1 | 2 |  | 2027
60079 | 2021 | 1 | 2026 | 2034 | 2041 |  | 2 | 3 | 1 |  | 2034
60080 |  |  | 2027 |  |  |  | 1
60081 |  |  | 2031 | 2038 |  |  | 1 | 2
60082 | 2024 | 3 | 2028 | 2040 |  |  | 1 | 2
60083
60085 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60086 | 2020 | 2 | 2027 | 2034 | 2041 |  | 3 | 1 | 2 |  | 2027
60087 | 2018 | 1 | 2027 | 2033 | 2040 |  | 2 | 3 | 1 |  | 2033
60088 | 2016 | 2 | 2026 | 2033 | 2040 |  | 3 | 1 | 2 |  | 2026
60089 | 2022 | 3 | 2031 | 2038 |  |  | 1 | 2
60090 |  |  | 2031 | 2038 |  |  | 1 | 2
60091
60092
60093 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60094 |  |  | 2026 | 2032 |  |  | 1 | 2
60095 | 2019 | 1 | 2028 |  |  |  | 2
60096 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60097
60098 | 2022 | 3 | 2027 | 2034 | 2041 |  | 1 | 2 | 3 |  | 2041
60099 | 2021 | 2 | 2031 | 2038 |  |  | 3 | 1 |  |  | 2031
60100 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60102
60103 | 2018 | 2 | 2028 | 2035 | 2042 |  | 3 | 1 | 2 |  | 2028
60104 |  |  | 2029 | 2036 | 2043 |  | 1 | 2 | 3 |  | 2043
60105 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60106
60107
60108
60109 |  |  | 2028 | 2034 | 2041 |  | 1 | 2 | 3 |  | 2041
60110
60111 | 2019 | 1 | 2030 | 2037 | 2044 |  | 2 | 3 | 1 |  | 2037
60112 | 2023 | 1 | 2028 | 2035 | 2042 |  | 2 | 3 | 1 |  | 2035
60113 | 2022 | 1 | 2026 | 2034 | 2041 |  | 2 | 3 | 1 |  | 2034
60114 | 2021 | 1 | 2029 | 2035 | 2042 |  | 2 | 3 | 1 |  | 2035
60115 |  |  | 2027 | 2034 | 2041 |  | 1 | 2 | 3 |  | 2041
60116 | 2020 | 3 | 2030 | 2037 | 2044 |  | 1 | 2 | 3 |  | 2044
60117 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60118 | 2018 | 2 | 2033 | 2040 |  |  | 3 | 1 |  |  | 2033
60119 | 2024 | 3 | 2034 | 2041 |  |  | 1 | 2
60120 | 2021 | 1 | 2027 |  |  |  | 2
60121
60122
60123 |  |  | 2027 | 2033 | 2040 |  | 1 | 2 | 3 |  | 2040
60124 | 2022 | 2 | 2028 | 2035 | 2042 |  | 3 | 1 | 2 |  | 2028
60125 | 2022 | 2 | 2028 | 2035 | 2042 |  | 3 | 1 | 2 |  | 2028
60126 |  |  | 2026 | 2032 | 2039 |  | 1 | 2 | 3 |  | 2039
60127 |  |  | 2026 | 2032 | 2039 |  | 1 | 2 | 3 |  | 2039
60128 |  |  | 2031 | 2038 |  |  | 1 | 2
60129 | 2020 | 1 | 2028 | 2034 | 2041 |  | 2 | 3 | 1 |  | 2034
60130 |  |  | 2031 | 2038 |  |  | 1 | 2
60131 |  |  | 2029 | 2036 | 2043 |  | 1 | 2 | 3 |  | 2043
60132 | 2018 | 2 | 2027 | 2034 | 2041 |  | 3 | 1 | 2 |  | 2027
60133 |  |  | 2031 | 2038 |  |  | 1 | 2
60135 |  |  | 2027 | 2034 | 2041 |  | 1 | 2 | 3 |  | 2041
60136 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60137
60138 | 2022 | 1 | 2028 | 2035 | 2042 |  | 2 | 3 | 1 |  | 2035
60139 | 2024 | 1 | 2030 | 2037 | 2044 |  | 2 | 3 | 1 |  | 2037
60140
60141 | 2022 | 2 | 2028 | 2035 | 2042 |  | 3 | 1 | 2 |  | 2028
60142
60143
60144 | 2025 | 1 | 2025 | 2031 | 2038 |  | 1 | 2 | 3 |  | 2038
60146 |  |  | 2027 | 2034 | 2041 |  | 1 | 2 | 3 |  | 2041
60147 |  |  | 2027 | 2034 | 2041 |  | 1 | 2 | 3 |  | 2041
60148 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60150 | 2019 | 1 | 2027 | 2034 | 2041 |  | 2 | 3 | 1 |  | 2034
60151 | 2021 | 3 | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60152
60153 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60154 | 2023 | 3 | 2029 | 2036 | 2043 |  | 1 | 2 | 3 |  | 2043
60155 | 2024 | 2 | 2030 | 2037 | 2044 |  | 3 | 1 | 2 |  | 2030
60156 | 2025 | 3 | 2025 | 2033 | 2040 |  | 3 | 1 | 2 |  | 2025
60157 |  |  | 2029 | 2036 | 2043 |  | 1 | 2 | 3 |  | 2043
60159 |  |  | 2029 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60160
60161 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60162
60163 | 2025 | 2 | 2025 | 2031 | 2038 |  | 2 | 3 | 1 |  | 2031
60164 | 2024 | 3 | 2026 | 2033 | 2040 |  | 1 | 2 | 3 |  | 2040
60165 |  |  | 2027 | 2032 | 2039 |  | 1 | 2 | 3 |  | 2039
60166 |  |  | 2029 | 2036 | 2043 |  | 1 | 2 | 3 |  | 2043
60167
60168
60169 |  |  | 2026 |  |  |  | 1
60170 |  |  | 2031 | 2038 |  |  | 1 | 2
60171 | 2025 | 1 | 2025 | 2032 | 2039 |  | 1 | 2 | 3 |  | 2039
60172 | 2025 | 2 | 2025 | 2033 | 2040 |  | 2 | 3 | 1 |  | 2033
60173 |  |  | 2031 | 2038 |  |  | 1 | 2
60174 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60175
60176
60178
60179
60180
60181 | 2023 | 2 | 2029 | 2036 | 2043 |  | 3 | 1 | 2 |  | 2029
60182 | 2023 | 2 | 2029 | 2036 | 2043 |  | 3 | 1 | 2 |  | 2029
60183
60184 | 2020 | 2 | 2028 | 2035 | 2042 |  | 3 | 1 | 2 |  | 2028
60187 | 2017 | 2 | 2026 | 2033 | 2040 |  | 3 | 1 | 2 |  | 2026
60188 | 2024 | 1 | 2030 | 2037 | 2044 |  | 2 | 3 | 1 |  | 2037
60189 | 2024 | 2 | 2030 | 2037 | 2044 |  | 3 | 1 | 2 |  | 2030
60190 | 2021 | 3 | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60191 | 2021 | 2 | 2027 | 2034 | 2041 |  | 3 | 1 | 2 |  | 2027
60192
60193
60194
60195
60196 |  |  | 2026 | 2032 | 2039 |  | 1 | 2 | 3 |  | 2039
60197 |  |  | 2029 | 2036 | 2043 |  | 1 | 2 | 3 |  | 2043
60198 |  |  | 2034 | 2041 |  |  | 1 | 2
60199 | 2013 | 1 | 2034 | 2041 |  |  | 2 | 3 |  |  | 2041
60200
60201 |  |  | 2031 | 2037 | 2044 |  | 1 | 2 | 3 |  | 2044
60202 | 2024 | 1 | 2030 |  |  |  | 2
60203 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60204 | 2025 | 1 | 2025 | 2031 | 2038 |  | 1 | 2 | 3 |  | 2038
60205 | 2025 | 1 | 2025 | 2031 | 2038 |  | 1 | 2 | 3 |  | 2038
60206 |  |  | 2029 | 2036 | 2043 |  | 1 | 2 | 3 |  | 2043
60207 | 2019 | 2 | 2027 | 2034 | 2041 |  | 3 | 1 | 2 |  | 2027
60208 | 2019 | 2 | 2027 | 2034 | 2041 |  | 3 | 1 | 2 |  | 2027
60209 | 2019 | 2 | 2027 | 2034 | 2041 |  | 3 | 1 | 2 |  | 2027
60211
60212 | 2018 | 3 | 2027 | 2034 | 2041 |  | 1 | 2 | 3 |  | 2041
60213 |  |  | 2029 | 2036 | 2043 |  | 1 | 2 | 3 |  | 2043
60214 | 2022 | 1 | 2028 | 2035 | 2042 |  | 2 | 3 | 1 |  | 2035
60215
60216
60217
60218
60219
60220
60221
60222
60223
60224 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60225
60226
60227
60228
60229 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60230 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60231 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60232 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60233 |  |  | 2031 | 2037 | 2044 |  | 1 | 2 | 3 |  | 2044
60234 |  |  | 2030 | 2037 | 2044 |  | 1 | 2 | 3 |  | 2044
60235
60236
60237
60238 | 2024 | 2 | 2030 | 2037 | 2044 |  | 3 | 1 | 2 |  | 2030
60239 | 2024 | 2 | 2030 | 2037 | 2044 |  | 3 | 1 | 2 |  | 2030
60240 | 2025 | 2 | 2025 | 2033 | 2040 |  | 2 | 3 | 1 |  | 2033
60241 | 2025 | 2 | 2025 | 2033 | 2040 |  | 2 | 3 | 1 |  | 2033
60242 | 2022 | 1 | 2028 | 2035 | 2042 |  | 2 | 3 | 1 |  | 2035
60243 |  |  | 2031 | 2038 | 2045 |  | 1 | 2 | 3 |  | 2045
60244
60245 | 2015 | 1
60246 |  |  | 2026 | 2032 | 2039 |  | 1 | 2 | 3 |  | 2039
60247
60248 |  |  | 2026 | 2032 | 2039 |  | 1 | 2 | 3 |  | 2039
60249 | 2013 | 1 | 2025 | 2031 |  |  | 2 | 3 |  |  | 2031
60252 | 2011 | 1 | 2026 | 2034 | 2041 |  | 2 | 3 | 1 |  | 2034
60253
60254
60255
60256
60257
60258 |  |  | 2028 | 2035 | 2041 |  | 1 | 2 | 3 |  | 2041
60259 |  |  | 2031 | 2043 |  |  | 1 | 2
60260 | 2023 | 1 | 2030 | 2037 | 2044 |  | 2 | 3 | 1 |  | 2037
60261
60262
60263
60264
60265
60266 | 2025 | 1 | 2025 | 2031 | 2038 |  | 1 | 2 | 3 |  | 2038
60267
60268
60269
60270
60271 | 2019 | 2 | 2026 | 2033 | 2040 |  | 3 | 1 | 2 |  | 2026
60273
60274
60275
60276
60277 | 2025 | 3 | 2025 | 2033 | 2040 |  | 3 | 1 | 2 |  | 2025
60279
60280 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60281
60282
60283
60284 |  |  | 2027 |  |  |  | 1
60285
60286
60287
60288
60289
60290
60291
60292
60293
60294
60295
60296
60297
60298
60299
60300
60301
60302
60303
60304 | 2024 | 3 | 2027 | 2033 | 2040 |  | 3 | 1 | 2 |  | 2027
60305
60306
60307 | 2025 | 1 | 2025 | 2032 | 2039 |  | 1 | 2 | 3 |  | 2039
60308 | 2024 | 2 | 2030 | 2037 | 2044 |  | 3 | 1 | 2 |  | 2030
60309
60310
60311
60312
60313
60315 |  |  | 2027 | 2034 | 2041 |  | 1 | 2 | 3 |  | 2041
60316 |  |  | 2029 | 2036 | 2043 |  | 1 | 2 | 3 |  | 2043
60317
60318
60319
60320
60321 |  |  | 2027 | 2034 | 2041 |  | 1 | 2 | 3 |  | 2041
60322 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60323
60324
60326
60327 | 2024 | 1 | 2030 | 2037 | 2044 |  | 2 | 3 | 1 |  | 2037
60328
60330
60331
60332
60333 | 2024 | 3 | 2033 | 2040 |  |  | 3 | 1 |  |  | 2033
60334
60335
60337 | 2025 | 3 | 2025 | 2033 | 2040 |  | 3 | 1 | 2 |  | 2025
60338 | 2025 | 1 | 2025 | 2031 |  |  | 1 | 2
60339
60340
60342
60343
60344
60345
60346 | 2021 | 2 | 2027 |  |  |  | 3 |  |  |  | 2027
60347
60348 | 2021 | 2 | 2028 | 2035 | 2042 |  | 3 | 1 | 2 |  | 2028
60349 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60350
60351 |  |  | 2026 | 2032 | 2039 |  | 1 | 2 | 3 |  | 2039
60352
60353
60354 | 2025 | 1 | 2029 | 2035 | 2042 |  | 2 | 3 | 1 |  | 2035
60355
60356
60357
60358 |  |  | 2025 | 2032 | 2039 |  | 1 | 2 | 3 |  | 2039
60359
60360
60361 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60362 |  |  | 2031 | 2038 |  |  | 1 | 2
60363 |  |  | 2031 | 2038 |  |  | 1 | 2
60364
60365
60366 |  |  | 2031 | 2038 |  |  | 1 | 2
60367
60368
60371
60374
60375
60376
60377 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60378
60379 |  |  | 2026 | 2032 | 2039 |  | 1 | 2 | 3 |  | 2039
60380
60381
60382 |  |  | 2028 | 2035 | 2042 |  | 1 | 2 | 3 |  | 2042
60383
60384 | 2020 | 2 | 2028 | 2035 | 2042 |  | 3 | 1 | 2 |  | 2028
60385
60386 |  |  | 2027 | 2034 | 2041 |  | 1 | 2 | 3 |  | 2041

## RpmDesignStandard
number of lanes | AADT lower limit | AADT upper limit | replacement cycle (years) | For planning purpose the adjustment factor [2 times of replacement cycle] | 2
2 |  | 6000 | 4
2 | 6000 | 18000 | 3
2 | 18000 |  | 2
4 |  | 10000 | 4
4 | 10000 | 30000 | 3
4 | 30000 | 75000 | 2
4 |  | 75000 | 2